## Slide 1
Business Integration Update
June 2011
Includes:
  Parking Deck Impact Assessment
  2012 Project Prioritization
Notes: <number>

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Update p. 3-7
    Project Portfolio Gantt Chart
      Sorted by go-live date
    Recent Developments
  Parking Deck Impact Assessment p. 8-10
    Introductory Comments
    Impact Assessment Results
    Endorsement Consideration (vote)
  2012 Project Prioritization p. 11-20
    Schedule
    Introductory Comments
    Details by Project Category
    Funding Summary
    Endorsement Consideration (vote)
Notes: <number>

## Slide 3: Project Portfolio – as of 6/3/2011 – Sorted by Go-Live Date
Date

## Slide 4: Project Portfolio – as of 6/3/2011 – Sorted by Go-Live Date
Date

## Slide 5: Project Portfolio – as of 6/3/2011 – Sorted by Go-Live Date
Date

## Slide 6: Project Portfolio – as of 6/3/2011 – Sorted by Go-Live Date
Date

## Slide 7: Project Portfolio – Recent Developments
TAC and Board Approved Several Additions to the PPL
  NPRR310, NPRR350, SCR764
Go-Lives Planned for June / July
  NPRR285 – Settlements portion
    Effective 6/6/2011
  NPRR341 – Remove AS Offers from SASM that Do Not Meet the Lead Time
    Effective 6/22/2011
  NPRR339 – Modifications to Heuristic Rules
    Effective 6/22/2011 – Day Ahead and Real Time
    Effective 7/20/2011 – CRR
  NPRR146 – ICCP Telemetry Information Submittals
    Effective 7/1/2011 if Board approves at June meeting
  NPRR323 – Correct DAM Credit Exposure Language and Enable Qualified Expiring CRRs to Offset PTP Bid Exposure
    Effective 7/20/2011
  NPRR282 – Dynamic Ramp Rates Use in SCED
    Effective 7/22/2011

## Slide 8: Parking Deck Impact Assessments – Phase 2 / 3 – Comments
ERCOT has completed the Impact Analysis for 10 of the NPRRs in the Phase 2 / Phase 3 portion of the Parking Deck
  Summary of results on the next slide
Since the 2012 project prioritization process is also underway, ERCOT has suggested delivery targets for these NPRRs
  See “Delivery Target” column on the next slide
  These dates coincide with future year funding recommendations (slides 15-16)
CBAs
  CBAs for these Parking Deck items are being worked in parallel with the approval process
  ERCOT will have draft CBAs available for review at the appropriate market subcommittee meetings in June
  Goal: Have CBAs ready for 6/23 PRS meeting
ERCOT will initiate market discussions on the remaining Parking Deck items
  These items will benefit from additional discussion before the IA is completed

## Slide 9: Parking Deck Impact Assessments – Phase 2 / 3 – IA Results
Rev Request | Description | Estimated Cost | Estimated Duration | Delivery Target
NPRR181 | FIP Definition Revision | $210k-$225k | 10-12 weeks | 2013
NPRR207 | Unit Deselection | $50k-$55k | 9-11 weeks | 2013
NPRR210 | Wind Forecasting Change to P50, Sync w/PRR841 | $45k-$55k | 8-16 weeks | 2013
NPRR222 | Half-Hour Start RUC Clawback | $15k-$20k | 5-7 weeks | 2012
NPRR240 | Proxy Energy Offer Curve | $50k-$60k | 12-14 weeks | 2013
NPRR241 | AIL Calc and Credit Reports Publish Corrections | $100k-$120k | 5-10 months | 2013
NPRR244 | Clarification of Other Binding Documents | $10k-$15k | n/a | 2011
NPRR256 | Sync w/PRR787, Add Non-Compliance Language to QSE Performance Standards | $120k-$135k | 9-10 months | 2013
NPRR258 | Sync with PRR824 and PRR833 | $145k-$160k | 8-10 weeks | 2011
NPRR272 | Definition and Participation of Quick Start Generation Resources | $30k-$35k | 20-22 weeks | 2012
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | TBD | TBD | TBD
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | TBD | TBD | 2012
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | TBD | TBD | TBD
SCR755 | ERCOT.com Website Enhancements | TBD | TBD | TBD
Further Discussion with the Market Requested
Completed Impact Analyses
*
* O&M effort – no project required

## Slide 10: Parking Deck Impact Assessments – Phase 2 / 3 – Endorsement
  Suggested endorsement language:
    <Market Subcommittee> endorses the Impact Analysis documents for the following Parking Deck revision requests :
      NPRR181: FIP Definition Revision
      NPRR207: Unit Deselection
      NPRR210: Wind Forecasting Change to P50, Sync with PRR841
      NPRR222: Half-Hour Start RUC Clawback
      NPRR240: Proxy Energy Offer Curve
      NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
      NPRR244: Clarification of Other Binding Documents
      NPRR256: Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards
      NPRR258: Sync with PRR824 and PRR833
      NPRR272: Definition and Participation of Quick Start Generation Resources
Notes: <number>

## Slide 11: 2012 Project Prioritization – Schedule
April 2011
  ERCOT prepares draft 2012 project list and reviews schedule with market
    Request input from the market on new additions
May 2011
  Initial review at market subcommittee meetings
    COPS (May 10)
    WMS (May 11)
    ROS (May 12)
    RMS (May 18)
June 2011
  Approval/endorsement by market subcommittees
    COPS (June 14)
    WMS (June 15)
    ROS (June 16)
    RMS (June 22)
    PRS (June 23)
July 2011
  Approval/endorsement by TAC (July 7)
  Available for F&A and Board review (July 18)

## Slide 12: 2012 Project Prioritization – Introductory Comments
ERCOT is working diligently to limit the 2012 budget to the most critical needs
$15M has been allocated for capital projects
Is $15M sufficient for ERCOT’s capital project needs?
  Answer: Yes
  Due to the recent Data Center Hardware project, 2012 is expected to have a more labor-intensive project mix than usual
  Supporting information:
    2012 – total project labor estimate = 108,000 hours
    2011 – YTD internal PPL project labor = $2.31M (~35,500 hours)
    2010 – total internal PPL project labor = $2.73M (~42,000 hours)
    2009 – total internal PPL project labor = $3.96M (~61,000 hours)

## Slide 13: Project Category Definitions
Key Areas of Focus (Project Categories)
  Regulatory
    Required by Legislature, PUCT, NERC, FERC or legal ruling
  Business Strategy
    Market driven enhancements and efficiencies
    ERCOT strategic initiatives
  Efficiencies & Enhancements
    Internally driven operational improvements
    Enhanced customer service
  Technical Foundation
    Required maintenance and upgrades
    Technical evolution and performance
    Systemic growth

## Slide 14: 2012 Project Prioritization – Regulatory
*
*
* Projected carryover project from 2011

## Slide 15: 2012 Project Prioritization – Business Strategy (page 1)
*
* Projected carryover project from 2011
*
*
*

## Slide 16: 2012 Project Prioritization – Business Strategy (page 2)
*
* Projected carryover project from 2011

## Slide 17: 2012 Project Prioritization – Efficiencies and Enhancements
*
* Projected carryover project from 2011
*

## Slide 18: 2012 Project Prioritization – Technical Foundation
*
* Projected carryover project from 2011
*
*
*

## Slide 19: 2012 Project Prioritization - Funding Summary
Project Category | Target Funding | Projects Started in Previous Years | New 2012 Projects
Regulatory | $ 1,600,000 | 2 | 1
Business Strategy | $ 5,950,000 | 5 | 15
Efficiencies & Enhancements | $ 2,050,000 | 2 | 9
Technical Foundation | $ 6,500,000 | 4 | 7
Total | $ 16,100,000 | 13 | 32
ERCOT will manage within the projected $15M project funding allocation.
As active projects move through the project lifecycle and new projects are considered for initiation, they will be reassessed for criticality, cost/benefit and resource availability against other projects in the portfolio.
Inclusion on the preliminary 2012 PPL does not guarantee funding!
*
* Projects projected to be funded in 2012
*

## Slide 20: 2012 Project Prioritization – Motion
Suggested Motion
Motion to approve/endorse:
  ERCOT’s proposal to fund 2012 projects in the amount of $15M
  ERCOT’s initial project rank and preliminary funding by project category
    <as amended by [market subcommittee]>
Notes: <number>