## Slide 1: NPRR 365 Change in Resource Outage Approvals from 8 to 90 Days
Woody Rickerson
Director Grid Coordination
5-17-11

## Slide 2: What it does . .
Enables ERCOT to more efficiently coordinate transmission and resource outage requests by:
Replacing the current 8-day automatic acceptance Resource timeline with a 90-day timeline. Outages received with less than 90-days notice would need ERCOT approval and be subject to ERCOT coordination.
Aligning Resource Outage timelines with Transmission Outage timelines within the 90-day window.
More clearly defining ERCOT’s role in withdrawing approval on previously approved Resource Outages in anticipation of emergency situations.

## Slide 3: Benefits
Increased accuracy of the CRR Model.
Decreased re-coordination of transmission Outages for both ERCOT and TSPs.
Increases ERCOT’s overall coordination of all Outages.
Clarifies the process for ERCOT to withdraw approval of “Accepted” or “Approved” Resource Outages.
Provides for a more efficient operation of the ERCOT System.
Detriments
Decreased flexibility for Resource owners scheduling Outages.
Increased work required on the part of ERCOT to approve instead of “Accept” Resource Outages.

## Slide 4
ISO Resource Outage Coordination
New England ISO – Planned outages are submitted before February 15th each year for the Commitment Period which starts in June. Planned Outages are subject to NEISO approval and rescheduling. Maintenance outages can be submitted up to 1 day ahead and are subject to NEISO coordination.
Californian ISO – Resource planned maintenance outages are submitted by October 15th, for the following calendar year. The submittals look forward 15 months. The plans are updated on a quarterly basis. CAISO approve or reject all requests within 30 days of receipt. Maintenance outages are evaluated on a daily basis and are subject to CAISO coordination.
Midwest ISO – Resources submit Planned outages 24 months in advance and update the schedule on a daily basis. All requests are subject MISO approval. Maintenance outages are evaluated on a daily basis and are subject to MISO approval.
PJM – Resources submit Planned Outages at least 30-days in advance of the outage. PJM can approve or reject the requests. Maintenance outages (limited to 9 days during peak times) can be submitted at any time and are subject to PJM postponement or rejection.
NYISO – Resources provide a 3-year schedule of Planned outages by July 1st each year (6 months prior to that start of the 3-yr period). The Planned outages are subject to NYISO review and rescheduling. Maintenance outages must be submitted 30-days in advance and are subject to NYISO approval and coordination.
ERCOT – Planned Resource Outages are submitted on a rolling 12-month plan. ERCOT accepts all Outages submitted with more than 8 days notice and approves or rejects Outages with less than 8 days or less notice.

## Slide 5
ERCOT Nodal Outage Statistics
46,287 Outages submitted 12/1/2010 – 5/5/11 (Transmission and Resource including all types)
3,718 Outages (~ 8%) were outages on Unit Outages including
    1751 Forced Outages
    647 Cancelled Outages
    599 Planned Outages
    486 Maintenance Level Outages
    224 Unavoidable Extensions
    11 Cancelled
Of the 599 Planned Resource Outages
    171 (28%) were subject to ERCOT “Approval” or “Rejection” (ERCOT received less than 8 days notice)
    None were rejected
2005 through 2010
    From all the Planned Resource Outages that were subject to ERCOT “Approval” or “Rejection” (18,678) only 0.4% were rejected by ERCOT and 0.1% had approval withdrawn by ERCOT.

## Slide 6
No Reliability Problems
Reliability Problems
CIM-derived EMS case containing
Date specific Topology
Load Forecast
Starting Gen. Pattern
Contingency file
Wind Scenarios
Previously Approved or Accepted
Resource and Transmission Outages
Outages Awaiting ERCOT Approval
Reject
Approve
Order of Receipt
Coordinate Outages
Modify Gen Pattern
Evaluate RAPs, MPs,
TOAPs
ERCOT Nodal Outage Statistics
NPRR365 would allow ERCOT to coordinate Resource Outages with Transmission outages (third layer) instead of simply accepting them as submitted (second layer). By allowing ERCOT the ability to coordinate all outages the amount of maintenance work that can be reliably accomplished is increased. In addition, the amount of re-coordination needed to accommodate late arriving resource outages would be decreased.

## Slide 7
Transmission
Resource
Transmission
Transmission
App
Approval
Target Day
To Start
Outage
BLOCK
DEADLINE
CRR Snapshot
45-day
TD + 45
9-day
TD + 30
4-day
App
TD+9
TD+4
TD+3
TD+1
Existing ERCOT Planned Outage Evaluation Timelines
Approval
TD + 90
TD + 75
90-day
Resources outages submitted > than 8 days out are automatically accepted
TD+8
Resource outages
That come in with
Less than 8 days notice
Are subject to ERCOT
Approval/rejection
Within 8 business
hours
3-d
A
TD+70
TD+40
Rolling Deadlines
Earliest Snapshot –
for outage starting
near first of month
Latest Snapshot -
for outage starting
near end of month
R
A

## Slide 8
Resource
Transmission
App
Approval
Target Day
To Start
Outage
BLOCK
DEADLINE
CRR Snapshot
45-day
TD +45
9-day
TD + 30
4-day
App
TD+9
TD+4
TD+3
TD+1
NPRR365 - ERCOT Planned Outage Evaluation Timelines
Approval
TD + 90
TD + 75
90-day
3-d
A
TD+70
TD+40
Earliest Snapshot –
for outage starting
near first of month
Latest Snapshot -
for outage starting
near end of month
4-day
9-day
45-day
3-d
90-day
Automatically
Accepted
Resource
Transmission

## Slide 9
BLOCK
DEADLINE
CRR Snapshot
Target Day
To Start
Outage
Planned Resource Outage Breakdown by Time
12/1/2011 -5/5/2011 (Nodal)
TD+70
TD+40
2 Week
Notice
4 Week
Notice
13 Week
Notice
(~90 days)
8 Week
Notice
Planned
Resource
Outages
(599 total)
13 %
13 %
5%
59 %
10%
~85% submitted after CRR snapshot

## Slide 10
BLOCK
DEADLINE
CRR Snapshot
Target Day
To Start
Outage
Resource Outage Breakdown for all Planned Resource Outages
12/1/2011 -5/5/2011 (Nodal)
599 Total Outages*
TD+80
TD+50
2 Week
Notice
4 Week
Notice
13 Week
Notice
(~90 days)
8 Week
Notice
Resource Outages
Lasting less than
1 day
Resource Outages
lasting more than
14 days
Resource Outages
lasting between
1 and 14 days
16 %
5%
7 %
18 %
17 %
16 %
0 %
8%
9%
88 %
47 %
37 %
0 %
12%
20 %
93 total
276 total
209 total
*Does not include 486 Maint Level Outages and 1753 Forced Outages

## Slide 11
Resource Outage Breakdown Notice vs Duration
April 2011 (149 Planned Resource Outages)

## Slide 12
Resource Outage Breakdown Notice vs Duration
May 2011 (153 Planned Resource Outages)

## Slide 13
Planned Transmission Outages Nodal
12/1/2010 to 5/5/2011 (21,961)