## Slide 1
Business Integration Update to PRS
June 2011
Includes:
  2011 Project Portfolio Update
  Parking Deck Impact Assessment
  2012 Project Prioritization
Notes: <number>

## Slide 2: Business Integration Update – Agenda (revised)
  2011 Project Portfolio Update p. 3-7
    Project Portfolio Gantt Chart
      Sorted by go-live date
    Recent Developments
  Parking Deck Impact Assessment p. 8-10
    Introductory Comments
    Impact Assessment Results
    Endorsement Consideration (vote)
  2012 Project Prioritization p. 11-20
    Schedule
    Introductory Comments
    Funding Summary
    Details by Project Category
    Endorsement Consideration (vote)
  Appendix p. 21-26
    Summary Project Descriptions
Notes: <number>

## Slide 3: Project Portfolio – as of 6/13/2011 – Sorted by Go-Live Date
Date

## Slide 4: Project Portfolio – as of 6/13/2011 – Sorted by Go-Live Date
Date

## Slide 5: Project Portfolio – as of 6/13/2011 – Sorted by Go-Live Date
Date

## Slide 6: Project Portfolio – as of 6/13/2011 – Sorted by Go-Live Date
Date

## Slide 7: Project Portfolio – Recent Developments
TAC and Board Approved Several Additions to the PPL
  NPRR310, NPRR350, SCR764
Go-Lives Planned for June / July
  NPRR285 – Settlements portion
    Effective 6/6/2011
  NPRR341 – Remove AS Offers from SASM that Do Not Meet the Lead Time
    Effective 6/22/2011
  NPRR339 – Modifications to Heuristic Rules
    Effective 6/22/2011 – Day Ahead and Real Time
    Effective 7/20/2011 – CRR
  NPRR146 – ICCP Telemetry Information Submittals
    Effective 7/1/2011 if Board approves at June meeting
  NPRR323 – Correct DAM Credit Exposure Language and Enable Qualified Expiring CRRs to Offset PTP Bid Exposure
    Effective 7/20/2011
  NPRR282 – Dynamic Ramp Rates Use in SCED
    Effective 7/22/2011

## Slide 8: Parking Deck Impact Assessments – Phase 2 / 3 – Comments
ERCOT has completed the Impact Analysis for 10 of the NPRRs in the Phase 2 / Phase 3 portion of the Parking Deck
  Summary of results on the next slide
Since the 2012 project prioritization process is also underway, ERCOT has suggested delivery targets for these NPRRs
  See “Delivery Target” column on the next slide
  These dates coincide with future year funding recommendations (slides 16-17)
CBAs
  CBAs for these Parking Deck items are being worked in parallel with the approval process
  Goal: Have draft CBAs ready for 6/23 PRS meeting and final CBAs ready for 7/7 TAC
ERCOT will initiate market discussions on the remaining Parking Deck items
  These items will benefit from additional discussion before the IAs are completed

## Slide 9: Parking Deck Impact Assessments – Phase 2 / 3 – IA Results
Rev Request | Description | Estimated Cost | Estimated Duration | Delivery Target
NPRR181 | FIP Definition Revision | $210k-$225k | 10-12 weeks | 2013
NPRR207 | Unit Deselection | $50k-$55k | 9-11 weeks | 2012
NPRR210 | Wind Forecasting Change to P50, Sync w/PRR841 | $45k-$55k | 8-16 weeks | 2013
NPRR222 | Half-Hour Start RUC Clawback | $15k-$20k | 5-7 weeks | 2012
NPRR240 | Proxy Energy Offer Curve | $50k-$60k | 12-14 weeks | 2013
NPRR241 | AIL Calc and Credit Reports Publish Corrections | $100k-$120k | 5-10 months | 2013
NPRR244 | Clarification of Other Binding Documents | $10k-$15k | n/a | 2011
NPRR256 | Sync w/PRR787, Add Non-Compliance Language to QSE Performance Standards | $120k-$135k | 9-10 months | 2013
NPRR258 | Sync with PRR824 and PRR833 | $55k-$60k | 8-10 weeks | 2011
NPRR272 | Definition and Participation of Quick Start Generation Resources | $145k-$160k | 20-22 weeks | 2012
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | TBD | TBD | TBD
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | TBD | TBD | 2012
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | TBD | TBD | TBD
SCR755 | ERCOT.com Website Enhancements | TBD | TBD | TBD
Further Discussion with the Market Requested
Completed Impact Analyses
*
* O&M effort – no project required

## Slide 10: Parking Deck Impact Assessments – Phase 2 / 3 – Endorsement
  Suggested endorsement language:
    PRS endorses the Impact Analysis documents for the following Parking Deck revision requests :
      NPRR181: FIP Definition Revision
      NPRR207: Unit Deselection
      NPRR210: Wind Forecasting Change to P50, Sync with PRR841
      NPRR222: Half-Hour Start RUC Clawback
      NPRR240: Proxy Energy Offer Curve
      NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
      NPRR244: Clarification of Other Binding Documents
      NPRR256: Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards
      NPRR258: Sync with PRR824 and PRR833
      NPRR272: Definition and Participation of Quick Start Generation Resources
Notes: <number>

## Slide 11: 2012 Project Prioritization – Schedule
April 2011
  ERCOT prepares draft 2012 project list and reviews schedule with market
    Request input from the market on new additions
May 2011
  Initial review at market subcommittee meetings
    COPS (May 10)
    WMS (May 11)
    ROS (May 12)
    RMS (May 18)
June 2011
  Approval/endorsement by market subcommittees
    COPS (June 14)
    WMS (June 15)
    ROS (June 16)
    RMS (June 22)
    PRS (June 23)
July 2011
  Approval/endorsement by TAC (July 7)
  Available for F&A and Board review (July 18)



COPS endorsed 3 changes in rank

## Slide 12: 2012 Project Prioritization – Introductory Comments
ERCOT is working diligently to limit the 2012 budget to the most critical needs
$15M has been allocated for capital projects
Is $15M sufficient for ERCOT’s capital project needs?
  Answer: Yes
  Due to the recent Data Center Hardware project, 2012 is expected to have a more labor-intensive project mix than usual
  Supporting information:
    2012 – total project labor estimate = 108,000 hours
    2011 – YTD internal PPL project labor = $2.31M (~35,500 hours)
    2010 – total internal PPL project labor = $2.73M (~42,000 hours)
    2009 – total internal PPL project labor = $3.96M (~61,000 hours)

## Slide 13: Project Category Definitions
Key Areas of Focus (Project Categories)
  Regulatory
    Required by Legislature, PUCT, NERC, FERC or legal ruling
  Business Strategy
    Market driven enhancements and efficiencies
    ERCOT strategic initiatives
  Efficiencies & Enhancements
    Internally driven operational improvements
    Enhanced customer service
  Technical Foundation
    Required maintenance and upgrades
    Technical evolution and performance
    Systemic growth

## Slide 14: 2012 Project Prioritization - Funding Summary
Project Category | Target Funding | Projects Started in Previous Years | New 2012 Projects
Regulatory | $ 1,600,000 | 2 | 1
Business Strategy | $ 5,950,000 | 5 | 15
Efficiencies & Enhancements | $ 2,050,000 | 2 | 9
Technical Foundation | $ 6,500,000 | 4 | 7
Total | $ 16,100,000 | 13 | 32
ERCOT will manage within the projected $15M project funding allocation.
As active projects move through the project lifecycle and new projects are considered for initiation, they will be reassessed for criticality, cost/benefit and resource availability against other projects in the portfolio.
Inclusion on the preliminary 2012 PPL does not guarantee funding!

## Slide 15: 2012 Project Prioritization – Regulatory
*
*
* Projected carryover project from 2011
See Appendix for brief project descriptions

## Slide 16: 2012 Project Prioritization – Business Strategy (page 1)
*
* Projected carryover project from 2011
*
*
*
*


Ranking changes by COPS


See Appendix for brief project descriptions

## Slide 17: 2012 Project Prioritization – Business Strategy (page 2)
See Appendix for brief project descriptions

## Slide 18: 2012 Project Prioritization – Efficiencies and Enhancements
*
* Projected carryover project from 2011
*
See Appendix for brief project descriptions

## Slide 19: 2012 Project Prioritization – Technical Foundation
*
* Projected carryover project from 2011
*
*
*
See Appendix for brief project descriptions

## Slide 20: 2012 Project Prioritization – Motion
Suggested Motion
Motion to approve/endorse ERCOT’s initial project rank and preliminary funding by project category
    <as amended by PRS>
Notes: <number>

## Slide 21
Appendix
Notes: <number>

## Slide 22: Project Descriptions – Regulatory
Rank | Project Name | Project Description
1 | REC Enhancements | Enhance the REC tool to comply with PUCT rules and incorporate additional functionality
2 | CFTC Compliance | Funds for use in a project to support ERCOT’s application for a CFTC exemption
3 | Compliance Software Tool | Automate the tracking of compliance obligations
Notes: <number>

## Slide 23: Project Descriptions – Business Strategy
Rank | Project Name | Project Description
1 | TX SET 4.0 | Continuation of TX SET 4.0 project
2 | SCR760 | SCR760 Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models
3 | Cyber Security Project #1 | Enhancement to system administrator infrastructure
4 | Cyber Security Project #2, Phase 1 | Enhancement to virus protection
5 | TSAT Wind Model | Implement wind models in TSAT application. Enhance reliability by delivering closer to real time stability information.
6 | PRR830/NPRR269 – Reactive Power Capability | Potential system changes needed due to final resolution between ERCOT and market stakeholders
7 | Demand Response / Look-Ahead SCED | Initial planning phase of the next major evolutionary phase of the Nodal systems (Nodal 2.0)
8 | Facilities Project | Funding reserved for relocation of remaining functions from the Met Center (if necessary)
9 | Cyber Security Project #3 | Enhancement to remote access capability
10 | Cyber Security Project #4 | Enhancement to malware protection
Notes: <number>

## Slide 24: Project Descriptions – Business Strategy
Rank | Project Name | Project Description
11 | NPRR347 – Single Daily Invoice | NPRR347 - Single Daily Invoice
12 | NPRR260 – MIS Secure Access | NPRR260 - MIS Secure Access
13 | MarkeTrak Upgrade/Enhancements | Enhance underlying MarkeTraksoftware and deploy enhancements agreed upon by ERCOT and market stakeholders
14 | TML Transition to MIS | Migrate remaining functions that support the Retail market from TML to MIS
15 | Planning Site Transition to MIS | Migrate Planning functions/data that currently reside on the POI to MIS
16 | NPRR222–Half Hour Start Clawback | NPRR222 - Half Hour Start Clawback
17 | Cyber Security Project #2, Phase 2 | Extend capabilities developed in the phase 1
18 | NPRR326 – Adjust RT SPP Calc. | NPRR326-Adjut RT SPP Calc.
19 | NPRR272 – Quick Start Resources | NPRR272 - Quick Start Resources
20 | NPRR207 – Unit Deselection | NPRR207 - Unit Deselection
Notes: <number>

## Slide 25: Project Descriptions – Efficiencies / Enhancements
Rank | Project Name | Project Description
1 | Incremental Update Capability – Phase 1 | Provide incremental update capability to all production systems for all model related data
2 | MP Online Data Entry – Phase 1 | Allow Market Participant and Resource registration through an electronic user interface to submit and view MP and Resource registration information
3 | CMS and MIR Replacement | Replace applications used to deploy web content to enhance scalability and reliability
4 | ERCOT Website Enhancements 2012 | Continuous improvement of www.ercot.com and public market communications
5 | Macomber Map NERC SA/Compliance Enhancements | Enhance the Macomber Map application to further address control room situational awareness
6 | IGRID Implementation | Improve operator situational awareness by bringing the Market, Outage Scheduler and EMS into a set of operator dashboards
7 | Contingency Functionality Enhancements | Enhance NMMS capabilities to allow business owners to submit, via NOMCR, contingency group configurations with a higher level of specificity
8 | SMTNET Improvements | SMTNET time point improvements to troubleshoot time points
9 | MP Communications Tool | Create a tool to be placed in market participant control rooms, to ensure that they are receiving continual high-level status information
10 | Smartphone Interface (“MyGrid”) | Create a smart-device (e.g., Android, Apple iOS, Blackberry) application showing a high-level view of system status
11 | OA Grid Health Operator View | Give operators a view into overall grid health that incorporates a variety of operational parameters into a single graphical dashboard interface
Notes: <number>

## Slide 26: Project Descriptions – Technical Foundation
Rank | Project Name | Project Description
1 | Data Center Migration | Completion of Data Center Hardware project
2 | Minor Cap – Critical – 2012 | Critical Minor Cap items for 2012
3 | Information Lifecycle Management Phase 2 | Continuation of project to implement a strategy for efficient data storage utilization while continuing to meet Protocol data retention requirements
4 | Settlement Upgrade | Continuation of project to rewrite the modules of the settlement system so they run more efficiently and are easier to maintain
5 | Oracle 11g Upgrade | Upgrade database software to the latest version
6 | EMS Upgrade | Upgrade EMS software to the latest version
7 | Enterprise Data Warehouse Platform Transition | Evaluate the platform that is the core foundation of market data transparency and archival requirements to determine the long-term approach to increasing overall reliability and maximize capacity utilization
8 | Job Scheduling Upgrade v8 | Upgrade batch job software to a more current version
9 | Siebel Upgrade | Upgrade software to the latest version
10 | NMMS Upgrade | Upgrade NMMS software to the latest version
11 | Data Center Growth & Asset Replacement | Funding for continued demand for growth of computing environment (storage, servers, etc.)
Notes: <number>