## Nodal Operating Guides
NERC RELIABILITY WORKING GROUP TASK LIST
Primary Assignee | Secondary Assignee | NERC Reliability Standard | Issue to be Addressed | Proposed Resolution Action | Action Taken | Due By
TBD |  | PER-005-1, R3.1 | There is language that requires TOPs to using "simulating technology". How can this be addressed in the region? | Consult with ERCOT ISO training group, as well as Operations Training Seminar group. |  | To be addressed at 07/28/2011 NRWG meeting
JC Culberson |  | TPL-001 - TPL-004 | Ensure the requirements are able to be met by ERCOT TPs. | Perhaps we need to schedule a joint NRWG/PLWG meeting to address TPL-001 - TPL-004 compliance issues within the region. |  | TBD
JC Culberson |  | TOP-002-2, R2 | Operations personnel to participate in the planning process, and how that may help the valley limit issues (different limits in the planning horizon than those established in the operating horizon). | Identification of the appropriate mechanism to perform this requirement within theERCOT Region. Propose a solution to these issues that may not show up in the planning process, but manifest themselves in operational issues. |  | To be addressed at 07/28/2011 NRWG meeting
Matt Stout |  | FAC-010 - FAC-014 | IROL Training | Find out if ERCOT ISO will be conducting IROL training this year, and if MPs are allowed to attend. |  | To be addressed at 07/28/2011 NRWG meeting
Matt Stout |  | NA | CEII - Inquire about CRR maps and the need for the level of detail that is contained in the .kml files on MIS. | Reach out to Steve Reedy and to the NDSWG to determine the need for one-line diagrams for the purpose of the CRR auction/market. |  | To be addressed at 07/28/2011 NRWG meeting
DeAnn Walker |  | NA | Reach out to internal contacts to find out if there is a reliability purpose for the CRR maps (containing one-line diagrams) on the CRR portion of the MIS. | Find out if other groups use the maps in question. Consult with ERCOT ISO to address the reason/necessity for posting CEII information to the MIS. |  | To be addressed at 07/28/2011 NRWG meeting
RESOLVED ISSUES
Primary Assignee | Secondary Assignee | NERC Reliability Standard | Issue to be Addressed | Proposed Resolution Action | Action Taken | Date Completed
John Moore | JC Culberson | FAC-008 & FAC-009 | Facility Ratings Methodology must be developed by Tos and made available to RC, TOPs, TPs, and PC that have responsibilities in the TO's area. | Develop Ratings Methodology in accordance with FAC-008-3. | Project 2009-06: http://www.nerc.com/filez/standards/Reliability_Standards_Under_Development.html Addressed on the NSRS call - 04-27-2011 The NERC Board of Trustees adopted the standard on May 24, 2011. http://www.nerc.com/filez/standards/Project_2009-06_Facility_Ratings.html | 2011-04-28