## 2012
| Flight Schedule | 0312 | 0912 | 1008 | 0109 | 0409 | 0709 | 1009 | 0312 | 0912 | 1008 | 0109 | 0409 | 0709 | 1009 | 0312 | 0912 | 1008 | 0109 | 0409 | 0709 | 1009
|  | Date | Date | Date | Date | Date | Date | Date | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Days between Tasks | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week | Day of Week
Activity
1 | Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | 2012-01-18 | 2012-07-18 | 2008-08-13 | 2008-11-05 | 2009-02-04 | 2009-05-13 | 2009-08-12 | [7 empty] | Wed | Wed | Wed | Wed | Wed | Wed | Wed
2 | Signup begins | 2012-02-15 | 2012-08-15 | #REF! | #REF! | #REF! | #REF! | #REF! | 7 | 7 | 7 | 6 | 6 | 6 | 6 | Wed | Wed | #REF! | #REF! | #REF! | #REF! | #REF!
3 | FLIGHT DEADLINE | 2012-02-22 | 2012-08-22 | #REF! | #REF! | #REF! | #REF! | #REF! | 7 | 7 | 7 | 8 | 8 | 8 | 8 | Wed | Wed | #REF! | #REF! | #REF! | #REF! | #REF!
The following 4 steps must be completed by 5 PM CST on the deadline for new CRs:
1. CR must have submitted ERCOT LSE Application and Application Fee
2. CR must have filed for PUC REP Certification
3. TW created on ERCOT Retail Testing Website
4. Sent an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com
The following steps must be completed by 5 PM CST on the deadline for current MPs:
1. TW updated on ERCOT Retail Testing Website
2. Sent an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com
4 | ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | 2012-02-24 | 2012-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Fri | Fri | #REF! | #REF! | #REF! | #REF! | #REF!
5 | Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | 2012-02-24 | 2012-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fri | Fri | #REF! | #REF! | #REF! | #REF! | #REF!
6 | Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | 2012-02-24 | 2012-08-24 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Fri | Fri | #REF! | #REF! | #REF! | #REF! | #REF!
7 | MPs to start scheduling connectivity | 2012-02-27 | 2012-08-27 | #REF! | #REF! | #REF! | #REF! | #REF! | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Mon | Mon | #REF! | #REF! | #REF! | #REF! | #REF!
9 | TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | 2012-02-27 | 2012-08-27 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Mon | Mon | #REF! | #REF! | #REF! | #REF! | #REF!
10 | Connectivity Testing kick-off Conference Call - Mandatory for all Testing Participants (black-out ends) | 2012-02-28 | 2012-08-28 | #REF! | #REF! | #REF! | #REF! | #REF! | 1 | 1 | 1 | 1 | 1 | 1 | 1 | Tue | Tue | #REF! | #REF! | #REF! | #REF! | #REF!
11 | Connectivity Testing begins for all Testing Participants | 2012-02-28 | 2012-08-28 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tue | Tue | #REF! | #REF! | #REF! | #REF! | #REF!
12 | Connectivity Test (CON51) and Penny Test (CON52) begins for all New Testing Participants | 2012-02-28 | 2012-08-28 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tue | Tue | #REF! | #REF! | #REF! | #REF! | #REF!
13 | TDSPs communicate Test bed load to Trading Partners and ERCOT | 2012-03-19 | 2012-09-17 | #REF! | #REF! | #REF! | #REF! | #REF! | 20 | 20 | 6 | 20 | 20 | 6 | 6 | Mon | Mon | #REF! | #REF! | #REF! | #REF! | #REF!
| TDSP Test Bed Load Days* | [7 empty] | 24 | 24 | 10 | 24 | 24 | 10 | 10
14 | Flight Kick off Conference Call - Mandatory for all Testing Participants | 2012-03-23 | 2012-09-21 | #REF! | #REF! | #REF! | #REF! | #REF! | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Fri | Fri | #REF! | #REF! | #REF! | #REF! | #REF!
15 | Conference Calls begin – Day 1 Transactions flow | 2012-03-26 | 2012-09-24 | #REF! | #REF! | #REF! | #REF! | #REF! | 3 | 3 | 3 | 3 | 3 | 3 | 3 | Mon | Mon | #REF! | #REF! | #REF! | #REF! | #REF!
16 | Flight tentatively scheduled to conclude | 2012-05-08 | 2012-11-06 | #REF! | #REF! | #REF! | #REF! | #REF! | 43 | 43 | 43 | 43 | 43 | 43 | 43 | Tue | Tue | #REF! | #REF! | #REF! | #REF! | #REF!
17 | Contingency Testing scheduled to conclude for Flight (black-out starts) | 2012-05-25 | 2012-11-21 | #REF! | #REF! | #REF! | #REF! | #REF! | 17 | 15 | 21 | 0 | 21 | 21 | 21 | Fri | Wed | #REF! | #REF! | #REF! | #REF! | #REF!
18 | PROD implementation scheduled for TX SET V4.0 | 2012-06-02 | N/A
19 | Contingency PROD implementation scheduled for TX SET V4.0 | 2012-06-09 | N/A
|  | 76 | 76 | #REF! | #REF! | #REF! | #REF! | #REF! | 93 | 91 | 83 | 76 | 97 | 83 | 83
| Next Flight Deadline | 2012-08-22 | 2013-01-09 | #REF! | #REF! | #REF! | #REF! |  | 0312 | 0912 | 1008 | 0109 | 0409 | 0709 | 1009 | 0312 | 0912 | 1008 | 0109 | 0409 | 0709 | 1009
| Time to Market** | 76 | 76 | #REF! | #REF! | #REF! | #REF! | #REF! | 76 | 76 | #REF! | #REF! | #REF! | #REF! | #REF!
*TDSP Test Bed Load Days is calculated by subtracting the date the testing participants is communicated to the TDSPs from the date they are required to communicate the completed Test bed Load
**Time to Market is calculated by subtracting the Flight Deadline from the date Flight tentatively scheduled to conclude
7 days
Formulas:
Date = [Date, row above]+28
Date = [Date, row above]+[Days between Tasks]