June 2011


	[image: image1.jpg]ERCOI




	
	System Planning 



	
	
	

	
	
	Monthly Status Report

June 2011


	
	Report Highlights
	

	
	
	

	
	· ERCOT is currently tracking 205 active generation interconnection requests totaling over 63,000 MW.  This includes over 37,000 MW of wind generation.
	

	
	· ERCOT  is currently reviewing proposed transmission improvements with a total cost of $622.4 Million

· Transmission Projects endorsed in 2011 total $23.6 Million

· All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion

· Transmission Projects energized in 2011 total about $174.0 million


	


Table of Contents
11.
Generation Interconnection


11.1
New Generation Registering for Commercial Operations


41.2
Publicly Disclosed Generation Interconnection Projects


61.3
Generation Projects Undergoing Full Interconnection Studies (not otherwise public)


81.4
Wind Generation


102.
Regional Planning Group Project Reviews


113.
Congestion Costs


134.
Wind Generation as a Percent of Load


145.
Planning Model Activities


156.
Other Notable Activities





1.
Generation Interconnection 
Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.  

1.1 New Signed Generation Interconnection Agreements – none this period
1.2 New Generation Registering for Commercial Operations
The total installed wind capacity is now reported as 9,452 MW by the resource owners through the registration process. Capacity by North, South and West is 292 MW, 1216 MW, and 7943 MW respectively. 850 MW is able to switch between the West and South zones.
Summary of Active Generation Interconnection Requests
	GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED

	Currently tracking 205 active generation interconnection or change requests

	As of June 30, 2011
	North
	South
	West
	Total

	Security Screening Study
	1
	2
	5
	8

	SSS Completed
	3
	7
	23
	33

	Full Interconnect Study
	20
	19
	94
	133

	FIS Completed
	1
	3
	6
	10

	Interconnect Agreement Completed 
	8
	9
	4
	21

	Capacity under Interconnection Agreements
	5,122
	4,404
	550
	10,076

	Capacity for Grid, MW
	17,431
	12,043
	34,080
	63,554

	Wind Capacity, MW
	3,369
	3,319
	30,724
	37,412


[image: image2.wmf]0

20,000

40,000

60,000

80,000

100,000

120,000

0

50

100

150

200

250

300

350

400

J

a

n

-

0

6

F

e

b

-

0

6

M

a

r

-

0

6

A

p

r

-

0

6

M

a

y

-

0

6

J

u

n

-

0

6

J

u

l

-

0

6

A

u

g

-

0

6

S

e

p

-

0

6

O

c

t

-

0

6

N

o

v

-

0

6

D

e

c

-

0

6

J

a

n

-

0

7

F

e

b

-

0

7

M

a

r

-

0

7

A

p

r

-

0

7

M

a

y

-

0

7

J

u

n

-

0

7

J

u

l

-

0

7

A

u

g

-

0

7

S

e

p

-

0

7

O

c

t

-

0

7

N

o

v

-

0

7

D

e

c

-

0

7

J

a

n

-

0

8

F

e

b

-

0

8

M

a

r

-

0

8

A

p

r

-

0

8

M

a

y

-

0

8

J

u

n

-

0

8

J

u

l

-

0

8

A

u

g

-

0

8

S

e

p

-

0

8

O

c

t

-

0

8

N

o

v

-

0

8

D

e

c

-

0

8

J

a

n

-

0

9

F

e

b

-

0

9

M

a

r

-

0

9

A

p

r

-

0

9

M

a

y

-

0

9

J

u

n

-

0

9

J

u

l

-

0

9

A

u

g

-

0

9

S

e

p

-

0

9

O

c

t

-

0

9

N

o

v

-

0

9

D

e

c

-

0

9

J

a

n

-

1

0

F

e

b

-

1

0

M

a

r

-

1

0

A

p

r

-

1

0

M

a

y

-

1

0

J

u

n

-

1

0

J

u

l

-

1

0

A

u

g

-

1

0

S

e

p

-

1

0

O

c

t

-

1

0

N

o

v

-

1

0

D

e

c

-

1

0

J

a

n

-

1

1

F

e

b

-

1

1

M

a

r

-

1

1

A

p

r

-

1

1

M

a

y

-

1

1

J

u

n

-

1

1

M

W

 

C

a

p

a

c

i

t

y

P

r

o

j

e

c

t

 

C

o

u

n

t

# In

-

Service ** 

# Signed Interconnect Agreement

# Projects Cancelled ***

# Completed Full Study

# in Full Study

# Screening Study Complete

# Initial Screening Study

MW Capacity Under Study * 

MW In Commercial Operation **

* Nameplate capacity will change across time due to additional projects, cancellations,    

expirations, adjustments from study results, and projects being placed in service.

** Having begun commercial 

operation since January 2006

*** Began tracking cancellations by 

month in March 2008


	Fuel Type
	Confidential Projects (MW)
	Projects Under Full Study (MW)
	Projects w/ Interconnect Agreement/Public Letter (MW)
	Grand Total (MW)

	Gas-CombinedCycle
	
	
	5,297
	11,647

	Gas-All Other
	
	
	
	715

	    Total Gas
	316
	6,749
	5,297
	12,362

	Nuclear
	
	
	5,900
	5,900

	Coal
	
	865
	3,045
	3,910

	Wind
	4,292
	27,971
	5,149
	37,412

	Solar
	740
	734
	90
	1,564

	Biomass
	
	50
	100
	150

	Other
	
	1,016
	1,240
	2,256

	Grand Total 
	5,348
	37,385
	20,821
	63,554


[image: image3.emf]0

50

100

150

200

250

300

0

20,000

40,000

60,000

80,000

100,000

120,000

Jan

-

06

Feb

-

06

Mar

-

06

Apr

-

06

May

-

06

Jun

-

06

Jul

-

06

Aug

-

06

Sep

-

06

Oct

-

06

Nov

-

06

Dec

-

06

Jan

-

07

Feb

-

07

Mar

-

07

Apr

-

07

May

-

07

Jun

-

07

Jul

-

07

Aug

-

07

Sep

-

07

Oct

-

07

Nov

-

07

Dec

-

07

Jan

-

08

Feb

-

08

Mar

-

08

Apr

-

08

May

-

08

Jun

-

08

Jul

-

08

Aug

-

08

Sep

-

08

Oct

-

08

Nov

-

08

Dec

-

08

Jan

-

09

Feb

-

09

Mar

-

09

Apr

-

09

May

-

09

Jun

-

09

Jul

-

09

Aug

-

09

Sep

-

09

Oct

-

09

Nov

-

09

Dec

-

09

Jan

-

10

Feb

-

10

Mar

-

10

Apr

-

10

May

-

10

Jun

-

10

Jul

-

10

Aug

-

10

Sep

-

10

Oct

-

10

Nov

-

10

Dec

-

10

Jan

-

11

Feb

-

11

Mar

-

11

Apr

-

11

May

-

11

Jun

-

11

Project Count

MW Capacity

MW Natural Gas MW Nuclear MW Coal MW Wind MW Solar *

MW Biomass * MW Other Total # Projects # Projects Cancelled

* 

Prior to September 2008, Category "Other" included "Solar" and "Biomass"

Projects in all phases of interconnection study are reflected in this graph

Project cancellation tracking by month began in March 2008


1.3 Publicly Disclosed Generation Interconnection Projects
The table below summarizes the publicly disclosed generation projects for the ERCOT region.  
(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)
	Generation Interconnections as of June 30, 2011

	INR
	SiteName
	Status
	County
	Region
	COD
	Fuel Type
	MW For Grid
	Change from Last Report

	08INR0065
	Buffalo Gap 4 and 5
	PL
	Nolan
	West
	TBD
	Wind
	465
	

	09INR0029
	CFB Power Plant Units 11&12
	IA
	Calhoun
	South
	Jul-11
	Coal
	260
	

	10INR0010
	Jack County 2
	IA
	Jack
	North
	Sep-11
	Gas
	565
	

	06INR0012b
	Sherbino Mesa Wind Farm 2
	IA
	Pecos
	West
	Oct-11
	Wind
	150
	

	12INR0003
	Throckmorton Wind Farm
	PL
	Throckmorton
	West
	Dec-11
	Wind
	400
	

	09INR0034
	Gatesville Wind Farm
	PL
	Coryell
	North
	Dec-11
	Wind
	200
	

	08INR0038
	M Bar Wind
	PL
	Andrews
	West
	Dec-11
	Wind
	194
	

	10INR0082
	FRV AE Solar
	IA
	Travis
	North
	Dec-11
	Solar
	30
	

	08INR0025
	Pistol Hill Energy Center
	PL
	Ector
	West
	Dec-11
	Wind
	300
	

	09INR0001
	Sandy Creek 1
	IA
	McLennan
	North
	Feb-12
	Coal
	925
	

	11INR0084
	2W Whatley Phase 1
	PL
	Ector
	West
	Mar-12
	Wind
	45
	

	08INR0062
	Trinity Hills
	IA
	Young
	West
	Mar-12
	Wind
	250
	

	09INR0037
	Scurry County Wind III
	PL
	Scurry
	West
	Jun-12
	Wind
	350
	

	09INR0024
	B&B Panhandle Wind
	PL
	Carson
	West
	Jun-12
	Wind
	1001
	

	09INR0007
	Nacogdoches Project
	IA
	Nacogdoches
	North
	Jun-12
	Biomass
	100
	

	11INR0086
	RRE Austin Solar
	IA
	Travis
	South
	Jun-12
	Solar
	60
	

	10INR0060
	Magic Valley Wind Project
	IA
	Willacy
	South
	Jun-12
	Wind
	202
	

	12INR0004
	Fort Concho Wind Farm
	PL
	Tom Green
	West
	Jul-12
	Wind
	400
	

	12INR0043
	2W Whatley Phase 2
	PL
	Ector
	West
	Aug-12
	Wind
	290
	

	08INR0011
	Senate Wind Project
	IA
	Jack
	North
	Sep-12
	Wind
	150
	

	09INR0061
	WKN Mozart
	IA
	Kent
	West
	Dec-12
	Wind
	30
	

	08INR0018
	Gunsight Mountain
	IA
	Howard
	West
	Dec-12
	Wind
	120
	

	11INR0033
	Los Vientos
	IA
	Cameron
	South
	Dec-12
	Wind
	400
	

	06INR0022c
	Penascal Wind Farm 3
	IA
	Kenedy
	South
	Dec-13
	Wind
	202
	

	10INR0020a
	Panda Temple Power
	IA
	Bell
	North
	May-14
	Gas
	780
	

	06INR0006
	Cobisa-Greenville
	IA
	Hunt
	North
	May-14
	Gas
	1792
	

	14INR0005
	White Stallion Energy Center
	PL
	Matagorda
	South
	Jul-14
	Coal
	1200
	

	10INR0020b
	Panda Temple Power
	IA
	Bell
	North
	May-15
	Gas
	780
	

	10INR0022
	Pondera King Power Project
	IA
	Harris
	South
	Jun-15
	Gas
	1380
	

	12INR0016a
	Las Brisas Energy Center
	IA
	Nueces
	South
	Oct-15
	Other
	620
	

	15INR0008
	STP 3 and 4
	PL
	Matagorda
	South
	Jun-16
	Nuclear
	2700
	

	12INR0016b
	Las Brisas Energy Center
	IA
	Nueces
	South
	Oct-16
	Other
	620
	

	14INR0002
	Coleto Creek Unit 2
	IA
	Goliad
	South
	Jan-17
	Coal
	660
	

	15INR0002
	Comanche Peak 3 and 4
	PL
	Somervel
	North
	Dec-21
	Nuclear
	3200
	Date

	
	
	
	
	
	
	Total
	20,821
	


County Location of Installed Generation and Interconnection Requests (all fuels)
[image: image4.png]Projects wi SGIA

\7

2,267 4533 6,800

MWW under Full Studies

D)

®|
le

oO0O)

2267 4533 6800

o

Existing MW Generation

2266 4532 6800





1.4 Generation Projects Undergoing Full Interconnection Studies (not otherwise public)
	INR
	County
	Capacity
	COD
	Fuel
	
	INR
	County
	Capacity
	COD
	Fuel

	09INR0054
	Stonewall
	149
	TBD
	Wind
	
	10INR0048
	Hardeman
	1,000
	TBD
	Wind

	10INR0079
	Nolan
	60
	TBD
	Wind
	
	10INR0054
	Palo Pinto
	36
	TBD
	Wind

	10INR0016
	Childress
	150
	TBD
	Wind
	
	10INR0029
	Hood
	810
	TBD
	Gas

	10INR0052a
	Knox
	21
	TBD
	Wind
	
	10INR0013
	Upton
	400
	TBD
	Wind

	10INR0041
	Floyd
	135
	TBD
	Wind
	
	09INR0074
	Motley
	70
	TBD
	Wind

	11INR0029
	Throckmorton
	200
	TBD
	Wind
	
	10INR0051
	Brazoria
	200
	TBD
	Wind

	10INR0042
	Mason
	170
	TBD
	Wind
	
	10INR0033
	Armstrong
	399
	TBD
	Wind

	10INR0032
	Navarro
	775
	TBD
	Gas
	
	10INR0019
	Deaf Smith
	609
	TBD
	Wind

	10INR0008
	Pecos
	500
	TBD
	Wind
	
	07INR0013
	Coke
	200
	TBD
	Wind

	11INR0076
	Archer
	94
	TBD
	Wind
	
	11INR0093
	San Patricio
	34
	TBD
	Wind

	11INR0085
	Nolan
	106
	TBD
	Wind
	
	11INR0075
	Fort Bend
	15
	TBD
	Coal

	11INR0062
	Nueces
	149
	TBD
	Wind
	
	11INR0061
	Presidio
	90
	TBD
	Solar

	11INR0060
	Tom Green
	90
	TBD
	Solar
	
	11INR0058
	Pecos
	135
	TBD
	Solar

	11INR0037
	Smith
	50
	TBD
	Biomass
	
	11INR0091
	Webb
	92
	TBD
	Wind

	11INR0065
	Nueces
	240
	TBD
	Wind
	
	11INR0057
	Cameron
	165
	TBD
	Wind

	11INR0054
	San Patricio
	161
	TBD
	Wind
	
	11INR0019
	Upton
	200
	TBD
	Wind

	10INR0089
	Harris
	40
	TBD
	Other
	
	10INR0023
	Haskell
	386
	TBD
	Wind

	09INR0050
	Fannin
	1,200
	TBD
	Gas
	
	08INR0020
	Eastland
	200
	TBD
	Wind

	11INR0006
	Lamar
	579
	TBD
	Gas
	
	11INR0040
	freestone
	640
	Aug-11
	Gas

	11INR0079a
	Clay
	200
	Sep-11
	Wind
	
	11INR0047
	Deaf Smith
	600
	Sep-11
	Wind

	10INR0081b
	Clay
	19
	Oct-11
	Wind
	
	10INR0062a
	Pecos
	80
	Oct-11
	Wind

	11INR0094
	Kent
	100
	Nov-11
	Solar
	
	11INR0090
	Howard
	60
	Nov-11
	Solar

	10INR0021
	Grayson
	646
	Nov-11
	Gas
	
	11INR0071
	Harris
	7
	Dec-11
	Gas

	11INR0070
	Reeves
	50
	Dec-11
	Solar
	
	11INR0043
	Coke
	300
	Dec-11
	Wind

	11INR0025
	Crockett
	400
	Dec-11
	Wind
	
	12INR0033
	Motley
	150
	Jan-12
	Wind

	10INR0085
	Ector
	40
	Jan-12
	Solar
	
	10INR0080
	Presidio
	81
	Jan-12
	Solar

	12INR0054
	Jones
	200
	Feb-12
	Wind
	
	10INR0018
	Madison
	550
	Mar-12
	Gas

	12INR0045
	Kleberg
	135
	Mar-12
	Wind
	
	12INR0075
	Wilbarger
	499
	Apr-12
	Wind

	11INR0049
	Wharton
	275
	May-12
	gas
	
	10INR0081a
	Clay
	30
	May-12
	Wind

	09INR0031
	Ector
	275
	May-12
	Gas
	
	12INR0053
	Crockett
	615
	Jun-12
	Wind

	08INR0031
	Childress
	100
	Jun-12
	Wind
	
	12INR0050
	King
	332
	Jun-12
	Wind

	12INR0079
	Kenedy
	94
	Aug-12
	Wind
	
	12INR0076
	Winkler
	36
	Sep-12
	Other

	12INR0026
	Randall
	400
	Oct-12
	Wind
	
	12INR0035
	Nueces
	249
	Nov-12
	Wind

	08INR0044
	Concho
	200
	Nov-12
	Wind
	
	13INR0036
	Hidalgo
	200
	Dec-12
	Wind

	12INR0072
	Kinney
	100
	Dec-12
	Wind
	
	12INR0068
	Jim Hogg
	80
	Dec-12
	Wind

	12INR0067
	Webb
	94
	Dec-12
	Wind
	
	12INR0060
	Schleicher
	58
	Dec-12
	Wind

	12INR0057
	Ector
	50
	Dec-12
	Solar
	
	12INR0055
	Baylor
	80
	Dec-12
	Wind

	12INR0005
	Floyd
	1,100
	Dec-12
	Wind
	
	11INR0081
	Live Oak
	72
	Dec-12
	Wind

	10INR0077
	Callahan
	101
	Dec-12
	Wind
	
	09INR0025
	Concho
	180
	Dec-12
	Wind

	08INR0042
	Coke
	200
	Dec-12
	Wind
	
	12INR0029
	Swisher
	500
	Dec-12
	Wind

	09INR0048
	Jack
	113
	Dec-12
	Wind
	
	08INR0049
	Clay
	50
	Dec-12
	Wind

	12INR0027
	Gray
	200
	Jan-13
	Wind
	
	10INR0024
	Briscoe
	2,940
	Jan-13
	Wind

	13INR0010a
	Parmer
	200
	Jan-13
	Wind
	
	12INR0034
	Borden
	342
	Mar-13
	Wind

	11INR0083B
	Crockett
	100
	Mar-13
	Wind
	
	11INR0082B
	Val Verde
	150
	Mar-13
	Wind

	11INR0050
	Crosby
	149
	Mar-13
	Wind
	
	10INR0056
	Borden
	249
	Mar-13
	Wind

	09INR0058
	Howard
	250
	Mar-13
	Wind
	
	12INR0018
	Gray
	500
	Apr-13
	Wind

	13INR0020a
	Glasscock
	200
	May-13
	Wind
	
	10INR0062b
	Pecos
	220
	May-13
	Wind

	09INR0051
	Borden
	249
	Jun-13
	Wind
	
	09INR0041
	Mitchell
	300
	Jun-13
	Wind

	13INR0023
	Ector
	240
	Jul-13
	Other
	
	13INR0016
	Deaf Smith
	251
	Aug-13
	Wind

	13INR0025
	Randall
	150
	Sep-13
	Wind
	
	11INR0083A
	Crockett
	50
	Sep-13
	Wind

	11INR0082A
	Val Verde
	50
	Sep-13
	Wind
	
	13INR0005
	Carson
	600
	Oct-13
	Wind

	13INR0004
	Deaf Smith
	500
	Oct-13
	Wind
	
	13INR0028
	Hale
	392
	Nov-13
	Gas

	13INR0026
	Oldham
	201
	Dec-13
	Wind
	
	13INR0017
	Childress
	200
	Dec-13
	Wind

	13INR0007
	Pecos
	200
	Dec-13
	Wind
	
	12INR0002a
	Briscoe
	200
	Dec-13
	Wind

	11INR0013
	Mills
	150
	Dec-13
	Wind
	
	10INR0009
	Castro
	300
	Dec-13
	Wind

	09INR0077
	Reagan
	500
	Dec-13
	Wind
	
	09INR0073
	Scurry
	200
	Dec-13
	Wind

	13INR0006
	Gray
	750
	Jan-14
	Wind
	
	08INR0019c
	Gray
	250
	Jan-14
	Wind

	08INR0019b
	Gray
	250
	Jan-14
	Wind
	
	08INR0019a
	Gray
	250
	Jan-14
	Wind

	13INR0010b
	Parmer
	500
	Jan-14
	Wind
	
	13INR0020b
	Glasscock
	150
	May-14
	Wind

	10INR0015
	Mitchell
	350
	May-14
	Wind
	
	14INR0003
	Nolan
	850
	Jun-14
	Coal

	12INR0042
	Deaf Smith
	400
	Sep-14
	Wind
	
	14INR0006
	Floyd
	151
	Oct-14
	Wind

	14INR0001
	Pecos
	500
	Dec-14
	Wind
	
	13INR0021
	Llano
	600
	Dec-14
	Gas

	12INR0002b
	Briscoe
	200
	Dec-14
	Wind
	
	13INR0010c
	Parmer
	500
	Jan-15
	Wind

	15INR0011b
	Borden
	38
	Dec-15
	Solar
	
	15INR0011a
	Borden
	112
	Dec-15
	Wind

	12INR0002c
	Briscoe
	350
	Dec-15
	Wind
	
	16INR0002
	Brazoria
	700
	Jun-17
	Other


1.5 Wind Generation    
Wind Capacity Installed by Year  
[image: image5.wmf]150 

550 

1,654 

1,654 

116 

816 

977 

1,173 

1,385 

1,854 

2,875 

4,785 

8,005 

8,916 

9,400 

9,550 

9,950 

11,054 

11,054 

0

2,000

4,000

6,000

8,000

10,000

12,000

2000

2001

2002

2003

2004

2005

2006

2007

2008

2009

2010

2011

2012

2013

2014

MW

Cumulative MW Installed

Cumulative Planned (Signed Interconnection Agreement)

ERCOT Wind Installations 

by Year  

(as of June 30, 2011)

The data presented here is based upon 

the latest registration data provided to 

ERCOT by the resource owners and can 

change without notice.  Any capacity 

changes will be reflected in current and 

subsequent years' totals.   Scheduling 

delays will also be reflected in the planned 

projects as that information is 

received.


County Location of Installed Capacity and Interconnection Requests (Wind only)
[image: image6.png]Projects wf SGA

\1

2267 4533 6,800

y,

|
W under Full Studies
L
HeREIR
«[ol00 e
of
267 4533 6300 | O ol
rd
° Olo
O —for
o}
Existing MW Generation \\ 3
. ’ N
o
266 4532 6800





2. Regional Planning Group Project Reviews
· CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

· American Electric Power Service Corporation has submitted the Laredo to the lower Rio Grande Valley 345 kV Project to improve reliability of the lower Rio Grande Valley transmission system. This project proposes a new 345kV transmission line to be constructed from Laredo to the lower Rio Grande Valley to provide a third 345kV source to the area with an in-service date in the 2016/2017 timeframe. The estimated cost for this project is $379.5 Million. This Tier 1 project is currently undergoing ERCOT Independent Review.

· Sharyland Utilities (Sharyland) and Brownsville Public Utilities Board (BPUB) has submitted the Cross Valley Brownsville Loop project that proposes a new 345kV line from LaPalma to Loma Alta and a new 345kV line from Loma Alta to Frontera. The estimated cost for this project is $117.9 Million.  This Tier 1 project is currently in the RPG study mode. Sharyland and BPUB submitted an study addendum report to the Cross valley project with additional options which is currently in the RPG study mode. 
3. Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

[image: image7.wmf]-

3

-

2

-

1

0

1

2

3

4

5

6

7

8

May

-

10

Jun

-

10

Jul

-

10

Aug

-

10

Sep

-

10

Oct

-

10

Nov

-

10

Dec

-

10

Jan

-

11

Feb

-

11

Mar

-

11

Apr

-

11

May

-

11

OOMC

RUC


      Monthly Average MCPE and LMP

      [image: image8.wmf]0

10

20

30

40

50

60

70

Jun

-

10

Jul

-

10

Aug

-

10

Sep

-

10

Oct

-

10

Nov

-

10

Dec

-

10

Jan

-

11

Feb

-

11

Mar

-

11

Apr

-

11

May

-

11

Jun

-

11

$

/

M

W

h

LMP

MCPE


Binding Constraints - June 2011
	Contingency

	Binding Element

	Number of 5-min intervals
	Shadow Price Range $/MWh
	Estimated Congestion Cost $ (Shadow Price*Limit)
	Transmission Project
	Clearance


	BASE CASE
	West to North Stability Limit
	3703
	0 - 3910
	20,058,229
	CREZ
	

	BASE CASE,  

Zorn - Marion and Clear Springs 345kV,  Clear Springs 345/138kV AT
	Marion 345/138kV Autotransformer
	391
	0 - 4500
	13,826,062
	
	Outage on Zorn - Hutto 345kV and Clear Springs - Gilleland Creek 345kV

	Gails To Keysb 138kV, Willow Valley - Sharon Ridge Exxon 138kV
	Ackerly Lyntegar - Sparenburg 69kV
	2910
	0 - 2800
	8,674,241
	Lamesa - Ackerly Vealmoor 69 kV line rebuild 

[11TPIT0060]
	

	Abilene South - Bluff Creek 138kV, 

Bluff Creek Auto T2_H & T2_L & T2_T 
	Nicole - Oak Creek 138kV
	3565
	0 - 3500
	5,895,745
	CREZ
	Outage on Bluff Creek - Abilene Mulberry Creek 345kV and Bluff Creek - San Angelo Red Creek 345kV

	Holt Switch 138/69kV AT1, 
Amoco North Cowden Tap - North Cowden Amoco 138kV
	Odessa North - Odessa Basin Switch 69KV
	811
	0 - 2800
	4,935,892
	Odessa North - North Cowden 69 kV line upgrade [14TPIT0009]
	

	Meadow - PH Robinson 345kV, 
PH Robinson 345/138kV AT1
	North Alvin Station - Hastings Sub 138kV
	538
	0 - 3500
	4,925,632
	Upgrade North Alvin-Hastings [14TPIT0018]
	

	Liggett Switch 345/138kV Autotransformer
	Cedar Hill Switch - Mayfield North Tap 138kV
	95
	0 - 3500
	4,403,431
	Cedar Hill Switch 138 kV terminal equipment upgrade [11TPIT0122]
	

	Austrop- Daffin and Austrop - Decker 138kV
	Decker - Sprinkle 138kV
	193
	0 - 3500
	4,174,760
	
	Outage on Kingsbery - Wheless Lane 138kV 

	Hackberry - Valley Ranch and Hackberry - Carrollton NW 345kV
	DFW D1 - DFW C East 138kV
	151
	0 - 3500
	3,452,614
	
	

	Greens Bayou - Gable and Hardy - Crocket 138kV
	Garrott - Midtown 138kV
	1270
	0 - 3500
	2,876,092
	Garrott to Midtown to Polk 138 kV upgrade [11TPIT0072]
	


Binding Constraints - January to June 2011
	Contingency

	Binding Element

	Number of 5-min intervals
	Shadow Price Range $/MWh
	Estimated Congestion Cost $ (Shadow Price*Limit)
	Transmission Project

	BASE CASE
	West to North Stability Limit
	16322
	0 - 3910
	74,186,928
	CREZ

	BASE CASE
	Valley Import
	273
	0 - 5000
	41,457,339
	

	Nelson Sharpe - Ajo 345kV
	Lon Hill - North Edinburg 345kV
	78
	0 - 4500
	31,689,757
	

	Denton - Argyle & West Denton 138kV, 

Fort Worth - W_Dent 138kV
	West Denton - Jim Cristal 138kV
	383
	40 - 3500
	22,404,765
	5YTP [2010-R12]

	BASE CASE,  

Zorn - Marion and Clear Springs 345kV,  

Clear Springs 345/138kV Autotransformer
	Marion 345/138kV Autotransformer
	391
	0 - 4500
	13,826,062
	

	Abilene South - Bluff Creek 138kV, 

Bluff Creek Auto T2_H & T2_L & T2_T 
	Nicole - Oak Creek 138kV
	8558
	0 - 3500
	10,646,043
	CREZ

	Greens Bayou - Gable and Hardy - Crocket 138kV, 

Singleton - Tomball and Singleton - Roanes Prairie 345kV, 

Meadow - Oasis 345kV, 

Thermal Energy Coop - Blodgett 138kV
	Garrott - Midtown 138kV
	3006
	0 - 3500
	9,576,167
	Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072]

	West Levee Switch 345/138kV AT1
	West Levee Switch 345/138kV AT2
	98
	0 - 3500
	9,073,730
	5YTP [2009-R21]

	Long Creek - Sweetwater - Abilene Mulberry 345kV, Graham SES - Long Creek Switching Station 345kV
	Paint Creek - Murray TU 138KV
	1508
	0 - 3500
	8,839,628
	CREZ

	Gails To Keysb 138kV, 

Willow Valley Switching Station - Sharon Ridge Exxon 138kV
	Ackerly Lyntegar - Sparenburg 69kV
	2910
	0 - 2800
	8,674,241
	Lamesa - Ackerly Vealmoor 69 kV line rebuild 

[11TPIT0060]


4. Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.
       [image: image9.png]MWs Percent
9500 30%
9400 5%
9300

20%
9200 1

15%
9100

10%
9000

o

8900 %
8800 0%

6/1/10  7/1/10 7/31/10 8/30/10 9/29/10 10/29/1011/28/1012/28/10 1/27/11 2/26/11 3/28/11 4/27/11 527111 6/26/11

——— TotalInstalled Wind Capacity ——— Wind Generation Percent of ERCOT Load





[image: image10.wmf]0%

5%

10%

15%

20%

25%

8400

8600

8800

9000

9200

9400

05/01/11

05/06/11

05/11/11

05/16/11

05/21/11

05/26/11

05/31/11

06/05/11

06/10/11

06/15/11

06/20/11

06/25/11

06/30/11

Percent

MWs

Total Installed Wind Capacity

Wind Generation Percent of ERCOT Load


[image: image11.wmf]0%

5%

10%

15%

20%

25%

30%

Jun

-

10

Jul

-

10

Aug

-

10

Sep

-

10

Oct

-

10

Nov

-

10

Dec

-

10

Jan

-

11

Feb

-

11

Mar

-

11

Apr

-

11

May

-

11

Jun

-

11

W

i

n

d

 

O

u

t

p

u

t

 

/

 

T

o

t

a

l

 

E

R

C

O

T

 

L

o

a

d

Monthly Aggregate Wind Output as a Percentage of Total ERCOT Load

Minimum

Maximum

Average


5. Planning Model Activities

· Work continues on Data Set A.  The remaining schedule is as follows:
· May 13, 2011
DSA Pass 0 Projects and Profiles from all (on-time)
· June 3, 2011
DSA Pass 1 Projects and Profiles due from all (projected on-time)
· June 17, 2011
DSA Pass 2 Projects and Profiles due from all
· June 27, 2011
DSA Pass 3 Comparison Spreadsheet Template built
· June 28 – 30 
DSA Meeting in Taylor, complete Passes 3, 4, 5
· July 8, 2011
DSA Pass 6 Projects and Profiles due from all
· July 15, 2011
DSA cases finalized and posted
· July 18, 2011
DSA Final Comparison Spreadsheet Template built
· July 29, 2011
DSA Final Comparison comments due for posting
· August 1, 2011
DSB Start
· ERCOT has submitted all nine parts of SCR760 as enhancements to Siemens Topology Processor following ERCOT Board approval in March 2011.  The first three parts submitted were items 3, 7 and 8.  The requirements for these items have been vetted by ERCOT, TSPs, and Siemens.  Siemens will be updating their cost estimates for these three items and then ERCOT will prepare a Statement of Work (SOW).  ERCOT has begun work on the requirements for items 2, 4, 5, and 9, creating an initial draft and sending to Siemens for comments.
	SCR Sub Part
	SCR Description
	Status

	SCR760-1  
	Upgrade to PSS/E v32
	Submitted

	SCR760-2  
	Distribution Capacitor banks
	Submitted

	SCR760-3  
	Zero Impedance Line Ratings
	Planning

	SCR760-4  
	Associate Loads and Capacitor banks with the correct CNG
	Submitted

	SCR760-5  
	Additional Transformer Data for Planning
	Submitted

	SCR760-6  
	FACTS Devices
	Submitted

	SCR760-7  
	Assign valid PSSE IDs to Breakers/

Switches/ Series Devices
	Planning

	SCR760-8  
	Phase shift of Autos for short circuit studies
	Planning

	SCR760-9  
	Multisection Line Grouping
	Submitted


Table 1:  In the following table:

1.  Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.  
2. Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).  
3. Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.
6. Other Notable Activities
· An update to the West-to-North stability limits is in progress for the current year 2011.

· Work on the 2010 Five-Year Transmission Plan is underway.  The work is currently focused on preparing the 5YTP start cases (condition the SSWG base cases).
© 2011 Electric Reliability Council of Texas, Inc. All rights reserved.
i

