|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report June 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 205 active generation interconnection requests totaling over 63,000 MW. This includes over 37,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $622.4 Million - Transmission Projects endorsed in 2011 total $23.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $10.0 Billion - Transmission Projects energized in 2011 total about $401.8 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Signed Generation Interconnection Agreements – none this period

## New Generation Registering for Commercial Operations

The total installed wind capacity is now reported as 9,452 MW by the resource owners through the registration process. Capacity by North, South and West is 292 MW, 1216 MW, and 7943 MW respectively. 850 MW is able to switch between the West and South zones.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 205 active generation interconnection or change requests |  |  |  |  |
| As of June 30, 2011 | North | South | West | Total |
| Security Screening Study | 1 | 2 | 5 | 8 |
| SSS Completed | 3 | 7 | 23 | 33 |
| Full Interconnect Study | 20 | 19 | 94 | 133 |
| FIS Completed | 1 | 3 | 6 | 10 |
| Interconnect Agreement Completed | 8 | 9 | 4 | 21 |
| Capacity under Interconnection Agreements | 5,122 | 4,404 | 550 | 10,076 |
| Capacity for Grid, MW | 17,431 | 12,043 | 34,080 | 63,554 |
| Wind Capacity, MW | 3,369 | 3,319 | 30,724 | 37,412 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CombinedCycle |  |  | 5,297 | 11,647 |
| Gas-All Other |  |  |  | 715 |
| Total Gas | 316 | 6,749 | 5,297 | 12,362 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 865 | 3,045 | 3,910 |
| Wind | 4,292 | 27,971 | 5,149 | 37,412 |
| Solar | 740 | 734 | 90 | 1,564 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 1,016 | 1,240 | 2,256 |
| Grand Total | 5,348 | 37,385 | 20,821 | 63,554 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of June 30, 2011 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | TBD |  | Wind |  | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Jul-11 |  | Coal |  | 260 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Sep-11 |  | Gas |  | 565 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-11 |  | Wind |  | 150 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-11 |  | Wind |  | 400 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind |  | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind |  | 194 |  |
| 10INR0082 | FRV AE Solar | IA | Travis | North | Dec-11 |  | Solar |  | 30 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind |  | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal |  | 925 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind |  | 45 |  |
| 08INR0062 | Trinity Hills | IA | Young | West | Mar-12 |  | Wind |  | 250 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind |  | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind |  | 1001 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 |  | Biomass |  | 100 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Jun-12 |  | Solar |  | 60 |  |
| 10INR0060 | Magic Valley Wind Project | IA | Willacy | South | Jun-12 |  | Wind |  | 202 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind |  | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind |  | 290 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Sep-12 |  | Wind |  | 150 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind |  | 120 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-14 |  | Gas |  | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas |  | 1792 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal |  | 1200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas |  | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-15 |  | Gas |  | 1380 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other |  | 620 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear |  | 2700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other |  | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-21 |  | Nuclear |  | 3200 | Date |
|  |  |  |  |  |  |  | Total |  | 20,821 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 10INR0029 | Hood | 810 | TBD | Gas |
| 10INR0052a | Knox | 21 | TBD | Wind |  | 10INR0013 | Upton | 400 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 09INR0074 | Motley | 70 | TBD | Wind |
| 11INR0029 | Throckmorton | 200 | TBD | Wind |  | 10INR0051 | Brazoria | 200 | TBD | Wind |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0019 | Deaf Smith | 609 | TBD | Wind |
| 10INR0008 | Pecos | 500 | TBD | Wind |  | 07INR0013 | Coke | 200 | TBD | Wind |
| 11INR0076 | Archer | 94 | TBD | Wind |  | 11INR0093 | San Patricio | 34 | TBD | Wind |
| 11INR0085 | Nolan | 106 | TBD | Wind |  | 11INR0075 | Fort Bend | 15 | TBD | Coal |
| 11INR0062 | Nueces | 149 | TBD | Wind |  | 11INR0061 | Presidio | 90 | TBD | Solar |
| 11INR0060 | Tom Green | 90 | TBD | Solar |  | 11INR0058 | Pecos | 135 | TBD | Solar |
| 11INR0037 | Smith | 50 | TBD | Biomass |  | 11INR0091 | Webb | 92 | TBD | Wind |
| 11INR0065 | Nueces | 240 | TBD | Wind |  | 11INR0057 | Cameron | 165 | TBD | Wind |
| 11INR0054 | San Patricio | 161 | TBD | Wind |  | 11INR0019 | Upton | 200 | TBD | Wind |
| 10INR0089 | Harris | 40 | TBD | Other |  | 10INR0023 | Haskell | 386 | TBD | Wind |
| 09INR0050 | Fannin | 1,200 | TBD | Gas |  | 08INR0020 | Eastland | 200 | TBD | Wind |
| 11INR0006 | Lamar | 579 | TBD | Gas |  | 11INR0040 | freestone | 640 | Aug-11 | Gas |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 11INR0094 | Kent | 100 | Nov-11 | Solar |  | 11INR0090 | Howard | 60 | Nov-11 | Solar |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 11INR0071 | Harris | 7 | Dec-11 | Gas |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0085 | Ector | 40 | Jan-12 | Solar |  | 10INR0080 | Presidio | 81 | Jan-12 | Solar |
| 12INR0054 | Jones | 200 | Feb-12 | Wind |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0045 | Kleberg | 135 | Mar-12 | Wind |  | 12INR0075 | Wilbarger | 499 | Apr-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0050 | King | 332 | Jun-12 | Wind |
| 12INR0079 | Kenedy | 94 | Aug-12 | Wind |  | 12INR0076 | Winkler | 36 | Sep-12 | Other |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 12INR0035 | Nueces | 249 | Nov-12 | Wind |
| 08INR0044 | Concho | 200 | Nov-12 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0072 | Kinney | 100 | Dec-12 | Wind |  | 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |
| 12INR0067 | Webb | 94 | Dec-12 | Wind |  | 12INR0060 | Schleicher | 58 | Dec-12 | Wind |
| 12INR0057 | Ector | 50 | Dec-12 | Solar |  | 12INR0055 | Baylor | 80 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-12 | Wind |
| 10INR0077 | Callahan | 101 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 09INR0048 | Jack | 113 | Dec-12 | Wind |  | 08INR0049 | Clay | 50 | Dec-12 | Wind |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |
| 13INR0010a | Parmer | 200 | Jan-13 | Wind |  | 12INR0034 | Borden | 342 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0050 | Crosby | 149 | Mar-13 | Wind |  | 10INR0056 | Borden | 249 | Mar-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 13INR0023 | Ector | 240 | Jul-13 | Other |  | 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 11INR0083A | Crockett | 50 | Sep-13 | Wind |
| 11INR0082A | Val Verde | 50 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 09INR0073 | Scurry | 200 | Dec-13 | Wind |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 13INR0020b | Glasscock | 150 | May-14 | Wind |
| 10INR0015 | Mitchell | 350 | May-14 | Wind |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 12INR0042 | Deaf Smith | 400 | Sep-14 | Wind |  | 14INR0006 | Floyd | 151 | Oct-14 | Wind |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 13INR0021 | Llano | 600 | Dec-14 | Gas |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 13INR0010c | Parmer | 500 | Jan-15 | Wind |
| 15INR0011b | Borden | 38 | Dec-15 | Solar |  | 15INR0011a | Borden | 112 | Dec-15 | Wind |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 16INR0002 | Brazoria | 700 | Jun-17 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

- American Electric Power Service Corporation has submitted the Laredo to the lower Rio Grande Valley 345 kV Project to improve reliability of the lower Rio Grande Valley transmission system. This project proposes a new 345kV transmission line to be constructed from Laredo to the lower Rio Grande Valley to provide a third 345kV source to the area with an in-service date in the 2016/2017 timeframe. The estimated cost for this project is $379.5 Million. This Tier 1 project is currently undergoing ERCOT Independent Review.

- Sharyland Utilities (Sharyland) and Brownsville Public Utilities Board (BPUB) has submitted the Cross Valley Brownsville Loop project that proposes a new 345kV line from LaPalma to Loma Alta and a new 345kV line from Loma Alta to Frontera. The estimated cost for this project is $117.9 Million.  This Tier 1 project is currently in the RPG study mode. Sharyland and BPUB submitted an study addendum report to the Cross valley project with additional options which is currently in the RPG study mode.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - June 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 3703 | 0 - 3910 | 20,058,229 | CREZ |  |
| BASE CASE, Zorn - Marion and Clear Springs 345kV, Clear Springs 345/138kV AT | Marion 345/138kV Autotransformer | 391 | 0 - 4500 | 13,826,062 |  | Outage on Zorn - Hutto 345kV and Clear Springs - Gilleland Creek 345kV |
| Gails To Keysb 138kV, Willow Valley - Sharon Ridge Exxon 138kV | Ackerly Lyntegar - Sparenburg 69kV | 2910 | 0 - 2800 | 8,674,241 | Lamesa - Ackerly Vealmoor 69 kV line rebuild [11TPIT0060] |  |
| Abilene South - Bluff Creek 138kV, Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 3565 | 0 - 3500 | 5,895,745 | CREZ | Outage on Bluff Creek - Abilene Mulberry Creek 345kV and Bluff Creek - San Angelo Red Creek 345kV |
| Holt Switch 138/69kV AT1, Amoco North Cowden Tap - North Cowden Amoco 138kV | Odessa North - Odessa Basin Switch 69KV | 811 | 0 - 2800 | 4,935,892 | Odessa North - North Cowden 69 kV line upgrade [14TPIT0009] |  |
| Meadow - PH Robinson 345kV, PH Robinson 345/138kV AT1 | North Alvin Station - Hastings Sub 138kV | 538 | 0 - 3500 | 4,925,632 | Upgrade North Alvin-Hastings [14TPIT0018] |  |
| Liggett Switch 345/138kV Autotransformer | Cedar Hill Switch - Mayfield North Tap 138kV | 95 | 0 - 3500 | 4,403,431 | Cedar Hill Switch 138 kV terminal equipment upgrade [11TPIT0122] |  |
| Austrop- Daffin and Austrop - Decker 138kV | Decker - Sprinkle 138kV | 193 | 0 - 3500 | 4,174,760 |  | Outage on Kingsbery - Wheless Lane 138kV |
| Hackberry - Valley Ranch and Hackberry - Carrollton NW 345kV | DFW D1 - DFW C East 138kV | 151 | 0 - 3500 | 3,452,614 |  |  |
| Greens Bayou - Gable and Hardy - Crocket 138kV | Garrott - Midtown 138kV | 1270 | 0 - 3500 | 2,876,092 | Garrott to Midtown to Polk 138 kV upgrade [11TPIT0072] |  |

Binding Constraints - January to June 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 16322 | 0 - 3910 | 74,186,928 | CREZ |
| BASE CASE | Valley Import | 273 | 0 - 5000 | 41,457,339 |  |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0 - 4500 | 31,689,757 |  |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 383 | 40 - 3500 | 22,404,765 | 5YTP [2010-R12] |
| BASE CASE, Zorn - Marion and Clear Springs 345kV, Clear Springs 345/138kV Autotransformer | Marion 345/138kV Autotransformer | 391 | 0 - 4500 | 13,826,062 |  |
| Abilene South - Bluff Creek 138kV, Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 8558 | 0 - 3500 | 10,646,043 | CREZ |
| Greens Bayou - Gable and Hardy - Crocket 138kV, Singleton - Tomball and Singleton - Roanes Prairie 345kV, Meadow - Oasis 345kV, Thermal Energy Coop - Blodgett 138kV | Garrott - Midtown 138kV | 3006 | 0 - 3500 | 9,576,167 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] |
| West Levee Switch 345/138kV AT1 | West Levee Switch 345/138kV AT2 | 98 | 0 - 3500 | 9,073,730 | 5YTP [2009-R21] |
| Long Creek - Sweetwater - Abilene Mulberry 345kV, Graham SES - Long Creek Switching Station 345kV | Paint Creek - Murray TU 138KV | 1508 | 0 - 3500 | 8,839,628 | CREZ |
| Gails To Keysb 138kV, Willow Valley Switching Station - Sharon Ridge Exxon 138kV | Ackerly Lyntegar - Sparenburg 69kV | 2910 | 0 - 2800 | 8,674,241 | Lamesa - Ackerly Vealmoor 69 kV line rebuild [11TPIT0060] |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Work continues on Data Set A.  The remaining schedule is as follows:

  - May 13, 2011	DSA Pass 0 Projects and Profiles from all (on-time)

  - June 3, 2011	DSA Pass 1 Projects and Profiles due from all (on-time)

  - June 17, 2011	DSA Pass 2 Projects and Profiles due from all (on-time)

  - June 27, 2011	DSA Pass 3 Comparison Spreadsheet Template built (on-time)

  - June 28 – 30 	DSA Meeting in Taylor, complete Passes 3, 4, 5 (on-time)

  - July 8, 2011	DSA Pass 6 Projects and Profiles due from all (projected on-time)

  - July 15, 2011	DSA cases finalized and posted

  - July 18, 2011	DSA Final Comparison Spreadsheet Template built

  - July 29, 2011	DSA Final Comparison comments due for posting

  - August 1, 2011	DSB Start

- ERCOT has submitted all nine parts of SCR760 as enhancements to Siemens Topology Processor following ERCOT Board approval in March 2011.  The first three parts submitted were items 3, 7 and 8 and a Statement of Work (SOW) has been completed.  Siemens has completed the initial coding for items 3 and 8 on their internal systems and sent ERCOT a Topology Processor output file to check and approve.  ERCOT is working with Siemens and the TSPs to complete the requirements for items 2, 4, 5, and 9.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Submitted |
| SCR760-2 | Distribution Capacitor banks | Planning |
| SCR760-3 | Zero Impedance Line Ratings | Planning |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Planning |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Planning |
| SCR760-8 | Phase shift of Autos for short circuit studies | Planning |
| SCR760-9 | Multisection Line Grouping | Planning |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- An update to the West-to-North stability limits is in progress for the current year 2011.

- Work on the 2010 Five-Year Transmission Plan is underway.  The work is currently focused on preparing the 5YTP start cases (condition the SSWG base cases).