## ACQ01
|  | Script ID | ACQ01 |  | Power Point
|  | Script Name | Acquisition Cancel Request Rejected By ERCOT
|  | Script Storyline | Losing CR sends an 814_08 on an ESI ID that is involved in an Acquisition Transfer. ERCOT rejects the cancel.
|  | Success Criteria | ERCOT rejects a cancel request for an ESI ID involved in an Acquisition Transfer.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | None | No
|  | Operating Rule | CC2010-742 |  | TRACK | TX SET V4.0
Simulated Entity
|  | Duns Number | 111111112
|  | Number of CR's | 2
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | CR1 set up as ROR | CR1 set up as ROR
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
|  | Day 06 | ERCOT | TDSP | 814_03 | BGN07 = AQ RMRD = Day 15 (DTM~375) | Acquisition Transfer requested for Day 15 | 1 |  |  | CR1
|  | Day 07 | TDSP | ERCOT | 814_04 | BGN07 = AQ SMRD = Day 15 (DTM~150) | TDSP response accepting Acquisition Transfer | 1 |  |  | CR1
|  | Day 08 | ERCOT | CR1 | 814_11 | BGN07 = AQ SMRD = Day 15 (DTM~150) | ERCOT sends accept response to CR1 | 1 |  |  | CR1
|  |  | ERCOT | SIM CR2 | 814_14 | BGN07 = AQ SMRD = Day 15 (DTM~150) | ERCOT sends accept response to SIM CR2 | 1 |  |  | SIM CR2
|  | Day 09 | CR1 | ERCOT | 814_08 | BGN07 = AQ REF~1P~B40 | CR1 sends cancel request | 1 |  |  | CR1
|  | Day 10 | ERCOT | CR1 | 814_09 | BGN07 = AQ REF~7G~ACR | ERCOT rejects the cancel request | 1 |  |  | CR1

## ACQ02
| Script ID | ACQ02 |  | Power Point
| Script Name | Acquisition Transfer
| Script Storyline | SIM CR2 (Losing CR) initiates an Acquisition Transfer on 2 ESI IDs (1 Standard and 1 Self-Selected). TDSP schedules each accordingly. Notification sent to SIM CR2 (Losing CR) and CR1 (Gaining CR).
| Success Criteria | CR, TDSP, and ERCOT populate segments accordingly for an Acquisition Transfer.
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential | Single Non IDR | None | 111111112 | No
| Operating Rule | CC2010-746 |  | TRACK | TX SET V4.0
Simulated Entity
| Duns Number | 111111112
| Number of CR's | 2
|  | ERCOT | TDSP | CR1
| Pretest Setup | SIM CR2 set up as ROR | SIM CR2 set up as ROR
Checkpoint Date | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 11 | ERCOT | TDSP | 814_03 | BGN07 = AQ N1~8R~ACQUISITION TRANSFER CUSTOMER PER~IC~ACQUISITION TRANSFER CUSTOMER LIN~1~SH~EL~SH~CE~SH~HI REF~SU~N DTM~656 = Day 11 | Acquisition Transfer requested for Standard Switch timeline | 1 |  |  | SIM CR2
|  | ERCOT | TDSP | 814_03 | BGN07 = AQ N1~8R~ACQUISITION TRANSFER CUSTOMER PER~IC~ACQUISITION TRANSFER CUSTOMER LIN~1~SH~EL~SH~CE~SH~HI~SH~SW REF~SU~N DTM~656 = Day 15 DTM~MRR = Day 15 | Acquisition Transfer requested for Self-Selected Switch timeline | 1 |  |  | SIM CR2
| Day 12 | TDSP | ERCOT | 814_04 | BGN07 = AQ LIN~1~SH~EL~SH~CE~SH~HI N1~8R~ACQUISITION TRANSFER CUSTOMER DTM~150 = Day 14 | TDSP response accepting Acquisition Transfer | 1 |  |  | SIM CR2
|  | TDSP | ERCOT | 814_04 | BGN07 = AQ LIN~1~SH~EL~SH~CE~SH~HI~SH~SW N1~8R~ACQUISITION TRANSFER CUSTOMER DTM~150 = Day 15 | TDSP response accepting Acquisition Transfer | 1 |  |  | SIM CR2
| Day 13 | ERCOT | SIM CR2 | 814_11 | BGN07 = AQ | ERCOT notifies Losing CR of the accept response
|  | ERCOT | SIM CR2 | 814_11 | BGN07 = AQ | ERCOT notifies Losing CR of the accept response
|  | ERCOT | CR1 | 814_14 | BGN07 = AQ N1~8R~ACQUISITION TRANSFER CUSTOMER REF~ACD~01 | ERCOT notifies Gaining CR of the accept response
|  | ERCOT | CR1 | 814_14 | BGN07 = AQ N1~8R~ACQUISITION TRANSFER CUSTOMER REF~ACD~01 | ERCOT notifies Gaining CR of the accept response

## MOU04
|  | Script ID | MOU04 |  | Power Point
|  | Script Name | Remittance Adjustment
|  | Script Storyline | MOU/EC TDSP sends usage to CR1 for two customers. CR1 sends invoices for each customer. MOU/EC TDSP sends remittance advice for customer A to CR1. Customer A's payment is returned, and Customer B sends payments so MOU/EC TDSP sends remittance with an adjustment for Customer A and a payment for Customer B resulting in a positive 820. Note: Script will utilize 2 ESI ID's
|  | Success Criteria | CR1 submits invoice for customers. MOU/EC TDSP sends remittance detail to CR1 when a customer pays and if a customer payment is returned, MOU/EC TDSP sends adjusted remittance advice.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | CC2004-607; Requirement 2 |  | TRACK | ALL MOU/EC CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | MOU/EC TDSP | CR1
|  | PreTest Setup | Set CR1 as Rep of Record (ROR) | Set CR1 as Rep of Record (ROR) | Establish Customer as active in system
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | MOU/EC TDSP | ERCOT | 867_03 | BPT01 = 00 DTM~649=Day 5 REF~1W | MOU/EC TDSP sends usage to ERCOT for Cust A | 1
|  |  | MOU/EC TDSP | ERCOT | 867_03 | BPT01 = 00 DTM~649=Day 5 REF~1W | MOU/EC TDSP sends usage to ERCOT for Cust B | 1
|  | Day 02 | ERCOT | CR1 | 867_03 | BPT01 = 00 DTM~649=Day 5 REF~1W | ERCOT forwards monthly usage to Current CR for Cust A | 1
|  |  | ERCOT | CR1 | 867_03 | BPT01 = 00 DTM~649=Day 5 REF~1W | ERCOT forwards monthly usage to Current CR for Cust B | 1
Day 2
| Day 3 | Day 03
|  | Day 04 | CR1 | MOU/EC TDSP | 810_03 | BIG08 = 00 REF~11~cust accnt nr | CR sends original cycle bill for Cust A | 1
|  |  | CR1 | MOU/EC TDSP | 810_03 | BIG08 = 00 REF~11~cust accnt nr | CR sends original cycle bill for Cust B | 1
| Day 5 | Day 05
| Day 6 | Day 06
| Day 7 | Day 07
| Day 8 | Day 08
| Day 9 | Day 09
| Day10 | Day 10
| Day 11 | Day 11 |  |  |  |  | Customer A makes a Payment | 1 |  | PYM
| Day 12 | Day 12 | MOU/EC TDSP | CR1 | 820_03 | RMR~11~customer acct nr (one each for Cust A) RMR03=PO RMR04=total pymt amt | Remittance advice is sent by MOU/EC TDSP | 1
| Day 13 | Day 13
Day 14
| Day 15 | Day 15
| Day 16 | Day 16
| Day 17 | Day 17 |  |  |  |  | Customer A's Payment is returned by the bank | 1 |  | RTN
[7 empty] | Customer B makes Payment | 1 |  | PYM
| Day 18 | Day 18 | MOU/EC TDSP | CR1 | 820_03 | RMR~11~cust acct nr (cust A) RMR03=AJ RMR04=total adjusted amt RMR07=72 (adjustment code for returned check) RMR08=adjustment amount RMR~11 - Cust B payment Info | Adjusted Remittance advice is sent by MOU/EC TDSP | 1
| Day 19 | Day 19
| Day 20 | Day 20
| Day 21 | Day 21
| Day 22 | Day 22
| Day 23 | Day 23
| Day 24 | Day 24
| Day 25 | Day 25

## SCR51
|  | Script ID | SCR51 |  | Power Point
|  | Script Name | Update To Power Outage And Service Restoration Contact Information
|  | Script Storyline | Current CR updates the power outage contact information by sending the TDSP an 814_PC.
|  | Success Criteria | CR sends 814_PC with contact updates. The TDSP updates the premise.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | CC2010-739 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | CR1 set up as ROR. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
| Day 6 | Day 06
Day 07
Day 08
Day 09
Day 10
|  | Day 11 | CR1 | TDSP | 814_PC | REF~SU~Y; PER with N1~FJ segment; PER~PO~~TE~5551234567~PC~9998887777~EM~CONTACT@EMAIL.COM | CR updates premise information with and contact information. | 1 |  |  | CR1
|  | Day 12 | TDSP | CR1 | 814_PD | ASI~WQ~001 | Response to CR1 indicating the premise has been updated. | 1 |  |  | CR1
| Day 7 | Day 13
| Day 8 | Day 14
| Day 9 | Day 15
Day 16
Day 17
Day 18
Day 19
Day 20
Day 21
| Day 16 | Day 22
| Day 17 | Day 23
| Day 18 | Day 24
| Day 19 | Day 25
| Day 20 | Day 26
| Day 21 | Day 27
| Day 22 | Day 28
| Day 23 | Day 29
| Day 24 | Day 30
| Day 25 | Day 31
| Day 26 | Day 32
| Day 27 | Day 33
| Day 28 | Day 34
| Day 29 | Day 35
Day 36
| Day 31 | Day 37
| Day 32 | Day 38
| Day 33 | Day 39
| Day 34 | Day 40

## SCR53
|  | Script ID | SCR53
|  | Script Name | Switch Hold Addition and Removal
|  | Script Storyline | TDSP detects meter tampering and sends 814_20M to ERCOT. Tampering Switch hold added by ERCOT and forwards the 814_20M to Current CR. Current CR sends 650_01 to TDSP to add a Payment Plan Switch hold. TDSP sends 814_20M to ERCOT to add the Payment Plan Switch hold. ERCOT forwards 814_20M to the Current CR. Current CR removes both Switch holds.
|  | Success Criteria | Meter tampering and Payment Plan Switch holds added and removed successfully by CR, TDSP, and ERCOT. TML/MIS testing will be done during internal ERCOT testing.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | CC2010-734 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | CR1 set up as ROR. | CR1 set up as ROR. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
|  | Day 01 | TDSP | ERCOT | 814_20 | REF~ST~SHA REF~TD~REFST | Tampering Switch hold added
|  | Day 02 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept Response
|  |  | ERCOT | CR1 | 814_20 | REF~ST~SHA REF~TD~REFST | ERCOT forwards 814_20M to Current CR
|  | Day 03 | CR1 | TDSP | 650_01 | BGN07=SH REF~8X~SH001 | Request to add Payment Plan Switch hold
|  | Day 04 | TDSP | CR1 | 650_02 | BGN07=SH BGN08=51 REF~8X~SH001 REF~SH~APS | Accept Response
| Day 1 | Day 05 | TDSP | ERCOT | 814_20 | REF~SP~SHA REF~TD~REFSP | Payment Plan Switch hold added
| Day 12 | Day 06 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept Response
|  |  | ERCOT | CR1 | 814_20 | REF~SP~SHA REF~TD~REFSP | ERCOT forwards 814_20M to Current CR
Day 12
| Day 13 | Day 07 | CR1 | TDSP | 650_01 | BGN07=SH REF~8X~SH003 | Request to remove Tampering Switch hold
Day 13
| Day 14 | Day 08 | TDSP | CR1 | 650_02 | BGN07=SH BGN08=51 REF~8X~SH003 REF~SH~RTS | Accept Response
Day 14
| Day 15 | Day 09 | TDSP | ERCOT | 814_20 | REF~ST~SHR REF~TD~REFST | Tampering Switch hold removed
Day 15
| Day 17 | Day 10 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept Response
|  |  | ERCOT | CR1 | 814_20 | REF~ST~SHR REF~TD~REFST | ERCOT forwards 814_20M to Current CR
|  | Day 11 | CR1 | TDSP | 650_01 | BGN07=SH REF~8X~SH002 | Request to remove Payment Plan Switch hold
|  | Day 12 | TDSP | CR1 | 650_02 | BGN07=SH BGN08=51 REF~8X~SH002 REF~SH~RPS | Accept Response
| Day 8 | Day 13 | TDSP | ERCOT | 814_20 | REF~SP~SHR REF~TD~REFSP | Payment Plan Switch hold removed
| Day 21 | Day 14 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept Response
|  |  | ERCOT | CR1 | 814_20 | REF~SP~SHR REF~TD~REFSP | ERCOT forwards 814_20M to Current CR

## SCR54
|  | Script ID | SCR54 |  | Power Point
|  | Script Name | Switch Rejected Due To Switch Hold In Place
|  | Script Storyline | Switch Hold for Payment Plan placed on ESI ID. CR1 submits a Switch and TDSP rejects for SHF due to the Switch Hold.
|  | Success Criteria | TDSP rejects Switch with an 814_04R for SHF. Switch is cancelled at ERCOT and CR1 successfully processes 814_05R SHF transaction.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Small Non Residential | NA | None | SIM CR2 | No
|  | Operating Rule | CC2010-736 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | SIM CR2 set up as ROR; Manually Add Tampering Switch Hold | SIM CR2 set up as ROR; Manually Add Tampering Switch Hold | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
|  | Day 06 | CR1 | ERCOT | 814_01 | No DTM~MRR segment | Standard switch request for Customer B
|  | Day 07 | ERCOT | TDSP | 814_03 | LIN~1~SH~EL~SH~CE | Standard switch request
|  | Day 08 | TDSP | ERCOT | 814_04 | ASI~U~021 REF~7G~SHF | Switch rejected by TDSP due to Switch hold
|  | Day 09 | ERCOT | CR1 | 814_05 | ASI~U~021 REF~7G~SHF | ERCOT sends reject to CR1

## SCR56
|  | Script ID | SCR56
|  | Script Name | Switch Cancelled For Complete Unexecutable
|  | Script Storyline | TDSP completes a Switch for Complete Unexecutable.
|  | Success Criteria | CR submits a self-selected Switch. TDSP completes the Switch for Complete Unexecutable.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | SIM CR2 | No
|  | Operating Rule | CC2010-745 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | SIM CR2 set up as ROR. | SIM CR2 set up as ROR. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
Day 03
Day 04
| Day 1 | Day 05
| Day 12 | Day 06 | CR1 | ERCOT | 814_01 | RMRD = Day 15 (DTM~MRR) LIN~1~SH~EL~SH~CE~SH~SW No REF~WI | Self-selected switch request for Customer A
Day 12
| Day 13 | Day 07 | ERCOT | TDSP | 814_03 | RMRD = Day 15 (DTM~MRR) LIN~1~SH~EL~SH~CE~SH~SW No REF~WI | Self-selected switch request for Customer A
Day 13
|  | Day 08 | TDSP | ERCOT | 814_04 | SMRD = Day 15 | Switch scheduled for Day 15
|  | Day 09 | ERCOT | CR1 | 814_05 | SMRD = Day 15 | Switch scheduled for Day 15
| Day 14 | Day 10 | TDSP | ERCOT | 814_28 | BGN07 = 09 LIN~1~SH~EL~SH~CE~SH~SW ASI~9~101 | Switch completed unexecutable
Day 14
| Day 15 | Day 11 | ERCOT | CR1 | 814_28 | BGN07 = 09 LIN~1~SH~EL~SH~CE~SH~SW ASI~9~101 | ERCOT cancels Switch and forwards 814_28 09 to CR1
Day 15

## SCR59
|  | Script ID | SCR59 |  | Power Point
|  | Script Name | Service Order - Installation of Generation Equipment
|  | Script Storyline | CR of record sends a 650_01 with FI012 code to TDSP. TDSP responds to CR with a 650_02 notifying the CR that the TDSP has received the information and will start the appropriate investigation.
|  | Success Criteria | CR is able to generate a 650_01 with appropriate code
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | NA | None | CR1 | No
|  | Operating Rule | CC2010-753 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP
|  | Pretest Setup |  | CR1 set up as ROR
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Day 01 | CR1 | TDSP | 650_01 | REF~8X~FI012 | Service Order Request sent with code for generation equipment | 1 |  |  | CR1
| Day 2 | Day 02 | TDSP | CR1 | 650_02 | BGN08 = WQ REF~8X~FI012 | TDSP responds to 650_01 | 1 |  |  | CR1
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
Day 06
Day 07
| Day10 | Day 08
Day 09
| Day 013 | Day 10
Day 11
Day 12
Day 13
| Day 014 | Day 14
Day 15
Day 16
Day 17
Day 18
Day 19
Day 20
Day 21
Day 22
| Day 27 | Day 23
| Day 28 | Day 24
| Day 29 | Day 25
Day 26
Day 27
| Day 32 | Day 28
| Day 33 | Day 29
| Day 34 | Day 30

## SCR61
|  | Script ID | SCR61 |  | Power Point
|  | Script Name | Move In Containing Special Instructions
|  | Script Storyline | CR submits a Move In with special instructions. ERCOT communicates this to the TDSP. TDSP notes the special instructions and schedules the Move In.
|  | Success Criteria | CR, ERCOT, and TDSP are able to process a Move In that contains special instructions.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | None | No
|  | Operating Rule | CC2010-759 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | None | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
|  | Day 06 | CR1 | ERCOT | 814_16 | RMRD = Day 10 (DTM~375) REF~RAA~GATE LOCKED BEFORE 5 PM | MVI requested for Day 10 with special instructions. Customer A | 1 |  |  | CR1
|  | Day 07 | ERCOT | TDSP | 814_03 | RMRD = Day 10 (DTM~375) REF~RAA~GATE LOCKED BEFORE 5 PM | MVI requested for Day 10 with special instructions. Customer A | 1 |  |  | CR1
|  | Day 08 | TDSP | ERCOT | 814_04 | SMRD = Day 10 (DTM~150) | TDSP response accepting MVI | 1 |  |  | CR1
|  | Day 09 | ERCOT | CR1 | 814_05 | SMRD = Day 10 (DTM~150) | ERCOT sends accept response to CR1 | 1 |  |  | CR1

## SCR64
|  | Script ID | SCR64 |  | Power Point
|  | Script Name | Advanced Meter Removal
|  | Script Storyline | TDSP removes AMS meter designation from ESI ID.
|  | Success Criteria | TDSP sends 814_20M to remove AMS meter designation from ESI ID. ERCOT forwards the 814_20M to current CR.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Small Commercial | Non AMS | None | CR1 | No
|  | Operating Rule | CC2011-778 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | CR1 set up as ROR | CR1 set up as ROR | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01
| Day 2 | Day 02
| Day 3 | Day 03
| Day 4 | Day 04
| Day 5 | Day 05
| Day 6 | Day 06 | TDSP | ERCOT | 814_20 | REF~TD~REFMR REF~MR~AMSM | TDSP adds AMSM meter designation
|  | Day 07 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept response
|  |  | ERCOT | CR1 | 814_20 | ASI~7~001 REF~TD~REFMR REF~MR~AMSM | ERCOT forwards 814_20M to Current CR
|  | Day 08 | TDSP | ERCOT | 814_20 | REF~TD~REFMR REF~MR~AMSR | TDSP adds AMSR meter designation
|  | Day 09 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept response
|  |  | ERCOT | CR1 | 814_20 | ASI~7~001 REF~TD~REFMR REF~MR~AMSR | ERCOT forwards 814_20M to Current CR
Day 10
|  | Day 11 | TDSP | ERCOT | 814_20 | ASI~7~001 REF~TD~REFMR REF~MR~R | TDSP removes AMS meter designation
|  | Day 12 | ERCOT | TDSP | 814_21 | ASI~WQ~001 | Accept response
|  |  | ERCOT | CR1 | 814_20 | ASI~7~001 REF~TD~REFMR REF~MR~R | ERCOT forwards 814_20M to Current CR

## SCR65
| Script ID | SCR65 |  | Power Point
| Script Name | Complete Unexecutable Rejected Due To Order Already Cancelled
| Script Storyline | SIM CR2 submits a MVI. TDSP schedules the MVI. ERCOT hard cancels the MVI and sends 814_08 transactions to the TDSP and SIM CR2. TDSP holds the 814_08 and instead sends an 814_28 09 Complete Unexecutable. ERCOT rejects the transaction due to the MVI already being cancelled.
| Success Criteria | ERCOT rejects the 814_28 09 Complete Unexecutable and sends 814_29R A78 back to TDSP.
| Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Residential | Single Non IDR | None | None | No
| Operating Rule | CC2008-720 |  | TRACK | TX SET V4.0
Simulated Entity
| Duns Number | 111111112
| Number of CR's | 1
|  | ERCOT | TDSP | CR1
| Pretest Setup | None | None
Checkpoint Date | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | SIM CR2 | ERCOT | 814_16 | RMRD = Day 7 (DTM~375) | MVI requested for Day 7. Customer A | 1 |  |  | SIM CR2
| Day 02 | ERCOT | TDSP | 814_03 | RMRD = Day 7 (DTM~375) | MVI requested for Day 7. Customer A | 1 |  |  | SIM CR2
| Day 03 | TDSP | ERCOT | 814_04 | SMRD = Day 7 (DTM~150) | TDSP response accepting MVI | 1 |  |  | SIM CR2
|  | ERCOT | SIM CR2 | 814_05 | SMRD = Day 7 (DTM~150) | ERCOT sends accept response to CR1 | 1 |  |  | SIM CR2
| Day 04 | ERCOT | TDSP | 814_08 | REF~1P~MAN | ERCOT hard cancels the MVI. TDSP holds the 814_08 and does not process it. | 1 |  |  | SIM CR2
|  | ERCOT | SIM CR2 | 814_08 | REF~1P~MAN | ERCOT hard cancels the MVI.
| Day 05 | TDSP | ERCOT | 814_28 | BGN07 = 09 ASI~09~021 REF~G7~T016 | TDSP sends complete unexecutable | 1 |  |  | SIM CR2
| Day 06 | ERCOT | TDSP | 814_29 | REF~7G~A78 | ERCOT rejects complete unexecutable due to MVI already being cancelled | 1 |  |  | SIM CR2

## STK30
|  | Script ID | STK30
|  | Script Name | Tampering Switch Hold Prior To Mass Transition
|  | Script Storyline | TDSP applies Tampering Switch hold on ESI ID that SIM CR2 is current ROR. ERCOT initiates Mass Transition. TDSP schedules the order and communicates that a Tampering Switch hold is in place. ERCOT notifies POLR CR of this in the 814_14 transaction.
|  | Success Criteria | Tampering Switch hold added prior to Mass Transition. TDSP communicates this in the 814_04 and ERCOT sends the segment in the 814_14 to the POLR CR.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | SIM CR2 | No
|  | Operating Rule | CC2011-780 |  | TRACK | TX SET V4.0
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | SIM CR2 set up as ROR. Manually Add Tampering Switch Hold | SIM CR2 set up as ROR. Manually Add Tampering Switch Hold | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
Day 03
Day 04
| Day 1 | Day 05 | ERCOT | TDSP | 814_03 | BGN07 = TS LIN~1~SH~EL~SH~CE~SH~SW~SH~HI | Mass Transition initiated for SIM CR2
| Day 12 | Day 06 | TDSP | ERCOT | 814_04 | BGN07 = TS REF~SH~Y | Switch hold indicator = Y due to tampering flag
Day 12
| Day 13 | Day 07 | ERCOT | POLR CR | 814_14 | BGN07 = TS REF~SH~Y
Day 13

## STK31
|  | Script ID | SCR62 |  | Power Point
|  | Script Name | Move In and Move Out Scheduled for Same Day - MVO become Force-Out and is Unexecuted
|  | Script Storyline | CR1 is REP of record. CR1 sends a move out request, for Customer A for Day 15, to the TDSP. The TDSP responds per protocol. On Day 15 SIM CR2 sends a same day move in request to the TDSP. The TDSP responds per protocol. Due to CC2010-766, the move out request is now considered a Force-out and the order is unexecuted using an 814_28 with code T023.
|  | Success Criteria | CR sends a request for a move-out on a residential premise for Day 15. TDSP responds to request. SIM CR2 requests a same day Day 15 move-in. The MVO is unexecuted using code T023. The MVI effectuates.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | CC2010-766 |  | TRACK | TX SET V4.0
Simulated Entity
|  | Duns Number | 111111112
|  | Number of CR's | 2
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | CR1 set up as ROR | CR1 set up as ROR | CR1 set up as ROR
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | CR1 | ERCOT | 814_24 | RMRD = Day 15 (DTM~376) | MVO requested for Day 15. Customer A | 1 |  |  | CR1
| Day 2 | Day 02 | ERCOT | TDSP | 814_24 | RMRD = Day 15 (DTM~376) | MVO requested for Day 15. Customer A | 1 |  |  | CR1
| Day 3 | Day 03 | TDSP | ERCOT | 814_25 | SMRD = Day 15 (DTM~376) | TDSP sends scheduled MVO for Day 15 as the date in the DTM~376 | 1 |  |  | CR1
| Day 4 | Day 04 | ERCOT | CR1 | 814_25 | SMRD = Day 15 (DTM~376) | TDSP sends scheduled MVO for Day 15 as the date in the DTM~376 | 1 |  |  | CR1
| Day 5 | Day 05
| Day 6 | Day 06
Day 07
Day 08
Day 09
Day 10
Day 11
Day 12
Day 13
[7 empty] | Day 1 of 2 day window for Day 15 MVO | 1 |  | E
Day 14
[7 empty] | Day 2 of 2 day window for Day 15 MVO | 1 |  | E
|  | Day 15 | SIM CR2 | ERCOT | 814_16 | RMRD = Day 15 (DTM~375) | MVI requested for Day 15. Customer B | 2 |  |  | SIM CR2
|  |  | ERCOT | TDSP | 814_03 | RMRD = Day 15 (DTM~375) | MVI requested for Day 15. Customer B | 2 |  |  | SIM CR2
|  |  | TDSP | ERCOT | 814_04 | SMRD = Day 15 (DTM~150) | TDSP response accepting MVI | 2 |  |  | SIM CR2
|  |  | TDSP | ERCOT | 814_28 | REF~G7~T023 | TDSP unexecutes MVO request | 1 |  |  | CR1
[7 empty] | Day 15 MVI Effectuates | 2 | MVI |  | SIM CR2
|  | Day 16 | ERCOT | SIM CR2 | 814_05 | SMRD = Day 15 (DTM~150) | ERCOT sends accept response to SIM CR2 | 2 |  |  | SIM CR2
|  |  | ERCOT | CR1 | 814_28 | REF~G7~T023 | ERCOT sends unexecutable response | 1 |  |  | CR1
Day 17
|  | Day 18 | TDSP | ERCOT | 867_04 | Initial Read for MVI | Initial Read for Customer B | 2 |  |  | SIM CR2
|  |  | TDSP | ERCOT | 867_03 | Final Read for Customer A | Final Read for Customer A | 1 |  |  | CR1
|  |  | TDSP | CR1 | 810_02 | Final Bill for Customer A | Final Bill for Customer A | 1 |  |  | CR1
|  | Day 19 | ERCOT | CR1 | 867_03 | Final Read for Customer A | Final Read for Customer A | 1 |  |  | CR1
|  |  | ERCOT | SIM CR2 | 867_04 | Initial Read for MVI | Initial Read for Customer B | 2 |  |  | SIM CR2