## EXAMPLE FROM PHASE II
|  | Script ID | MTDV3 |  | Power Point
|  | Script Name | DEV-LSE TDSP Submit
|  | Script Storyline | TDSP submits MarkeTrak with modification of StartTime and StopTime and inputs "Service History with DUNS for Effected Period". ERCOT will review MT and perform their validations. If the MT passes validation, it is transitioned to the CR to begin working. CR will review MT and compares to their system and agrees to the issue.
|  | Success Criteria | One issue is downloaded and successfully processed and the results correctly uploaded to the MarkeTrak system. The TDSP continues processing until the issue is closed.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | TDSP | ERCOT | Create: TDSP | GUI | TDSP selects "LSE Date Change Start and Stop" from the submit tree. TDSP fills in all required fields. TDSP clicks "OK" | Entering the Service History with DUNS for Effected Period (SHwDfEP) at the submission of this issue will test if the (SHwDfEP) information is proprietary only to the TDSP and ERCOT.
|  |  | 1 | ERCOT | ERCOT | New ERCOT | Begin Working | ERCOT selects "Begin Working".
|  |  | 1 | ERCOT | CR | In Progress (ERCOT) ERCOT | Passed Analysis | ERCOT validates the MT against their internal data. ERCOT agrees selects "Passed Analysis", and transitions the issue to the CR.
|  |  | 1 | CR | CR | New (Pending Approval) CR | Begin Working | CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Assignee)
|  |  | 1 | CR | ERCOT | In Progress (Pending Approval): CR | Update Approved | CR selects "Update Approved"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT Resolve) ERCOT | Begin Working | ERCOT selects "Begin Working".
|  |  | 1 | ERCOT | TDSP | In Progress (ERCOT Resolve) ERCOT | Complete | ERCOT selects "Complete"
|  |  | 1 | TDSP | TDSP | Pending Complete TDSP | Complete | TDSP reviews 727 extract. TDSP selects "Complete".