|  |  |  |  | Monthly System Planning Report |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | April 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 201 active generation interconnection requests totaling over 62,000 MW. This includes over 36,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $555.6 Million - Transmission Projects endorsed in 2011 total $23.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2011 total about $174.0 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Signed Generation Interconnection Agreements

## FRV Solar (10INR0082) 30 MW Wind in Travis County

## New Generation Registering for Commercial Operations

The total installed wind capacity is now reported as 9,452 MW by the resource owners through the registration process. Capacity by North, South and West is 292 MW, 1216 MW, and 7943 MW respectively. 850 MW is able to switch between the West and South zones.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 201 active generation interconnection or change requests |  |  |  |  |
| As of April 30, 2011 | North | South | West | Total |
| Security Screening Study | 2 | 0 | 6 | 8 |
| SSS Completed | 1 | 10 | 21 | 32 |
| Full Interconnect Study | 21 | 15 | 92 | 128 |
| FIS Completed | 1 | 8 | 5 | 14 |
| Interconnect Agreement Completed | 8 | 8 | 3 | 19 |
| Capacity under Interconnection Agreements | 5,122 | 4,344 | 520 | 9,986 |
| Capacity for Grid, MW | 17,414 | 12,179 | 33,044 | 62,637 |
| Wind Capacity, MW | 3,056 | 3,399 | 29,669 | 36,124 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CombinedCycle |  |  | 5,297 | 11,988 |
| Gas-All Other |  |  |  | 966 |
| Total Gas | 327 | 7,330 | 5,297 | 12,954 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 865 | 3,210 | 4,075 |
| Wind | 3,210 | 27,795 | 5,119 | 36,124 |
| Solar | 640 | 784 | 30 | 1,454 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 740 | 1,240 | 1,980 |
| Grand Total | 4,177 | 37,564 | 20,896 | 62,637 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of April 30, 2011 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Apr-11 |  | Wind | 465 | Date |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Jul-11 |  | Coal | 260 | Date |
| 10INR0010 | Jack County 2 | IA | Jack | North | Sep-11 |  | Gas-CC | 565 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-11 |  | Wind | 150 | Date |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-11 |  | Wind | 400 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 10INR0082 | FRV AE Solar | IA | Travis | North | Dec-11 |  | Solar | 30 | NEW |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 |  |
| 08INR0062 | Archer-Young | IA | Young | West | Mar-12 |  | Wind | 250 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1001 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 |  | Biomass | 100 | Date |
| 10INR0060 | Magic Valley Wind Project | IA | Willacy | South | Jun-12 |  | Wind | 202 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Sep-12 |  | Wind | 150 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind | 400 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind | 202 | Date |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-14 |  | Gas-CC | 780 | Date |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC | 1792 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas-CC | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-15 |  | Gas-CC | 1380 | Date |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other | 620 | Date |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other | 620 | Date |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal | 660 | Date |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3200 |  |
|  |  |  |  |  |  |  | Total | 20,896 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0054 | Palo Pinto | 36 | TBD | Wind |  | 10INR0079 | Nolan | 60 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 10INR0029 | Hood | 810 | TBD | Gas |
| 10INR0052a | Knox | 21 | TBD | Wind |  | 10INR0013 | Upton | 400 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 09INR0074 | Motley | 70 | TBD | Wind |
| 11INR0029 | Throckmorton | 200 | TBD | Wind |  | 10INR0042 | Mason | 170 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0051 | Brazoria | 200 | TBD | Wind |
| 10INR0033 | Armstrong | 399 | TBD | Wind |  | 10INR0019 | Deaf Smith | 609 | TBD | Wind |
| 10INR0008 | Pecos | 500 | TBD | Wind |  | 07INR0013 | Coke | 200 | TBD | Wind |
| 11INR0076 | Archer | 94 | TBD | Wind |  | 11INR0088 | Brazos | 45 | TBD | Gas |
| 11INR0085 | Nolan | 106 | TBD | Wind |  | 11INR0050 | Crosby | 149 | TBD | Wind |
| 11INR0075 | Fort Bend | 15 | TBD | Coal |  | 11INR0037 | Smith | 50 | TBD | Biomass |
| 11INR0062 | Nueces | 149 | TBD | Wind |  | 11INR0061 | Presidio | 90 | TBD | Solar |
| 11INR0060 | Tom Green | 90 | TBD | Solar |  | 11INR0058 | Pecos | 135 | TBD | Solar |
| 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |  | 11INR0091 | Webb | 92 | Jun-11 | Wind |
| 11INR0057 | Cameron | 165 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0040 | freestone | 640 | Aug-11 | Gas |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 11INR0094 | Kent | 100 | Nov-11 | Solar |
| 11INR0090 | Howard | 60 | Nov-11 | Solar |  | 11INR0070 | Reeves | 50 | Dec-11 | Solar |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 09INR0048 | Jack | 100 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 10INR0085 | Ector | 40 | Jan-12 | Solar |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 12INR0045 | Kleberg | 135 | Mar-12 | Wind |  | 12INR0075 | Wilbarger | 499 | Apr-12 | Wind |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0026 | Randall | 400 | Oct-12 | Wind |
| 08INR0041 | Coke | 200 | Oct-12 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0072 | Kinney | 100 | Dec-12 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-12 | Wind |
| 12INR0057 | Ector | 40 | Dec-12 | Solar |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 12INR0027 | Gray | 200 | Jan-13 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 12INR0034 | Borden | 342 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 10INR0056 | Borden | 249 | Mar-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0023 | Ector | 240 | Jul-13 | Gas |
| 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |  | 13INR0025 | Randall | 150 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 11INR0013 | Mills | 150 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 10INR0009 | Castro | 300 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 13INR0010b | Parmer | 500 | Jan-14 | Wind |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 10INR0015 | Mitchell | 350 | May-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0006 | Floyd | 151 | Oct-14 | Wind |
| 13INR0021 | Llano | 600 | Dec-14 | Gas |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 13INR0010c | Parmer | 500 | Jan-15 | Wind |
| 15INR0011b | Borden | 38 | Dec-15 | Solar |  | 15INR0011a | Borden | 112 | Dec-15 | Wind |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 16INR0002 | Brazoria | 700 | Jun-17 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Brazos Electric Cooperative has submitted a project to move some load that is currently being served by the Entergy Texas system into the ERCOT system.  The project would involve disconnecting the subject load from the Entergy Texas system, constructing a new 345/ 138 kV substation in ERCOT, upgrading an existing 69 kV line in the ERCOT system and constructing two new 138 kV lines to serve the load from the ERCOT system.  The estimated cost of this project is $51.1 M.  ERCOT has completed the Independent Review for this Tier 1 project.

- CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

- American Electric Power Service Corporation has submitted the Laredo to the lower Rio Grande Valley 345 kV Project to improve reliability of the lower Rio Grande Valley transmission system. This project proposes a new 345kV transmission line to be constructed from Laredo to the lower Rio Grande Valley to provide a third 345kV source to the area with an in-service date in the 2016/2017 timeframe. The estimated cost for this project is $379.5 Million. This Tier 1 project is currently in the comment phase.

- Oncor and WETT has submitted a project with proposed changes to the Lamesa Area Upgrade project. The original Lamesa Area Upgrade Project was reviewed and approved by RPG previously. As per the RPG Charter and Procedures changes to already-approved projects will be processed as Tier 3 project. This Tier 3 project has completed the RPG review and ERCOT has sent an acceptance letter to Oncor and WETT .

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - March 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 3349 | 0 - 410 | 13,949,765 | CREZ |  |
| Bluff Creek Auto T2_H ,T2_L & T2_T | Nicole - Oak Creek 138kV | 2136 | 0 - 209 | 1,610,275 | CREZ |  |
| Odessa North - Odessa Basin Switch 69kV | Holt Switch - Ector Shell Tap 69kV | 108 | 0 - 2800 | 934,380 | Upgrade existing 69kV line [14TPIT0008] |  |
| Odessa EHV Switch - Morgan Creek SES & Quail Switch 345kV, Gail - Keysb 138kV, Willow Valley Switch - Exxon Sharon Ridge 138 kV | Ackerly Vealmoor Switch - Ackerly 69kV | 624 | 0 - 2800 | 796,808 | Lamesa - Ackerly Vealmoor 69 kV line rebuild [ 11TPIT0060] |  |
| Fort Stockton - Barilla 138kV | Fort Stockton Switch - Barrilla 69kV | 530 | 0 - 952 | 581,960 | CREZ |  |
| Lon Hill 345/138kV AXFMR | Nelson Sharpe - Celanese Bishop 138kV | 157 | 22 - 3500 | 391,772 |  |  |
| Pawnee - Lon Hill 345kV | Sinton - Skidmore 69kV | 284 | 0 - 2800 | 310,484 | Lon Hill to Sinton 69 kVLine Modifications [11TPIT0103] |  |
| Moss Switch - Holt Switch 138kV | Odessa North 138/69kV autotransformer | 40 | 0 - 2800 | 305,580 | 5YTP [2009-R4] |  |
| Coleto Creek Generator 1, STP Units 1 &2 | Blessing - Lolita 138kV | 82 | 0 - 1461 | 204,277 |  |  |
| Graham SES - Long Creek & Cook Field 345kV | Bomarton - Seymour 69kV | 30 | 2334 - 2800 | 167,506 |  |  |

Binding Constraints - April 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 3023 | 0 - 3515 | 11,286,160 | CREZ |  |
| Long Creek - Sweetwater - Abilene Mulberry 345kV, Graham SES - Long Creek Switching Station 345kV | Paint Creek - Murray TU 138KV | 1508 | 0 - 3500 | 8,839,628 | CREZ |  |
| Jewett - Singleton 345kV | Twin Oak Switch - Jack Creek 345kV | 715 | 0 - 4500 | 5,480,086 | Zenith to Fayetteville 345kV project [14TPIT0002] |  |
| Moss Switch - Holt Switch 138kV | Odessa North 138/69kV autotransformer | 233 | 0 - 2800 | 2,265,354 | 5YTP [2010-R7, R8] |  |
| Watermill Switch - Desoto Switch and Cedar Hill Switch 345kV | Amelia Street - UT SW Medical Center 138kV | 32 | 622 - 3500 | 1,434,716 |  |  |
| PH Robinson - Center and Cedar Bayou Plant 345kV, North Alvin - Hastings 138KV | North Alvin - Alvin Sub 138kV | 102 | 0 - 3500 | 1,393,513 | Upgrade North Alvin-Hastings [14TPIT0018] |  |
| Singleton - Zenith 345kV | Singleton - Tomball 345KV | 282 | 0 - 4500 | 1,326,692 | Zenith to Fayetteville 345kV project [14TPIT0002] |  |
| Ingleside Cogen Switch - Oxychem Corpus Christi 138kV | Dupont PP1 Ingleside - Dupont Switch Ingleside 138kV | 24 | 0 - 3500 | 1,302,468 |  |  |
| Fort Stockton - Barilla 138kV | Fort Stockton Switch - Barilla 69kV | 1297 | 0 - 1202 | 1,276,250 | CREZ |  |
| Singleton - Tomball and Singleton - Roans Prairie 345kV | Singleton - Zenith 345kV | 383 | 0 - 4500 | 1,220,079 | Zenith to Fayetteville 345kV project [14TPIT0002] |  |

Binding Constraints - January to April 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 9618 | 0 - 3515 | 41,616,966 | CREZ |  |
| BASE CASE | Valley Import | 273 | 0 - 5000 | 41,457,339 |  |  |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0 - 4500 | 31,689,757 |  |  |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 383 | 40 - 3500 | 22,404,765 | 5YTP [2010-R12] |  |
| West Levee Switch 345/138kV AT1 | West Levee Switch 345/138kV AT2 | 98 | 0 - 3500 | 9,073,730 | 5YTP [2009-R21] |  |
| Long Creek - Sweetwater - Abilene Mulberry 345kV, Graham SES - Long Creek Switching Station 345kV | Paint Creek - Murray TU 138KV | 1508 | 0 - 3500 | 8,839,628 | CREZ |  |
| Chamber - King & Cedar Bayou - Northbelt 345kV | Center - PH Robinson 345kV | 78 | 0 - 4500 | 6,386,600 |  |  |
| Jewett - Singleton 345kV | Twin Oak Switch - Jack Creek 345kV | 715 | 0 - 4500 | 5,480,086 | Zenith to Fayetteville 345kV project [14TPIT0002] |  |
| Braunig - Toyota & Valley 138kV, DCKT WB Tuttle - Austin Road 138kV, Fern Street - Ball Park 138kV, Nacogdoches Road - Skyline 138kV, Streich - Braunig 138kV, Calavers -Streich 138kV | Five Points - Westside CPS 138kV | 2037 | 0 - 3500 | 5,108,772 | Westside substation equipment upgrade [12TPIT0054] | Outage on Cagnon - Marbach 138kV, Marbach - Valley 138kV |
| Kendall 345/138kV AT2 | Kendall 345/138kV AT1 | 225 | 0 - 4500 | 4,434,846 | Kendall Autotransformer Replacement [ 12TPIT0024] |  |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Work continues on Data Set A.  TPMCRs have been accepted and and MOD was re-seeded with a new base case incorporating the TPMCRs.  The Pass 0 comparison template spreadsheet has been created by Centerpoint.  Comments are due May 20th.  The remaining schedule is as follows:

  - May 13, 2011	DSA Pass 0 Projects and Profiles from all (projected on-time)

  - June 3, 2011	DSA Pass 1 Projects and Profiles due from all

  - June 17, 2011	DSA Pass 2 Projects and Profiles due from all

  - June 27, 2011	DSA Pass 3 Comparison Spreadsheet Template built

  - June 28 – 30 	DSA Meeting in Taylor, complete Passes 3, 4, 5

  - July 8, 2011	DSA Pass 6 Projects and Profiles due from all

  - July 15, 2011	DSA cases finalized and posted

  - July 18, 2011	DSA Final Comparison Spreadsheet Template built

  - July 29, 2011	DSA Final Comparison comments due for posting

  - August 1, 2011	DSB Start

- ERCOT has submitted all nine parts of SCR760 as enhancements to Siemens Topology Processor following ERCOT Board approval in March 2011.  The first three parts submitted were items 3, 7 and 8.  The requirements for these items have been vetted by ERCOT, TSPs, and Siemens.  Siemens will be updating their cost estimates for these three items and then ERCOT will prepare a Statement of Work (SOW).

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Submitted |
| SCR760-2 | Distribution Capacitor banks | Submitted |
| SCR760-3 | Zero Impedance Line Ratings | Planning |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Submitted |
| SCR760-5 | Additional Transformer Data for Planning | Submitted |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Planning |
| SCR760-8 | Phase shift of Autos for short circuit studies | Planning |
| SCR760-9 | Multisection Line Grouping | Submitted |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- ERCOT is currently working on the 2011 Five-Year Transmission Plan (5YTP) studies. Currently working on creating the start cases based on the latest 2011 SSWG Data Set B cases posted on April 29, 2011.

- Transient Stability Study for 2011 winter off-peak conditions: As part of the annual reliability assessment of the network, a transient stability study was performed on an ERCOT 2011 winter off-peak case.  The study shows that the 2011 winter off-peak conditions network mets the NERC TPL reliability requirements.

- The dynamic data set for 2011 summer on-peak without wind models was approved by DWG.  ERCOT is currently working on the corresponding dynamic data set for 2011 summer on-peak with wind models.

- The West-to-North Stability matrix is being updated for the year 2011.  ERCOT is evaluating stability limits for selected scenarios corresponding to low-load, medium load and high-load network conditions.