|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for February 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 192 active generation interconnection requests totaling over 63,000 MW. This includes over 36,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $176.1 Million - Transmission Projects endorsed in 2011 total $23.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.3 Billion - Transmission Projects energized in 2010 total about $857.1 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

The total installed wind capacity is reported as 9,400 MW by the resource owners through the registration process.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 191 active generation interconnection or change requests |  |  |  |  |
| As of February 28, 2011 | North | South | West | Total |
| Security Screening Study | 2 | 6 | 8 | 16 |
| SSS Completed | 1 | 2 | 15 | 18 |
| Full Interconnect Study | 18 | 14 | 87 | 119 |
| FIS Completed | 5 | 13 | 5 | 23 |
| Interconnect Agreement Completed | 7 | 6 | 3 | 16 |
| Capacity under Interconnection Agreements | 5,092 | 3,742 | 520 | 9,354 |
| Capacity for Grid, MW | 18,690 | 12,845 | 31,809 | 63,344 |
| Wind Capacity, MW | 3,457 | 4,067 | 28,839 | 36,363 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CombinedCycle |  |  | 5,297 | 11,988 |
| Gas-All Other |  |  |  | 650 |
| Total Gas | 11 | 7,330 | 5,297 | 12,638 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,210 | 4,950 |
| Wind | 2,870 | 28,176 | 5,317 | 36,363 |
| Solar | 544 | 819 |  | 1,363 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 740 | 1,240 | 1,980 |
| Grand Total | 3,425 | 38,855 | 21,064 | 63,344 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of February 28, 2011 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 260 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas | 565 | Capacity |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-11 |  | Wind | 400 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jan-12 |  | Wind | 150 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 08INR0062 | Archer-Young | IA | Young | West | Mar-12 |  | Wind | 250 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1,001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jul-12 |  | Wind | 400 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Sep-12 |  | Wind | 150 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Dec-13 |  | Wind | 400 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Feb-14 |  | Gas | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas | 1,792 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-14 |  | Gas | 1,380 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1,200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas | 780 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Jul-15 |  | Other | 620 | Date |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-16 |  | Coal | 660 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2,700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Jul-16 |  | Other | 620 | Date |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3,200 |  |
| 04INR0011b | Cedar Elm | XX | Shackelford | West | 6/2/2014 |  | Wind | 136 | Cancel |
| 04INR0011c | Cottonwood Wind | XX | Shackelford | West | 6/2/2014 |  | Wind | 100 | Cancel |
|  |  |  |  |  |  |  | TOTAL | 21,064 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 09INR0061 | Kent | 258 | TBD | Wind |
| 10INR0048 | Hardeman | 1,000 | TBD | Wind |  | 10INR0016 | Childress | 150 | TBD | Wind |
| 10INR0054 | Palo Pinto | 36 | TBD | Wind |  | 10INR0079 | Nolan | 60 | TBD | Wind |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 10INR0041 | Floyd | 135 | TBD | Wind |
| 09INR0074 | Motley | 70 | TBD | Wind |  | 11INR0029 | Throckmorton | 200 | TBD | Wind |
| 10INR0019 | Deaf Smith | 609 | TBD | Wind |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0080 | Presidio | 144 | TBD | Solar |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0051 | Brazoria | 200 | TBD | Wind |
| 10INR0060 | Willacy | 401 | TBD | Wind |  | 07INR0013 | Coke | 200 | TBD | Wind |
| 10INR0008 | Pecos | 500 | TBD | Wind |  | 10INR0077 | Callahan | 101 | TBD | Wind |
| 11INR0076 | Archer | 94 | TBD | Wind |  | 11INR0088 | Brazos | 45 | Mar-11 | Gas |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0085 | Nolan | 106 | Mar-11 | Wind |
| 11INR0075 | Fort Bend | 15 | Apr-11 | Coal |  | 11INR0071 | Harris | 7 | Apr-11 | Gas |
| 11INR0086 | Travis | 60 | Apr-11 | Solar |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 11INR0033a | Cameron | 200 | May-11 | Wind |  | 11INR0033b | Cameron | 200 | May-11 | Wind |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 10INR0089 | Harris | 40 | Jun-11 | Other |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 11INR0057 | Cameron | 165 | Jun-11 | Wind |  | 11INR0065 | Nueces | 240 | Jun-11 | Wind |
| 11INR0091 | Webb | 92 | Jun-11 | Wind |  | 08INR0020 | Eastland | 200 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 10INR0062a | Pecos | 80 | Oct-11 | Wind |  | 10INR0081b | Clay | 19 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 11INR0090 | Howard | 60 | Nov-11 | Solar |
| 11INR0094 | Kent | 100 | Nov-11 | Solar |  | 11INR0089 | Hays | 20 | Dec-11 | Solar |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 08INR0049 | Clay | 50 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 10INR0082 | Travis | 30 | Dec-11 | Solar |  | 09INR0048 | Jack | 100 | Dec-11 | Wind |
| 10INR0085 | Ector | 40 | Jan-12 | Solar |  | 12INR0021 | Edwards | 165 | Jan-12 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |  | 12INR0045 | Kleberg | 135 | Mar-12 | Wind |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 11INR0049 | Wharton | 275 | May-12 | Gas |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0053 | Crockett | 615 | Jun-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 12INR0035 | Nueces | 249 | Nov-12 | Wind |
| 08INR0044 | Concho | 200 | Nov-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 11INR0081 | Live Oak | 72 | Dec-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 09INR0058 | Howard | 250 | Mar-13 | Wind |
| 10INR0056 | Borden | 249 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 12INR0034 | Borden | 342 | Mar-13 | Wind |
| 12INR0018 | Gray | 500 | Apr-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0023 | Ector | 240 | Jul-13 | Gas |
| 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Brazos Electric Cooperative has submitted a project to move some load that is currently being served by the Entergy Texas system into the ERCOT system.  The project would involve disconnecting the subject load from the Entergy Texas system, constructing a new 345/ 138 kV substation in ERCOT, upgrading an existing 69 kV line in the ERCOT system and constructing two new 138 kV lines to serve the load from the ERCOT system.  The estimated cost of this project is $51.1 M.  This Tier 1 project is currently undergoing ERCOT Independent Review.

- CenterPoint Energy has submitted the South Lane City  to West Columbia 138 kV upgrade project. This is a Tier 3 project that is estimated to cost $ 23.6 million. The Regional Planning Group (RPG) has reviewed and accepted this Tier 3 transmission project.

- CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - January 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | Valley Import | 259 | 0 - 5000 | 11,349,558 |  |  |
| BASE CASE | West to North Stability Limit | 1840 | 0 - 2833 | 6,613,340 | CREZ |  |
| Lon Hill - North Edinburg 345kV | Rio Hondo 345kV Series Capacitor 1 | 15 | 460 - 4500 | 3,251,815 |  |  |
| Watermill - Desoto Switch & Cedar Hill 345kV | West Levee 345/138kV autotransformer | 11 | 4500 - 4500 | 2,813,100 | 5YTP [2009-R21] |  |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 61 | 0 - 3500 | 2,091,723 | 5YTP [2009-R11] |  |
| Lewisville Switch 345/138kV AT1, Parker Switch - Eagle Mountain - Roanoke 345kV, Lewisville Switch - Carrollton Northwest 345kV | Lewisville Jones Street - Lewisville Switch 138kV | 318 | 0 - 3500 | 2,027,937 |  | Outage on Lewisville - Roanoke Switch 345kV, Lewisville - Argyle 138kV |
| Braunig - Toyota & Valley 138kV, Fern Street - Ball Park 138kV, Streich - Braunig 138kV, Calavers -Streich 138kV | Five Points - Westside CPS 138kV | 975 | 0 - 3500 | 1,447,941 | Westside substation equipment upgrade [12TPIT0054] | Outage on Cagnon - Marbach 138kV, Marbach - Valley 138kV |
| Moss Switch - Holt Switch 138kV | Odessa North 138/69kV autotransformer | 79 | 0 - 2800 | 663,020 | 5YTP [2009-R4] |  |
| Gail - Keysb 138kV | Ackerly Vealmoor Switch - Ackerly 69kV | 134 | 0 - 2800 | 576,371 | Rebuild existing 69kV line [11TPIT0060] |  |
| Farmersville - Monticello 345kV | Monticello SES - Sulpher Springs Switch 345kV | 25 | 0 - 4500 | 460,973 |  |  |

# Wind Generation as a Percent of Load

One-hour average Settlement quality data shown.

# Planning Model Activities

- ERCOT and SSWG agreed to use ROS Option 2 to build the 2011 Data Set A and B cases transitioning to using ROS Option 1 starting with Data Set A in April 2012.

- ERCOT and the TSP are working to complete Cost Benefit Analysis for SCR760 based on the ROS approved comments from the January meeting and readied the CBA for presentation to TAC on March 3, 2011.

- ERCOT is working on several defects with Siemens regarding the Topology Processor and will receive a new release in early March 2011.

- ERCOT is working on creating a new MOD environment to use for the 2011 Case Building efforts.  This will allow ERCOT to continue testing on the first MOD environment with the Topology Processor output.

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan (5YTP) is wrapping up.  The studies & report have been completed for the 2010 5YTP.  The report is currently going through ERCOT internal review.

- Transient Stability Study for 2011 Winter off-peak conditions: As part of the annual reliability assessment of the network, a transient stability study study is being performed on an ERCOT 2011 Winter off-peak case.