## Sheet1
Reliability Deployment Task Force- TRACKING LIST
Item | Issue from PUCT Transcript | Consensus Item | Status/Concerns | Work Product | Next Steps
1 | Offers should be at system wide offer cap for responsive reserve service & up reg service used for capacity | Yes | ERCOT will draft NPRR for discussion; no system change; offer price methodology; adjustment check | NPRR through stakeholder process | Luminant will draft and provide NPRR at next reliability deployment task force
2 | Prices should be at system wide offer cap when ERCOT deploy load resources or EILS- reprice after deployment | Need more clarification on implementation. | ERCOT will draft NPRR for discussion. System Impact. Pricing run immediately after deployment; interim solution?? | NPRR through stakeholder process | ERCOT will draft NPRR and look at interim solution
3 | ERCOT should deploy non-spin in increments smaller than a thousand MW. | Yes | Part of ERCOT's current NSRS deployment and desk procedure | NA | Complete
4 | ERCOT deploys RUC units for capacity insufficiency at the offer cap; RUC for system capacity should be offered liked mothballed RMR | Anderson- wants ERCOT to formally comment on (protocol changes and system impact); Nelson agreed during the discussion with Evan Rowe | ERCOT will check the implementation details |  | ERCOT to bring back solutions at next reliability directive task force
5 | Online non-spin units and quick start units should always be offered in SCED and deployed by SCED | Yes | ERCOT preparing report and skelton NPRR being drafted; concerns about performance metrics; deployment of clustered offers; should this be an adder instead of offer floor; duct burners and ramp rate constraint in SCED; performance measurements and offers for PUNS (RRS and NSRS); reporting requirements | Skelton NPRR through stakeholder process | Reliant will draft skelton NPRR and provide NPRR at next RDTF