|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report August 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 190 active generation interconnection requests totaling over 60,000 MW. This includes over 35,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $767.9 Million - Transmission Projects endorsed in 2011 total $43.9 Million - All projects (in engineering, routing, licensing and construction) total approximately $10.0 Billion - Transmission Projects energized in 2011 total about $401.8 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Signed Generation Interconnection Agreements - none

## New Generation Registering for Commercial Operations

10INR0010 – Jack County 2 – 565 MW Gas – Jack County

09INR0029 – CFB Power Plant Units 11&12 – 260 Coal – Calhoun County

11INR0071 – Air Liquide Gulf Coast Gas H2 Plant – 7 MW – Harris County

The total installed wind capacity is now reported as 9,452 MW by the resource owners through the registration process. Capacity by North, South and West is 292 MW, 1216 MW, and 7943 MW respectively. 850 MW is able to switch between the West and South zones.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 190 active generation interconnection or change requests |  |  |  |  |
| As of August 31, 2011 | North | South | West | Total |
| Security Screening Study | 1 | 0 | 6 | 7 |
| SSS Completed | 1 | 8 | 17 | 26 |
| Full Interconnect Study | 19 | 20 | 91 | 130 |
| FIS Completed | 1 | 1 | 5 | 7 |
| Interconnect Agreement Completed | 7 | 8 | 5 | 20 |
| Capacity under Interconnection Agreements | 4,557 | 4,144 | 651 | 9,352 |
| Capacity for Grid, MW | 16,671 | 11,544 | 32,187 | 60,402 |
| Wind Capacity, MW | 3,184 | 3,170 | 28,841 | 35,195 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 0 | 708 |
| Gas-CombinedCycle |  |  | 4,732 | 10,999 |
| Total Gas | 508 | 6,467 | 4,732 | 11,707 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 865 | 2,785 | 3,650 |
| Wind | 3,284 | 27,626 | 4,285 | 35,195 |
| Solar | 620 | 834 | 90 | 1,544 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 1,016 | 1,240 | 2,256 |
| Grand Total | 4,412 | 36,858 | 19,132 | 60,402 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of August 31, 2011 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 08INR0065 | Buffalo Gap 4 and 5 | XX | Nolan | West | TBD |  | Wind |  | 465 | Cancelled |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Oct-11 |  | Wind |  | 150 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind |  | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind |  | 194 |  |
| 10INR0082 | FRV AE Solar | IA | Travis | North | Dec-11 |  | Solar |  | 30 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind |  | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal |  | 925 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind |  | 45 |  |
| 08INR0062 | Trinity Hills | IA | Young | West | Mar-12 |  | Wind |  | 250 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind |  | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind |  | 1,001 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 |  | Biomass |  | 100 |  |
| 10INR0060 | Magic Valley Wind Project | IA | Willacy | South | Jun-12 |  | Wind |  | 202 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind |  | 290 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 |  | Solar |  | 60 | date |
| 12INR0080 | Blanco Canyon Wind | PL | Taylor | West | Dec-12 |  | Wind |  | 300 |  |
| 10INR0077 | Kaiser Creek Windfarm | IA | Callahan | West | Dec-12 |  | Wind |  | 101 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Dec-12 |  | Wind |  | 150 | date |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind |  | 120 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-14 |  | Gas-CC |  | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC |  | 1,792 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal |  | 1,200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas-CC |  | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-15 |  | Gas-CC |  | 1,380 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other |  | 620 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear |  | 2,700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other |  | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-21 |  | Nuclear |  | 3,200 |  |
|  |  |  |  |  | TOTAL |  |  |  | 19,132 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0016 | Childress | 150 | TBD | Wind |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 10INR0013 | Upton | 400 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 09INR0074 | Motley | 70 | TBD | Wind |
| 11INR0029 | Throckmorton | 200 | TBD | Wind |  | 10INR0051 | Brazoria | 200 | TBD | Wind |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0019 | Deaf Smith | 609 | TBD | Wind |
| 10INR0008 | Pecos | 500 | TBD | Wind |  | 07INR0013 | Coke | 200 | TBD | Wind |
| 11INR0076 | Archer | 94 | TBD | Wind |  | 11INR0085 | Nolan | 106 | TBD | Wind |
| 11INR0075 | Fort Bend | 15 | TBD | Coal |  | 11INR0062 | Nueces | 149 | TBD | Wind |
| 11INR0061 | Presidio | 90 | TBD | Solar |  | 11INR0060 | Tom Green | 90 | TBD | Solar |
| 11INR0058 | Pecos | 135 | TBD | Solar |  | 11INR0037 | Smith | 50 | TBD | Biomass |
| 11INR0091 | Webb | 92 | TBD | Wind |  | 11INR0065 | Nueces | 240 | TBD | Wind |
| 11INR0057 | Cameron | 165 | TBD | Wind |  | 11INR0054 | San Patricio | 161 | TBD | Wind |
| 11INR0019 | Upton | 200 | TBD | Wind |  | 10INR0089 | Harris | 40 | TBD | Other |
| 10INR0023 | Haskell | 386 | TBD | Wind |  | 09INR0050 | Fannin | 1,200 | TBD | Gas |
| 11INR0006 | Lamar | 579 | TBD | Gas |  | 11INR0040 | freestone | 640 | TBD | Gas |
| 11INR0079a | Clay | 200 | TBD | Wind |  | 11INR0047 | Deaf Smith | 600 | TBD | Wind |
| 10INR0062a | Pecos | 80 | Oct-11 | Wind |  | 11INR0094 | Kent | 100 | Nov-11 | Solar |
| 11INR0090 | Howard | 60 | Nov-11 | Solar |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 12INR0081 | Upton | 113 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 10INR0085 | Ector | 40 | Jan-12 | Solar |
| 10INR0080 | Presidio | 81 | Jan-12 | Solar |  | 12INR0054 | Jones | 200 | Feb-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0075 | Wilbarger | 499 | Apr-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0050 | King | 332 | Jun-12 | Wind |
| 12INR0079 | Kenedy | 94 | Aug-12 | Wind |  | 12INR0076 | Winkler | 36 | Sep-12 | Other |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 12INR0035 | Nueces | 249 | Nov-12 | Wind |
| 08INR0044 | Concho | 200 | Nov-12 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0072 | Kinney | 100 | Dec-12 | Wind |  | 12INR0069 | Presidio | 50 | Dec-12 | Solar |
| 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |  | 12INR0067 | Webb | 94 | Dec-12 | Wind |
| 12INR0060 | Schleicher | 58 | Dec-12 | Wind |  | 12INR0059 | Pecos | 50 | Dec-12 | Solar |
| 12INR0057 | Ector | 50 | Dec-12 | Solar |  | 12INR0055 | Baylor | 80 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |  | 11INR0093 | San Patricio | 34 | Dec-12 | Wind |
| 11INR0081 | Live Oak | 72 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 09INR0048 | Jack | 113 | Dec-12 | Wind |
| 08INR0049 | Clay | 50 | Dec-12 | Wind |  | 13INR0040 | Harris | 0 | Jan-13 | Gas |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |
| 13INR0010a | Parmer | 200 | Jan-13 | Wind |  | 12INR0034 | Borden | 342 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0050 | Crosby | 149 | Mar-13 | Wind |  | 10INR0056 | Borden | 249 | Mar-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 12INR0070 | Knox | 300 | Apr-13 | Wind |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0023 | Ector | 240 | Jul-13 | Other |
| 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |  | 13INR0025 | Randall | 150 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 12INR0058 | San Patricio | 50 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 13INR0010b | Parmer | 500 | Jan-14 | Wind |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 10INR0015 | Mitchell | 350 | May-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 12INR0042 | Deaf Smith | 400 | Sep-14 | Wind |
| 14INR0006 | Floyd | 151 | Oct-14 | Wind |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 13INR0021 | Llano | 600 | Dec-14 | Gas |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 15INR0011b | Borden | 38 | Dec-15 | Solar |
| 15INR0011a | Borden | 112 | Dec-15 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

- American Electric Power Service Corporation has submitted the Laredo to the lower Rio Grande Valley 345 kV Project to improve reliability of the lower Rio Grande Valley transmission system. This project proposes a new 345kV transmission line to be constructed from Laredo to the lower Rio Grande Valley to provide a third 345kV source to the area with an in-service date of 2016. The estimated cost for this project is $525 Million. This Tier 1 project has completed the ERCOT Independent Review. The project will be presented to the ERCOT BOD (September 2011 BOD meeting) for approval.

- Sharyland Utilities (Sharyland) and Brownsville Public Utilities Board (BPUB) has submitted the Cross Valley Brownsville Loop project that proposes a new 345kV line from LaPalma to Loma Alta and a new 345kV line from Loma Alta to Frontera. The estimated cost for this project is $117.9 Million.  This Tier 1 project is undergoing ERCOT Independent Review. Sharyland and BPUB submitted an study addendum report to the Cross valley project with additional options which is is currently undergoing ERCOT Independent Review.

- TNMP has submitted the Wink-Cochise-Pecos 69 kV line rebuild project to solve the existing and forecasted West Texas North (WTN) voltage problems. The estimated cost for this project is $20.3 Million.  This Tier 3 project has completed the RPG review and the ERCOT project acceptance letter was send to TNMP.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - August 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| PH Robinson 345/138KV AT2 | PH Robinson 345/138KV AT1 | 85 | 0 - 4500 | 7,740,294 |  | High loads and generation pattern in Houston Metropolitan Area |
| Amoco North Cowden Tap - North Cowden Amoco 138kV | Odessa North 138/69kV Autotransformer | 708 | 0 - 2800 | 4,702,274 | 5YTP [2010-R7, R8] |  |
| Calmont Switch - Benbrook 138kV | Saginaw Switch - American MFG Tap 138kV | 99 | 0 - 3500 | 4,361,904 | Upgrade existing 138 kV line [11TPIT0033] |  |
| Collin 345/138kV auto | Allen Switch - Plano Custer Road 138kV | 46 | 25 - 3500 | 3,946,549 | Upgrade existing double-circuit 138 kV line [10TPIT0017] |  |
| Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 91 | 0 - 3500 | 2,814,296 | 5YTP [2010-R12] |  |
| Allen Switch - Royse Switch and Monticello SES 345kV | Apollo - Richardson East 138kV | 189 | 0 - 3500 | 2,649,907 | Upgrade the Apollo to East Richardson 138kV line [10TPIT0013] |  |
| Jewett - Singleton 345kV | Twin Oak Switch - Jack Creek 345kV | 55 | 0 - 4500 | 2,202,605 | Zenith to Fayetteville 345kV project [14TPIT0002] |  |
| Moss Switch - Odessa Ehv Switch 345kV | Odessa - Odessa North 138kV | 190 | 0 - 3500 | 1,863,074 | 5YTP [2010-R7, R8] |  |
| Olinger - Ben Davis - Elm Grove 138kV | Olinger - Firwheel 138kV | 256 | 0 - 3500 | 1,600,131 |  | Incorrect contingency definition |
| Greens Bayou - Gable and Hardy - Crocket 138kV | Garrott - Midtown 138kV | 334 | 0 - 3500 | 1,539,608 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] |  |

Binding Constraints - January to August 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 16600 | 0 - 3910 | 75,176,625 | CREZ |
| BASE CASE | Valley Import | 273 | 0 - 5000 | 41,457,339 |  |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0 - 4500 | 31,689,757 |  |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 474 | 0 - 3500 | 25,219,060 | 5YTP [2010-R12] |
| Lewisville Switch 345/138kV Auto, Lewisville Switch - Carrollton Northwest 345kV | Carrollton Northwest - Lakepointe 138kV | 444 | 0 - 3500 | 15,137,927 | Upgrade NW Carrollton - Lakepointe (TNMP) 138 kV line [14TPIT0014] |
| BASE CASE, Zorn - Marion and Clear Springs 345kV, Clear Springs 345/138kV Autotransformer | Marion 345/138kV Autotransformer | 391 | 0 - 4500 | 13,826,062 |  |
| Amoco North Cowden Tap - North Cowden Amoco 138kV | Odessa North 138/69kV Autotransformer | 1526 | 0 - 2800 | 12,290,366 | 5YTP [2010-R7, R8] |
| Greens Bayou - Gable and Hardy - Crocket 138kV, Singleton - Tomball and Singleton - Roanes Prairie 345kV, Meadow - Oasis 345kV, Thermal Energy Coop - Blodgett 138kV, W.A. Parish - Obrien 345kV | Garrott - Midtown 138kV | 4102 | 0 - 3500 | 11,698,047 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] |
| Abilene South - Bluff Creek 138kV, Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 8645 | 0 - 3500 | 10,787,958 | CREZ |
| Gails To Keysb 138kV, Willow Valley Switching Station - Sharon Ridge Exxon 138kV | Ackerly Lyntegar - Sparenburg 69kV | 3170 | 0 - 2800 | 10,092,284 | Lamesa - Ackerly Vealmoor 69 kV line rebuild [11TPIT0060] |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Work on Data Set A has been completed.  Data Set B work has begun and has started one week late.  The remaining schedule is as follows:

  - Aug 4, 2011	DSA cases finalized and posted (delayed from July 15)

  - Aug 26, 2011	DSA Final Comparison posted (delayed from Aug 1)

  - Aug 8, 2011	DSB Case Build started (delayed from Aug 1)

  - Sept 9, 2011	DSB Pass 2 changes due from TSP (on-time)

  - Oct 7, 2011	DSB cases finalized and posted (projected on-time)

  - Oct 28, 2011	DSB Final Comparison posted (projected on-time)

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): Release received and tested.  Defect fixes underway.  Also received updated TP Enhancement and PSSE/IMM Mapping.  Anticipate production date for October on-cycle (10/19 – 10/23) release.

  - Bundle 2 (Items 2, 4, 9):  SOW signed by both Vendor and ERCOT.  Expected code release in December 2011 with production date of March 2012.

  - Item 5:  Requirements completed by ERCOT and TSPs.  Sent to Siemens for estimate.

  - Bundle 3 (Items 1 and 6):  Asked Siemens to update document previously sent in December 2010 to determine differences between version 32 and version 30 of RAWD format.  Update will determine differences through version 33 of RAWD.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Submitted |
| SCR760-2 | Distribution Capacitor banks | Planning |
| SCR760-3 | Zero Impedance Line Ratings | Release |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Planning |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Release |
| SCR760-8 | Phase shift of Autos for short circuit studies | Release |
| SCR760-9 | Multisection Line Grouping | Planning |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- Transient Stability Study for 2011 - A transient stability study was performed on an ERCOT 2011 summer on-peak case and results indicate that it complies with the NERC reliability requirements related to transient tests.

- UFLS Assessment Study as required by NERC PRC-006 is in progress.

- DFW Dynamic Reactive Reserve Study is in progress.

- A LAARs Assessment study has started, looking into potential increase in LAARs percentage respect of 2300 MW and 2800 MW total responsive reserve.

- Work on the 2011 Five-Year Transmission Plan is underway.  The 5YTP start cases (condition the SSWG base cases) are completed for 2012, 2014 and 2016 and posted. The work is currently focused on the performing the reliability assessement for 2012, 2014 and 2016.