## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
October 20, 2011

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Update p. 3-7
    Upcoming Project Go-Lives
    Project Portfolio Gantt Chart
  2011 Project Spending Update p. 8
  ERCOT FTE Tracking p. 9
  Multi-Year PPL Update and 2012 Release Plan p. 10

## Slide 3: Project Portfolio – Upcoming Activities
Go-Lives Planned for October / (No November release)
  PR-10055 – Data Agg Performance Improvements
    Project to address data aggregation processing performance risk
  NPRR258 – Sync with PRR824 and PRR833 and Additional Clarifications
  SCR762 – Enable Single Step Cancel/Resubmit of Trades
  NPRR320 – Minimum PTP Option Bid and Settlement
  SCR766 – Load Zone and Hub LMPs Distributed by ICCP
  IT Security Infrastructure Upgrade
  SCR764 – Public Access to Select MIS Dashboards
    Oct. – 3rd phase – SCED Up/Down Dashboard
  SCR760 – Recommended Changes Needed for Information Model Mgr and Topology Processor
    Oct. – Deliverables 3, 7, and 8
  Stabilization/Deferred Defects
    Oct. – Release 9
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Project Portfolio Status – as of 10/17/2011

## Slide 5: Project Portfolio Status – as of 10/17/2011

## Slide 6: Project Portfolio Status – as of 10/17/2011

## Slide 7: Project Portfolio Status – as of 10/17/2011

## Slide 8: 2011 Project Spending Update – 10/17/2011
PPL | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 28,178,937 | $ 24,548,629 | $ 20,911,765
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 7,627,112 | $ 3,689,343
Totals | $ 41,900,000 | $ 36,363,937 | $ 32,175,741 | $ 24,601,108
* Data Center Hardware Budget reduced by the amount of purchasing accelerated from 2011 to 2010 (~$5.5M)
*

## Slide 9: ERCOT FTE Tracking
Summary of FTE Impact of Revision Requests - By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR320 | Operations | Congestion Revenue Rights | 0.10 | 0 |  | Manual workaround no longer needed after project implementation in October 2011
NPRR343 | Operations | Market Analysis | 1.00 | 0 |  | Manual workaround no longer needed after project implementation in December 2011
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 |  | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 6.80 | 2 |  | 
--- In-Flight at TAC --- |  |  |  |  |  | 
None |  |  |  |  |  | 
 | In-Flight at TAC |  | 0.00 | 0 |  | 
 | Total of All Items |  | 6.80 | 2 |  | 

## Slide 10: Project Portfolio – Multi-Year PPL and 2012 Release Plan
In August, the Board approved 2012 project funding in the amount of $15M
  The supporting PPL materials included project forecasts for 2012-2014
  The PPL format is being changed to accommodate a multi-year view
Also in progress is a forecast of project implementations in 2012
  6 releases (1 every other month)
    Occasional off-cycle releases when necessary
  Includes projects forecasted on the Board-approved PPL… plus…
  Revision Requests approved in the stakeholder process since August
    17 NPRRs and 1 SCR
  Projects in the 1st 2012 release will be initiating in November/December
The new PPL and release plan will be presented to PRS in November
  Resource availability analysis currently underway
An added benefit to the multi-year PPL is that the yearly project prioritization process should become a confirmation of what is planned for the upcoming year (rather than the current bottom up approach)