| Proposed MarkeTrak Phase 3 Activity and Meeting Schedule Release 1 for Phase III |  |  |
| --- | --- | --- |
| ACTIVITY | LOCATION | CALENDAR DATE |
| MarkeTrak Taskforce Meeting: Define, Review and Approve 1st draft of Use Cases | ERCOT – Room 168 | Nov 01, 2010 |
| RMS Approval and Endorsement of Project Prioritization Schedule | ERCOT – Room 206 | Jun 22, 2011 |
| Approval and Endorsement by TAC for the Project Prioritization Schedule | ERCOT | Jul 07, 2011 |
| Project Approval by Board | ERCOT | Jul 19, 2011 |
| MarkeTrak Taskforce Meeting: ALL Use Cases FINALIZED, Respond to MT Survey concerns and Finalized RMGRevisions – sent out August 29th, 2011 to “RevisionRequest@Ercot.com”. | ERCOT – Room 168 | Aug 23, 2011 |
| ERCOT Project update for Critical issues from Troy Anderson **No official Project number** | ERCOT – Room 168 | Aug 23, 2011 |
| MT Script Team review first draft of scripts | ERCOT – Room 168 | Aug 24, 2011 |
| ERCOT BUSINESS REQUIREMENTS for RELEASE 1 | ERCOT due date Sep 7 | Mon Sep 26, 2011 |
| CONCEPTUAL DESIGN REVIEW for RELEASE 1 | ERCOT due date Sep 16 | Mon Sep 26, 2011 |
| ERCOT presents Conceptual Design to Task Force | ERCOT – Room 168 | Tue Sep 27, 2011 |
| Task Force review and Comments period | ERCOT – Room 168 | Tue Sep 27, 2011 |
| ERCOT revisions to Conceptual Design | ERCOT – Room 168 | Fri Sept 27, 2011 |
| ERCOT presents Business Requirements to Task Force | ERCOT – Room 168 | Sep 27, 2011 |
| MarkeTrak Taskforce Meeting: Review proposed activity and meeting schedule and test plan document for Release bucket 1. | ERCOT – Room 168 | Tue Sept 27, 2011 |
| DETAILED DESIGN REVIEW (95% CONFIDENCE) for RELEASE 1 | ERCOT due date Sep 30 | Mon Oct 17, 2011 |
| ERCOT presents Detail Design (100% CONFIDENCE) to Task Force | ERCOT – Room 168 | Tue Oct 25, 2011 |
| TEST PLAN FOR RELEASE 1 | ERCOT due date Oct 12 | Tue Oct 25, 2011 |
| ERCOT presents Test Plan to Task Force | ERCOT – Room 168 | Tue Oct 25, 2011 |
| MarkeTrak Taskforce Meeting: Review proposed ERCOT testing execution plan, other agenda items and test plan document for Release bucket 1. | ERCOT – Room 168 | Tue Oct 25, 2011 |
| Script Sub Team review second draft of scripts | AEP - Austin | Wed Oct 26, 2011 |
| ERCOT – ITEST (Internal Testing Complete) |  | Tue Nov 1, 2011 |
| MarkeTrak Taskforce Meeting: Review test scripts from sub team, other agenda items and test plan document for Release bucket 1. | ERCOT – Room 168 | Thu Nov 17, 2011 |
| Script Sub Team review third draft of scripts | AEP - Austin | Fri Nov 18, 2011 |
| MarkeTrak Taskforce Meeting: Review test scripts from sub team, other agenda items and test plan document for Release bucket 1. | ERCOT – Room 168 | Thu Dec 8, 2011 |
| Script Sub Team review fourth draft of scripts | AEP - Austin | Wed Dec 7, 2011 |
| Deadline for feedback for MarkeTrak test scripts |  | Wed Dec 14, 2011 |
| Script Sub Team meeting review to present scripts to TXSET | CNP - Houston | Mon Jan 9, 2012 |
| MarkeTrak Task Force present Phase III scripts to TXSET for review and approval - DEADLINE for approval for Flight 1 2012 – 01.31.2012 | Austin | Wed Jan 11, 2012 |
| MarkeTrak Task Force Meeting – amendment scripts if any recommendations from TXSET - DEADLINE for approval for Flight 1 2012 – 01.31.2012 | WebEX | Tue Jan 24, 2012 |
| MarkeTrak Taskforce Meeting: Review test scripts - Deadline for feedback for MarkeTrak test scripts | Austin | Fri Jan 27, 2011 |