## TX SET V4.0 Requirements
Change Control Number | Requested Priority | Implemented in Version | Description | Trans Set(s) | Requestor | Company | Date Requested | Disposition by Texas Standard Electronic Transactions | Market Testing Required? (Y/N) | Assigned To | Comments | Script Name | Status | Approved
2007-706 | N | Version 4.0 | Remove the EM Communicaton Number Qualifier from the 814_24 | 814_24 | Catherine Meiners | ERCOT | 2007-04-25 | Approved 3/28/07 change control | N
2008-718 | N | Version 4.0 | Change to ERCOT logic to use receipt of an 814_04 on a Move In in order to determine if the Move Out should be cancelled. | 814_24 | Kathy Scott | Centerpoint | 2008-02-14 | Approved 5/22/08 change control | N
2008-720 | N | Version 4.0 | Add code A78 "Item or Service already Established (Requested action has already completed)" as a valid reject reason to the 814_29. | 814_29 | Kathryn Thurman | ERCOT | 2008-04-15 | Approved 5/22/08 change control | Y | Gene | Leave SCR49 as is; New script to have MVI submitted by SIM CR and ERCOT hard cancels; TDSP does not process 814_08 but sends 814_28 09; ERCOT rejects with 814_29 A78 due to order being cancelled | SCR65 | Complete | Y
2008-722 | N | Version 4.0 | IG currently requires Originating Tran ID and Estimated Restoration Date whenever purpose code = "79". It is actually only required when purpose code = 79 AND Suspension/Reactivation code = RC001. Causing false rejection of a 650_04 Reactivate after disconnect for denial of access when Originating Transaction ID and Estimated Restoration Date is not also included. | 650_04 | Kathy Scott | Centerpoint | 2008-04-17 | Approved 10/12/10 Change Control Call | N |  | Discussed with Dave Lowder 10/13/11 - Nueces is currently sending the 650_04 as such; Testing not needed
2010-734 | N | Version 4.0 | New REF Segment to the 814_20 with Switch Hold Add and Removal and new Reason for Change added to REF~TD segment to support Meter Tampering Rulemaking | 814_20 | Kathy Scott | Centerpoint | 2010-06-17 | Approved 10/12/10 Change Control Call | Y | Gene |  | SCR53 | Complete | Y
2010-736 | N | Version 4.0 | In order to reject a Move In or Switch which currently has a Switch Hold, a new reject code of SHF will be added to the appropriate transactions. | 814_04, 814_05 | Kathy Scott | Centerpoint | 2010-06-17 | Approved 10/12/10 Change Control Call | Y | Gene |  | SCR54 | Complete | Y
2010-738 | N | Version 4.0 | New Critical Care status designations are required when Critical Care = Y and additional Contact information is required for certain Critical Care status. | 814_04, 814_05, 814_14, 814_22 | Kathy Scott | Centerpoint | 2010-06-28 | Approved 10/12/10 Change Control Call | Y | Jim | New Change Control to be written | STK31
2010-739 | N | Version 4.0 | Changes are required to the 814_PC in order for the TDSPs to receive customer contact information for power outages and service restoration. | 814_PC | Kathy Scott | Centerpoint | 2010-06-28 | Approved 10/12/10 Change Control Call | Y | Gene |  | SCR51 | Complete | Y
2010-740 | N | Version 4.0 | If the 814_27 is received with REF~1P~HUU (Status Reason) HISTORICAL USAGE UNAVAILABLE, ERCOT should close the Business Process Instance (BPI) and the 867_02 transaction should not be expected by the CR or ERCOT | 814_04, 814_05, 814_27 | Kathy Scott | Centerpoint | 2010-04-06 | Approved 10/12/10 Change Control Call | N
2010-741 | N | Version 4.0 | Adding a priority code to the 814_24 to allow for same day requests to be processed at a different level from standard Move Outs. | 814_24, 814_03 | Jennifer Frederick | Direct Energy | 2010-08-12 | Approved 10/12/10 Change Control Call | N
2010-742 | N | Version 4.0 | Addition of new reject code ACR - Acquisition Cancel Reject to be used when a CR submits an 814_08 on a Acquisition | 814_09 | Kathryn Thurman | ERCOT | 2010-08-13 | Approved 10/12/10 Change Control Call | N
2010-743 | N | Version 4.0 | Addition of new reject code CW1 for use when a CR submits an 814_08 or 814_12 within 1 day of Scheduled Meter Read | 814_09, 814_13 | Kathryn Thurman | ERCOT | 2010-08-13 | Approved 10/12/10 Change Control Call | N
2010-745 | N | Version 4.0 | Add the ability for a TDSP to Complete Unexecutable a Switch | 814_28, 814_29 | Kathy Scott | Centerpoint | 2010-08-23 | Approved 10/12/10 Change Control Call | Y | Gene |  | SCR56 | Complete | Y
2010-746 | N | Version 4.0 | TX SET Guide changes by transaction required to support Acquisition Transfer | 814_03, 814_04, 814_08, 814_09, 814_11, 814_14 | Kathryn Thurman | ERCOT | 2010-09-15 | Approved 10/12/10 Change Control Call | Y | Gene |  | ACQ01 | Complete | Y
2010-747 | N | Version 4.0 | In order to provide REPs information on whether an ESI ID has a provisioned Advanced Meter installed at the premise, a new REF segment will be added to the 814_04, 814_05, 814_14, 814_22 and 814_20. | 814_04, 814_05, 814_14, 814_22 and 814_20 | Jennifer Frederick | Direct Energy | 2010-09-21 | Approved 10/12/10 Change Control Call | Y | Monica | Add to 814_04 in existing script | SCR56 | Complete | Y
2010-748 | N | Version 4.0 | The purpose of this Change Control is to sync the names of the Texas SET Guide transactions, with the names of the transactions in Protocol and the Retail Market Guide. | 824, 650_02, 650_04, 650_05, 810_02, 810_03, 814_01, 814_02, 814_03, 814_04, 814_05, 814_06, 814_08, 814_09, 814_18, 814_19, 814_20, 814_21, 814_22, 814_26, 814_27, 814_29, 820_02, 820_03, 867_03, 867_04, T0, T1, T2, T3, T4 | Kathryn Thurman | ERCOT | 2010-09-22 | Approved 10/12/10 Change Control Call | N
2010-749 | N | Version 4.0 | Explanation of the 2 options for the REF~IK segment in the 810_03 transaction. | 810_03 | Chris Duncan | Nueces | 2010-09-22 | Approved 10/12/10 Change Control Call | Y | Gene | Add to MOU33 | MOU33 | Complete | Y
2010-751 | N | Version 4.0 | Adding new codes Force Majeure Event (FME) and Weather Moratorium (WTM) | 650_02, 814_04, 814_05, 814_11, 814_13, 814_25, and 814_28 | Kathy Scott | Centerpoint | 2010-08-31 | Approved 10/12/10 Change Control Call | Y | Gene |  | SCR58 | Complete | Y
2010-752 | N | Version 4.0 | Remove incorrect link for locating ISO country codes from TX SET implementation Guides. | 814_01, 814_10, 814_14, 814_16, 814_24 and 814_PC | Kathryn Thurman | ERCOT | 2010-09-30 | Approved 10/12/10 Change Control Call | N
2010-753 | N | Version 4.0 | Create a new code in both the 650_01 and 650_02 transactions that will allow a CR to notify a TDSP when a customer has installed some type of generation equipment at the premise | 650_01, 650_02 | Kathy Scott | Centerpoint | 2010-10-01 | Approved 10/12/10 Change Control Call | Y | Monica | Removed script at 09/14/11 Texas SET/MCT meeting | SCR59 | Complete | Y
2010-754 | Y | Version 4.0 | Add a new code to allow a CR to notify a TDSP when a customer has an Electric Vehicle as an end-use device at a premise. | 650_01, 650_02 | Ed Echols | Oncor | 2010-10-13 | Approved 10/21/10 Change Control Call | N
2010-755 | Y | Version 4.0 | In order for the TDSP to send discretionary charges due to tampering a new type code should be added to the 810_02. | 810_02 | Jonathan Landry | Gexa Energy | 2010-10-14 | Approved 10/21/10 Change Control Call | Y | Gene | Possibly add to SCR33 for Flight 0312 going forward; option to waive payment and verify CRs can accurately reflect the revamped invoice on the 820 | SCR33 | Complete | Y
2010-756 | Y | Version 4.0 | Cleanup after 3.0A to have off-cycle updated to reflect self selected | 814_03, 814_04, 814_05 & 814_11 | Kathryn Thurman | ERCOT | 2010-10-15 | Approved 10/21/10 Change Control Call | N
2010-757 | Y | Version 4.0 | Missed 814_20 transaction left out on CC 738 - New Critical Care status designations are required when Critical Care = Y and additional Contact information is required for certain Critical Care status. | 814_20 | Diana Rehfeldt | Texas-New Mexico Power | 2010-10-18 | Approved 10/21/10 Change Control Call | Y | Jim | Should be able to incorporate into STK31 | STK31
2010-759 | Y | Version 4.0 | Add a new REF segment to the 814_16 to provide key information to the TDSP about a condition that may affect the execution of a MVI, MVO or MVO to CSA. | 814_16, 814_03 and 814_24 | Johnny Robertson | TXU Energy | 2010-10-19 | Approved 10/28/10 Change Control Call | Y | Gene |  | SCR61 | Complete | Y
2010-760 | Y | Version 4.0 | Add a new code in the ESIID attributes to specify LED bulb types for Unmetered Service type. | 814_04, 814_05, 814_14, 814_20 814_22 and 867_03 | Ed Echols | Oncor | 2010-10-21 | Approved 10/28/10 Change Control Call | N
2010-761 | Y | Version 4.0 | Add to the existing REF02 of the REF~PRT segment the "WF" code to represent Wi-Fi (Wireless Fidelity). | 814_04, 814_05, 814_14, 814_20 814_22 and 867_03 | Kathy Scott | Centerpoint | 2010-10-25 | Approved 10/28/10 Change Control Call | N
2010-762 | Y | Version 4.0 | Discontinue use of the 650_05 response transaction that doesn’t provide or require a response by the TDSP once received. | 650_05 | Kathy Scott | Centerpoint | 2010-10-26 | Approved 10/28/10 Change Control Call | N
2010-764 | Y | Version 4.0 | Add an expiration date to the Special Needs designation to allow CRs to audit these designations and ask TDSPs for clarification of whether a status has been removed if the expiration date has passed without receiving an update. | 814_04, 814_05, 814_14, 814_20, & 814_22 | Jennifer Fredrick | Direct Energy | 2010-10-27 | Approved 10/28/10 Change Control Call | Y | Monica |  | STK34
2010-765 | Y | Version 4.0 | The final rule language for Critical Care adopted the concept that TDSPs are required to provide notice to REPs when a Customer's ESIID is placed on Temporary Status for either Critical Care Residential or Chronic Care Residential. Adding 2 additional codes for the temporary Critical Care status | 814_04, 814_05, 814_14, 814_20 and 814_22 | Ed Echols | Oncor | 2010-11-01 | Approved 11/08/10 Change Control Call | N
2010-766 | Y | Version 4.0 | In order to provide codes that are more specific than "Other" with a text explanation, TX SET shall add a new code T023 to the REF~G7 for Move Out treated as a force off due to Move In scheduled for same date. | 814_28 | Kathy Scott | Centerpoint | 2010-10-28 | Approved 11/08/10 Change Control Call | Y | Mike |  | STK31 | Complete | Y
2010-767 | Y | Version 4.0 | In order to accommodate the reason for change when updating the expiration date for special needs customers add the REF02 code of the DTM036 to the REF~TD of the LIN loop. | 814_20 | Diana Rehfeldt | Texas-New Mexico Power | 2010-11-01 | Approved 11/08/10 Change Control Call | Y | Jim |  | SCR63
2010-770 | N | Version 4.0 | Add new code T024 to the REF~G7 to the 814_28 for “Switch or Move-In cannot be completed due to Switch Hold recently applied to this ESI ID” | 814_28 | Kathy Scott | Centerpoint | 2010-11-19 | Approved at RMS 12/8/10 | N
2011-771 | N | Future | Clarification of the gray box language further for the REF~1P~HIU code that was modified and approved in Change Control 2010-740. | 814_04, 814_05, and 814_27 | Diana Rehfeldt | Texas-New Mexico Power | 2011-01-24 | Recommended for Approval 02/10/11 | N
2011-772 | N | Future | Modifications to Change Control 2010-753 to remove Electric Vehicles (which was Approved in 2010-754) from the Purpose Code and only applying the new FI012 Purpose Code to Generation devices at the premises. | 650_01 and 650_02 | Kathy Scott | Centerpoint | 2011-01-24 | Recommended for Approval 02/10/11 | N
2011-773 | N | Future | Clarifications to bring the TX SET Implementation Guides compliant and resolve disparities between Change Control 2010-738 and PUCT Critical Care Form. | 814_04, 814_05, 814_14, and 814_22 | Kathy Scott | Centerpoint | 2011-01-24 | Recommended for Approval 02/10/11 | N
2011-774 | N | Future | Changes were made to the Critical Care form by the PUCT and subsequently changes are required to Change Control 2010-757 to update the telephone numbers to be non-specific. | 814_20 | Diana Rehfeldt | Texas-New Mexico Power | 2011-01-24 | Recommended for Approval 02/10/11 | N
2011-775 | N | Future | Add grey box to the DC005 purpose code of the 650_01: This code authorizes the TDSP to disconnect service at any location accessible to them, which includes premium disconnect location. | 650_01 | Jennifer Frederick | Direct Energy | 2011-02-09 |  | N
2011-776 | N |  | This Change Control updates the existing 2010-734 Change Control for Switch Hold. This new Change Control breaks out Switch Hold into Switch Hold for Tampering and Switch Hold for Payment Plan. | 814_20 |  |  |  | Recommended for Approval 3/10/11 Approved as Non Emergency at RMS 03/23/2011 | Y | Gene |  | SCR53 | Complete | Y
2011-777 | N |  | Adding new codes in the REF~8X to Add Payment Plan Switch Hold and two removal codes – (1) for Switch Hold Removal due to Tampering and (1) Switch Hold Removal for Payment Plan Switch Hold at the request of the REP of Record. | 650_01 and 650_02 |  |  |  | Recommended for Approval 3/10/11 Approved as Non Emergency at RMS 03/23/2011 | Y | Gene |  | SCR53 | Complete | Y
2011-778 | N |  | This Change Control adds a new code "R" to the existing Change Control 2010-747 for the 814_20 transaction only. Adding the “R” code in the 814_20 will remove the AMSM/AMSR code in the event a meter is replaced with non-AMS meter. | 814_20 |  |  |  | Recommended for Approval 3/21/11 Approved as Non Emergency at RMS 03/23/2011 | Y | Gene |  | SCR64 | Complete | Y
2011-779 | N |  | This Change Control appends to 2010-748 to sync up the transaction names due to being inadvertently left out. | 814_23 and 814_28 |  |  |  | Recommended for Approval 4/14/11 Apparoved as Non Emergency at RMS 04/20/2011 | N
2011-780 | N |  | Gray box language added to a new REF segment (REF~SH) notfiying a POLR that a Tampering Switch Hold existed prior to the Mass transition. This Change Control replaces 2010-735 and Change Control 2010-768. | 814_04 and 814_14 |  |  |  | Recommended for Approval 4/14/11 Approved as Non Emergency at RMS 04/20/2011 | Y | Gene |  | STK30 | Complete | Y
2011-781 | N |  | The Critical Care Change Controls have been consolidated into this new Change Control. This Change Control replaces 2010-738, 2010-757, 2010-764, 2010-765, 2010-767, 2011-773, and 2011-774. | 814_04, 814_05, 814_14, 814_20 and 814_22 |  |  |  | TX SET Recommended for Approval 05/13/2011 RMS Approved as Non Emergency on 05/18/2011 | Y | Gene | Change 814_20 to come after the SW is Scheduled. 814_20 will have effective date later than RMRD. | STK33 | Complete | Y
2011-782 | N |  | Add the “DUP” reject code to be a valid rejection reason in the 650_02 transaction to indicate a duplicate 650_01 was received by the TDSP. Also clarifying DC005 “Disconnect due to tampering” is really a “Disconnect for non-payment of charges associated to Tampering”. | 650_01 and 650_02 |  |  |  | TX SET Recommended for Approval 05/13/2011 RMS Approved as Non Emergency on 05/18/2011 | N
2011-783 | N |  | This Change Control appends to 2010-760 and 2010-761 to add codes for Light Emitting Diode and Wi-Fi to the 867_02 due to being inadvertently left out. | 867_02 |  |  |  | TX SET Recommended for Approval 05/13/2011 RMS Approved as Non Emergency on 05/18/2011 | N
2011-784 | N |  | Adding new Cancel Code of CMO “Cancel Move Out” to the 814_08 transaction. | 814_08 |  |  |  | TX SET Recommended for Approval 05/13/2011 RMS Approved as Non Emergency on 05/18/2011 | N
2011-785 | N |  | Add the new reject code of "TCC" to notify all REPs that the TDSP has completed a competing transcaction for the same scheduled date. | 814_04, 814_05, 814_11, 814_13, 814_25, 650_02, and 814_28 |  |  |  | Submitted 05/13/11 | N