|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report October 2011 |
|  | Report Highlights |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $159.2 Million Transmission Projects endorsed in 2011 total $579.9 Million All projects (in engineering, routing, licensing and construction) total approximately $9.8 Billion Transmission Projects energized in 2011 total about $694.8 million A comprehensive review of the status of each generation interconnection study is currently underway. The results will be included in next month’s report. |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	2

1.5	Generation Projects Undergoing Full Interconnection Studies	3

1.6	Wind Generation	3

2.	Regional Planning Group Project Reviews	4

3.	Congestion Costs	5

4.	Wind Generation as a Percent of Load	8

5.	Planning Model Activities	9

6.	Other Notable Activities	9

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Signed Generation Interconnection Agreements

08INR0049 – Windthorst 1  – 50 MW Wind – Clay County

12INR0072 – Anacacho  – 100 MW Wind – Kinney County

## New Generation Registering for Commercial Operations

06INR0012b – Sherbino Mesa 2  – 158 MW Wind – Pecos County

The total installed wind capacity is now reported as 9,592 MW by the resource owners through the registration process. Capacity by North, South and West is 232 MW, 1216 MW, and 8144 MW respectively. 850 MW is able to switch between the West and South zones.

## Summary of Active Generation Interconnection Requests

Due to the increased focus on potential future resources in light of high demands last summer and potential unavailability of existing resources due to environmental compliance and the ongoing drought, ERCOT is undertaking a comprehensive review of the status of each generation interconnection request in the interconnection queue with both the transmission service provider assigned to perform the interconnection study and the requesting generation developer.  This review has not yet been completed.  To avoid presentation of data that has been only partially validated, the tables and charts related to generation interconnection request status are not included this month.  The validated data will be included in the report released in December.

## Projects with Interconnection Agreements

## (Status: IA=Interconnect Agreement,  PL= Public Letter, XX= cancelled)

| Generation Interconnections as of October 31, 2011 |
| --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 10INR0082 | FRV AE Solar | IA | Travis | North | Dec-11 | Solar | 30 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 | Wind | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 | Coal | 925 |  |
| 08INR0062 | Trinity Hills | IA | Young | West | Mar-12 | Wind | 250 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 | Wind | 45 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | May-12 | Wind | 150 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 | Biomass | 100 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 | Wind | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 | Wind | 1001 |  |
| 10INR0060 | Magic Valley Wind Project | IA | Willacy | South | Jun-12 | Wind | 202 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 | Wind | 290 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 | Solar | 60 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 | Wind | 100 | New |
| 10INR0077 | Kaiser Creek Windfarm | IA | Callahan | West | Dec-12 | Wind | 101 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 | Wind | 30 |  |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 | Wind | 400 |  |
| 08INR0049 | Windthorst I | IA | Clay | North | Dec-12 | Wind | 50 | New |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 | Wind | 202 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-14 | Gas-CC | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 | Gas-CC | 1792 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1200 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 | Wind | 120 | Date |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 | Gas-CC | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-15 | Gas-CC | 1380 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 | Other | 620 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 | Nuclear | 2700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 | Other | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 | Coal | 660 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-21 | Nuclear | 3200 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | TBD | Wind | 200 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | TBD | Wind | 194 |  |

## Generation Projects Undergoing Full Interconnection Studies

Due to the increased focus on potential future resources in light of high demands last summer and potential unavailability of existing resources due to environmental compliance and the ongoing drought, ERCOT is undertaking a comprehensive review of the status of each generation interconnection request in the interconnection queue with both the transmission service provider assigned to perform the interconnection study and the requesting generation developer.  This review has not yet been completed.  To avoid presentation of data that has been only partially validated, the tables and charts related to generation interconnection request status are not included this month.  The validated data will be included in the report released in December.

## Wind Generation

Wind Capacity Installed by Year

# Regional Planning Group Project Reviews

- Sharyland Utilities (Sharyland) and Brownsville Public Utilities Board (BPUB) has submitted the Cross Valley Brownsville Loop project that proposes a new 345kV line from LaPalma to Loma Alta and a new 345kV line from Loma Alta to Frontera. The estimated cost for this project is $117.9 Million.  This Tier 1 project is undergoing ERCOT Independent Review. Sharyland and BPUB submitted an study addendum report to the Cross valley project with additional options which is is currently undergoing ERCOT Independent Review.

- South Texas Electric Cooperative (STEC) has submitted the El Campo to Vanderbilt rebuild project to rebuild the existing 69 kV transmission between El Campo and Vanderbilt with a double circuit 138/69 kV line. The proposed project is to accommodate 118 MW of new load in Jackson County. This is a Tier 2 project that is estimated to cost $ 26.8 million. This Tier 2 project is undergoing ERCOT Independent Review.

- LCRA and STEC has submitted the STEC Ricebird and LCRA TSC Nada 138/69 kV auto project. This is a Tier 3 project that is estimated to cost approximately $ 15 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - October 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 1853 | 0-3581 | 9,791,780 | CREZ |  |
| Elmcreek - Hill Country and Skyline 345 kV, San Miguel - Elmcreek - Marion 345 kV | Marion - Skyline 345 kV | 95 | 1-4500 | 9,616,126 | Skyline to Marion - 345 kV Substation Equipment Upgrade (12TPIT0124) | Outage on Hill Country breakers |
| Greens Bayou - Gable and Hardy - Crocket 138kV, Singleton - Tomball and Singleton - Roanes Prairie 345kV | Garrott - Midtown 138kV | 713 | 0-3500 | 5,667,416 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] | Outage on Greens Bayou 345/138 kV AT2 |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69kV Autotransformer | 502 | 0-2800 | 4,283,866 | 5YTP [2010-R7, R8] |  |
| Austrop - Garfield and Zorn 345 kV, Garfield - Onion Creek and Hicross 138 kV, | Austrop 345/138 kV Autotransformer AT2 | 491 | 0-4500 | 3,500,960 |  | Outage on Austrop 345/138 Autotransformer AT1 |
| STP - Elmcreek 345 kV, Pawnee - Calavers 345 kV, STP - Hillje and Elmcreek 345 kV, Formosa unit G12, Marion -Zorn and Clear Springs 345 kV | Blessing - Lolita 138 kV | 350 | 0-3500 | 2,227,474 |  | Outage on STP - White Point 345 kV and STP - Elm Creek 345 kV |
| Roans prairie - Kuykendahl - King & Singleton - Tomball 345kV | Singleton - Zenith 345kV | 272 | 0-4500 | 1,892,669 | Zenith to Fayetteville 345kV project [14TPIT0002] | Outage on Singleton - Zenith 345 kV |
| Greens Bayou - King 345 kV | Greens Bayou 138/69 kV Autotransformer | 10 | 0-3500 | 1,175,953 | Greens Bayou Autotransformer Upgrade (13TPIT0102) | Outage on Greens Bayou 345/138 kV AT2 |
| Graham SES - Long Creek 345 kV | Putnam 138/69 kV Autotransformer | 119 | 180-1972 | 1,115,313 | CREZ |  |
| Marion - Zorn and Clear Springs 345 kV | Seguin - Seguin West 138 kV | 31 | 0-3500 | 1,060,830 |  | Outage on Hill Country breakers |

Binding Constraints - January to October 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 18912 | 0-3910 | 86,785,737 | CREZ |
| BASE CASE | Valley Import | 273 | 0-5000 | 41,457,339 | Laredo to LRGV Project |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0-4500 | 31,689,757 | Laredo to LRGV Project |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 474 | 0-3500 | 25,219,060 | 5YTP [2010-R12] |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69kV Autotransformer | 2403 | 0-2800 | 19,532,853 | 5YTP [2010-R7, R8] |
| Greens Bayou - Gable and Hardy - Crocket 138kV, Singleton - Tomball and Singleton - Roanes Prairie 345kV, Meadow - Oasis 345kV, Thermal Energy Coop - Blodgett 138kV, W.A. Parish - Obrien 345kV | Garrott - Midtown 138kV | 5104 | 0-3500 | 18,923,133 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] |
| Lewisville Switch 345/138kV Auto, Lewisville Switch - Carrollton Northwest 345kV | Carrollton Northwest - Lakepointe 138kV | 444 | 0-3500 | 15,137,927 | Upgrade NW Carrollton - Lakepointe (TNMP) 138 kV line [14TPIT0014] |
| BASE CASE, Zorn - Marion and Clear Springs 345kV, Clear Springs 345/138kV Autotransformer | Marion 345/138kV Autotransformer | 391 | 0-4500 | 13,826,062 |  |
| Roans prairie - Kuykendahl - King & Singleton - Tomball 345kV | Singleton - Zenith 345kV | 946 | 0-4500 | 13,261,025 | Zenith to Fayetteville 345kV project [14TPIT0002] |
| Abilene South - Bluff Creek 138kV, Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 8881 | 0-3500 | 11,113,649 | CREZ |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Work on Data Set B has been completed.  An update of the Contingency List and calculation of the Transmission Loss Factors are underway. The remaining schedule is as follows:

  - Oct 28, 2011	2012 Transmission Loss Factor Calculation Updates due to ERCOT

  - Nov 4, 2011	ERCOT sends out Pass1 2012 Transmission Loss Factor Calculations

  - Nov 11, 2011	Pass 1 2012 Transmission Loss Factor Updates due to ERCOT

  - Nov 18, 2011	ERCOT sends out Pass2 2012 Transmission Loss Factor Calculations

  - Nov 18, 2011	Pass 0 Contingency Updates due to ERCOT

  - Nov 18, 2011	ERCOT sends out request to update Data Dictionary

  - Nov 21, 2011	DSB Consistency Validation spreadsheet posted

  - Nov 28, 2011	Pass 2 Updates and Transmission Loss Factor Approval due to ERCOT

  - Nov 29, 2011	ERCOT sends out Pass 1 Contingency Updates

  - Dec 9, 2011	Data Dictionary Pass 0 Updates due to ERCOT

  - Dec 14, 2011	ERCOT Finalizes Contingency database

  - Dec 22, 2011	ERCOT sends out Pass 1 Data Dictionary Updates

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2, 4, 9):  SOW signed by both Vendor and ERCOT.  Expected code release in late November 2011 with production date of February 2012 on-cycle release.  A Project Change Request is underway for Item 2 to allow additional functionality requested by TSPs.  RAW file output for Item 9, Multi-section Line Grouping, created by vendor, was reviewed by ERCOT with positive results.  Vendor starting work on part of Item 4, Associate Loads with correct CNG.  Note:  The other part of Item 4, Associate Capacitor banks with correct CNG, is now part of the change request for Item 2, Distribution Capacitor banks.  Work estimates for change request due week of November 7th.

  - Item 5:  Requirements completed by ERCOT and TSPs.  Sent to Vendor for estimate.

  - Bundle 3 (Items 1 and 6):  ERCOT and TSPs are updating document to identify new fields or records added between version 33 and version 30 of the PSS/E RAWD format.  Began creating the envaluation process for Item 1 that would be added to SSWG Procedure Manual.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Planning |
| SCR760-2 | Distribution Capacitor banks | Planning |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Planning |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Planning |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- UFLS Assessment Study as required by NERC PRC-006 is in progress.

- DFW Dynamic Reactive Reserve Study is in progress.

- Dynamic data set preparation for year 2015 network conditions – As part of year 2011 DWG activities, ERCOT is preparing a future year 2015 no-disturbance data set for dynamic studies.

- Work on the 2011 Five-Year Transmission Plan is underway.  The 5YTP start cases (condition the SSWG base cases) are completed for 2012, 2014 and 2016 and posted. The results and base cases for the reliability assessement with initial set of projects (for 2012, 2014 and 2016) was posted on September 23, 2011.

- A Resource Integration, Registration and Modeling Workshop was held on September 27, 2011 at ERCOT Met Center location.  The workshop was intended for Resource Entities, Transmission Service Providers, and ERCOT to discuss resource data received through the Resource Asset Registration Form (RARF).  ERCOT presented an introduction to the modeling process, the RARF Process, and possible new Fields and Tabs that will be added to the RARF.  Transmission Service Providers from the SSWG, DWG, SPWG, and NDSWG presented information relative to their specific use of RARF data in their respective study cases and the importance of accurate information.  It is anticipated that much of the information provided will be added to the Resource Registration Guide to help RE’s provide the data needed for the various ERCOT models.