## MTIGRV1-1 (Redirect Fees)
|  | Script ID | MTIGRV1 |  | Power Point
|  | Script Name | Redirect Fees (IG)
|  | Script Storyline | Losing CR discovers lights-out situation, must submit priority Move-In to restore service at location, submits MarkeTrak issue under "Redirect Fees" subtype, provides BGN of priority Move-In, Gaining CR agrees, TDSP confirms reversal of fees.
|  | Success Criteria | Losing CR creates issue, Gaining CR agrees, TDSP confirms reversal of fees. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Losing CR | ERCOT | New (ERCOT) | Submit | Losing CR populates all required fields and selects "Submit" transition. MarkeTrak system updates state to - New (ERCOT)
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Gaining CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and the Issue is in a state of "New (Gaining CR)
|  |  | 1 | Gaining CR | Gaining CR | New (Gaining CR) | Begin Working | Gaining CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Gaining CR)
|  |  | 1 | Gaining CR | TDSP | In Progress (Gaining CR) | Agree | CR selects "Agree"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | "In Progress (TDSP)" | Redirect Fees | TDSP selects "Redirect Fees"
|  |  | 1 | Losing CR | Losing CR | Regaining Transaction Submitted (PC) | Complete | Losing CR selects "Complete". Issue is closed.

## MTIGRV1-2 (Redirect Fees)
|  | Script ID | MTIGRV2 |  | Power Point
|  | Script Name | Redirect Fees (IG)
|  | Script Storyline | Losing CR submits MarkeTrak issue under "Redirect Fees" subtype, Gaining CR chooses “Send to Losing CR” requesting information, Gaining CR agrees, TDSP confirms redirection of fees.
|  | Success Criteria | Losing CR creates issue, Gaining CR agrees, TDSP confirms reversal of fees. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Losing CR | ERCOT | New (ERCOT) | Submit | Losing CR populates all required fields and selects "Submit" transition. MarkeTrak system updates state to - New (ERCOT)
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Gaining CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and the Issue is in a state of "New (Gaining CR)
|  |  | 1 | Gaining CR | Gaining CR | New (Gaining CR) | Begin Working | Gaining CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Gaining CR)
|  |  |  | Gaining CR | Losing CR | In Progress (Gaining CR) | Send to Losing CR | Gaining CR selects "Send to Losing CR"
|  |  |  | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working". MarkeTrak updates state to "In Progress (Losing CR)"
|  |  |  | Losing CR | Gaining CR | In Progress (Losing CR) | Send to Gaining CR | Losing CR selects "Send to Gaining CR". Issue is in a state of "New (Gaining CR)" with Gaining CR Responsible MP.
|  |  | 1 | Gaining CR | Gaining CR | New (Gaining CR) | Begin Working | Gaining CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Gaining CR)
|  |  | 1 | Gaining CR | TDSP | In Progress (Gaining CR) | Agree | CR selects "Agree"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | "In Progress (TDSP)" | Redirect Fees | TDSP selects "Redirect Fees"
|  |  | 1 | Losing CR | Losing CR | Regaining Transaction Submitted (PC) | Complete | Losing CR selects "Complete". Issue is closed.

## MTIGRV1-3 (Redirect Fees)
|  | Script ID | MTIGRV3 |  | Power Point
|  | Script Name | Redirect Fees (IG)
|  | Script Storyline | Losing CR submits MarkeTrak issue under "Redirect Fees" subtype, Gaining CR chooses “Unexecutable”, issue is closed
|  | Success Criteria | Losing CR creates issue, Gaining CR chooses "Unexecutable", issue is closed by Losing CR
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Losing CR | ERCOT | New (ERCOT) | Submit | Losing CR populates all required fields and selects "Submit" transition. MarkeTrak system updates state to - New (ERCOT)
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Gaining CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and the Issue is in a state of "New (Gaining CR)
|  |  | 1 | Gaining CR | Gaining CR | New (Gaining CR) | Begin Working | Gaining CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Gaining CR)
|  |  | 1 | Gaining CR | Losing CR | In Progress (Gaining CR) | Unexecutable | CR selects "Unexecutable"
|  |  | 1 | Losing CR | Losing CR | Unexecutable (PC) | Accept | Losing CR selects "Accept". Issue is closed.

## MTIGRV1-4 (Redirect Fees)
|  | Script ID | MTIGRV1 |  | Power Point
|  | Script Name | Redirect Fees (IG)
|  | Script Storyline | Losing CR submits MarkeTrak issue under "Redirect Fees" subtype, Gaining CR agrees, TDSP chooses “Return to Losing CR” because TDSP cannot accommodate request, Losing CR closes issue
|  | Success Criteria | Losing CR creates issue, Gaining CR agrees, TDSP chooses "Return to Losing CR", Losing CR accepts. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Losing CR | ERCOT | New (ERCOT) | Submit | Losing CR populates all required fields and selects "Submit" transition. MarkeTrak system updates state to - New (ERCOT)
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Gaining CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and the Issue is in a state of "New (Gaining CR)
|  |  | 1 | Gaining CR | Gaining CR | New (Gaining CR) | Begin Working | Gaining CR selects "Begin Working". MarkeTrak system updates state to - In Progress (Gaining CR)
|  |  | 1 | Gaining CR | TDSP | In Progress (Gaining CR) | Agree | CR selects "Agree"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | "In Progress (TDSP)" | Return to Losing CR | TDSP selects "Return to Losing CR" | Comments required
|  |  | 1 | Losing CR | Losing CR | Return to Losing CR (PC) | Accept | Losing CR selects "Accept". Issue is closed.

## MTRES18-1 (Customer Rescission)
|  | Script ID | MTRES18 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR submits MarkeTrak issue under "Customer Rescission" subtype, Losing CR agrees to regain, Losing CR submits BDMI, reinstates ESIID one day following DOL
|  | Success Criteria | Gaining CR submits issue, Losing CR agrees to regain, Losing CR submits BDMI, reinstates ESIID one day following DOL. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Losing CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and all required fields are populated, and the Issue is in a state of "New Losing CR) | Tester should verify that Regain date is Gaining CR's switch date plus one
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Send to TDSP | Losing CR selects "Send to TDSP"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | In Progress (TDSP) | "Ready to Receive" | TDSP selects "Ready to Receive"
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Submit) | Begin Working | Losing CR selects "Begin Working"
Day 1
|  |  | 1 | Losing CR | Gaining | In Progress (Submit Regaining) | Provide Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Submitted (PC) | Complete | Gaining CR selects "Complete" and issue is closed | Or, issue may complete as a result of Siebel automation

## MTRES18-2 (Customer Rescission)
|  | Script ID | MTRES18-2 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR submits MarkeTrak issue under "Customer Rescission" subtype, Losing CR selects "Unexecutable" transition, issue is closed
|  | Success Criteria | Gaining CR submits issue, Losing CR selects "Unexecutable", Gaining CR accepts. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Losing CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and all required fields are populated, and the Issue is in a state of "New Losing CR) | Tester should verify that Regain date is Gaining CR's switch date plus one
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Unexecutable | Losing CR selects "Unexecutable" | Comments Required
|  |  | 1 | Gaining CR | Gaining CR | Unexecutable (PC) | Accept | Gaining CR selects "Accept" and issue is closed

## MTRES18-3 (Customer Rescission)
|  | Script ID | MTRES18-3 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR submits MarkeTrak issue under "Customer Rescission" subtype, Losing CR clicks Unexecutable, Gaining CR returns issue to Losing CR, Losing CR agrees to regain
|  | Success Criteria | Gaining CR submits issue, Losing CR selects "Unexecutable", Gaining CR returns issue, Losing CR agrees to regain. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Losing CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and all required fields are populated, and the Issue is in a state of "New Losing CR) | Tester should verify that Regain date is Gaining CR's switch date plus one
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Unexecutable | Losing CR selects "Unexecutable" | Comments Required
|  |  | 1 | Gaining CR | Gaining CR | Unexecutable (PC) | Return to Losing CR | Gaining CR selects "Return to Losing CR" | Comments Required
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Send to TDSP | Losing CR selects "Send to TDSP"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | In Progress (TDSP) | "Ready to Receive" | TDSP selects "Ready to Receive"
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Submit) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Gaining | In Progress (Submit Regaining) | Provide Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Submitted (PC) | Complete | Gaining CR selects "Complete" and issue is closed | Or, issue may complete as a result of Siebel automation

## MTRES18-4 (Customer Rescission)
|  | Script ID | MTRES18-4 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR attempts to submit MarkeTrak issue under "Customer Rescission" subtype, ERCOT performs validations, determines ESIID was not enrolled via 814_01, displays error message, user cancels submission.
|  | Success Criteria | Gaining CR attempts to submit issue, receives error message due to enrollment not via 814_01, issue cannot move forward, Gaining CR accepts. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | Gaining CR | Gaining CR | Remains in "Create" state due to error message | Cancel | Gaining CR selects "Cancel"- issue cannot proceed due to enrollment transaction is not an 814_01. Submit action is successfully cancelled. | Error message received: "This issue is unable to proceed because the tran type for this Global ID is not an 814_01. Please enter a different ESIID/Original Tran ID or consult the Retail Market Guide to determine the proper course of action."

## MTRES18-5 (Customer Rescission)
|  | Script ID | MTRES18-5 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR attempts to submit MarkeTrak issue under "Customer Rescission" subtype, ERCOT performs validations, determines ESIID was not enrolled within last 25 calendar days, displays error message, user cancels submission.
|  | Success Criteria | Gaining CR attempts to submit issue, receives error message due to enrollment not within 25 days, issue cannot move forward, Gaining CR accepts. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | Gaining CR | Gaining CR | Remains in "Create" state due to error message | Cancel | Gaining CR selects "Cancel"- issue cannot proceed due to enrollment transaction is not within 25 calendar days. Submit action is successfully cancelled. | Error message received: This issue is unable to proceed because the effective date of the originating transaction at this premise was more than 25 calendar days in the past. Please enter a different ESIID or consult the Retail Market Guide to determine the proper course of action.”

## MTRES18-6 (Customer Rescission)
|  | Script ID | MTRES18-6 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR attempts to submit MarkeTrak issue under "Customer Rescission" subtype, ERCOT displays error message (in this example, 814_01 error), Gaining CR enters new BGN which passes validation, issue proceeds.
|  | Success Criteria | Gaining CR attempts to submit issue, receives error message due to enrollment not via 814_01, new BGN is entered, workflow contiunes as normal. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | Gaining CR | Gaining CR | Remains in "Create" state due to error message. Gaining CR enters new BGN, selects OK, issue proceeds to next step. | OK | Gaining CR selects "OK"- issue is able to proceed as normal once information is corrected. | ERCOT becomes Responsible MP, validation is passed.

## MTRES18-7 (Customer Rescission)
|  | Script ID | MTRES18-7 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR attempts to submit MarkeTrak issue under "Customer Rescission" subtype, ERCOT performs validations, determines ESIID is not a valid ESIID within the ERCOT system, displays error message, user cancels submission.
|  | Success Criteria | Gaining CR attempts to submit issue, ERCOT performs validations, determines ESIID is not a valid ESIID within the ERCOT system, displays error message, user cancels submission. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | Gaining CR | Gaining CR | Remains in "Create" state due to error message | Cancel | Gaining CR selects "Cancel"- issue cannot proceed due to invalid ESIID entered into ESIID field | Error message received: “ESIID ___________ is not valid according to the ERCOT Registration System. ”

## MTRES18-8 (Customer Rescission)
|  | Script ID | MTRES18-8 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR submits MarkeTrak issue under "Customer Rescission" subtype, Losing CR agrees to regain, Issue remains in a state of “Regaining Transaction Submitted (PC)” for more than 3-5 business/calendar days (depending on version upgrade), an email notification is sent to the Losing CR, Losing CR submits BDMI, reinstates ESIID one day following DOL
|  | Success Criteria | Gaining CR submits issue, Losing CR agrees to regain, Issue remains in a state of “Regaining Transaction Submitted (PC)” for more than 3-5 business/calendar days (depending on version upgrade), an email notification is sent to the Losing CR, Losing CR submits BDMI, reinstates ESIID one day following DOL. All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Losing CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and all required fields are populated, and the Issue is in a state of "New Losing CR) | Tester should verify that Regain date is Gaining CR's switch date plus one
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Send to TDSP | Losing CR selects "Send to TDSP"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | In Progress (TDSP) | "Ready to Receive" | TDSP selects "Ready to Receive"
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Submit) | Begin Working | Losing CR selects "Begin Working"
Day 1
|  |  | 1 | Losing CR | Gaining | In Progress (Submit Regaining) | Provide Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information | Invalid BGN is entered
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Submitted (PC) | No action by Gaining CR | No action by Gaining CR | An email notification is sent to Losing CR after Siebel has not recognized BGN for 5 calendar days
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Re-Submit) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Gaining | In Progress (Re-Submit Regaining) | Re-Submit Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information | Valid BGN is now entered
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Re-Submitted (PC) | Complete | Gaining CR selects "Complete" and issue is closed | Or, issue may complete as a result of Siebel automation

## MTRES18-9 (Customer Rescission)
|  | Script ID | MTRES18-9 |  | Power Point
|  | Script Name | Customer Rescission
|  | Script Storyline | Gaining CR submits MarkeTrak issue under "Customer Rescission" subtype, Losing CR agrees to regain, Issue remains in a state of “Regaining Transaction Submitted (PC)” for more than 3-5 business/calendar days (depending on version upgrade), an email notification is sent to the Losing CR, Losing CR re-submits BDMI, issue remains in PC state for greater than 3-5 business/calendar days. Issue auto closes.
|  | Success Criteria | Gaining CR submits issue, Losing CR agrees to regain, Issue remains in a state of “Regaining Transaction Submitted (PC)” for more than 3-5 business/calendar days (depending on version upgrade), an email notification is sent to the Losing CR, Losing CR re-submits BDMI, issue remains in PC state for greater than 3-5 business/calendar days. Issue auto closes.All transitions work as intended, issue is able to reach resolution.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS | 31, 32 |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | Gaining CR | ERCOT | New (ERCOT) | Submit | Gaining CR populates all required information and selects "OK"
|  |  | 1 | ERCOT | ERCOT | New (ERCOT) | Begin Working | ERCOT selects "Begin Working". Issue is in a state of "In Progress (ERCOT)"
|  |  | 1 | ERCOT | Losing CR | In Progress (ERCOT) ERCOT | Select IAS parties | ERCOT performs all validations and selects Gaining and Losing CR. ERCOT chooses "Select IAS Parties" transition and all required fields are populated, and the Issue is in a state of "New Losing CR) | Tester should verify that Regain date is Gaining CR's switch date plus one
|  |  | 1 | Losing CR | Losing CR | New (Losing CR) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Losing CR | In Progress (Losing CR) | Send to TDSP | Losing CR selects "Send to TDSP"
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | Losing CR | In Progress (TDSP) | "Ready to Receive" | TDSP selects "Ready to Receive"
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Submit) | Begin Working | Losing CR selects "Begin Working"
Day 1
|  |  | 1 | Losing CR | Gaining | In Progress (Submit Regaining) | Provide Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information | Invalid BGN is entered
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Submitted (PC) | No action by Gaining CR | No action by Gaining CR | An email notification is sent to Losing CR after Siebel has not recognized BGN for 5 calendar days
|  |  | 1 | Losing CR | Losing CR | New (Losing CR Re-Submit) | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | Losing CR | Gaining | In Progress (Re-Submit Regaining) | Re-Submit Regaining BGN02 | Losing CR selects "Provide Regaining BGN02" and populates all required information | Invalid BGN is entered
|  |  | 1 | Gaining CR | Gaining CR | Regaining Transaction Re-Submitted (PC) | No action by Gaining CR | No action by Gaining CR | No email notification is sent to Losing CR after Siebel has not recognized BGN for 5 calendar days. Issue will auto-close within 10 calendar days if there is no activity.

## MTUSG13D-1 (AMS LSE Dispute)
|  | Script ID | MTUSG13D-1 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Dispute
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Dispute" subtype, TDSP is able to accommodate request, issue is able to be transitioned to a normal resolution.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Complete | TDSP selects "Complete"
|  |  | 1 | CR | CR | Pending Complete | Complete | CR selects "Complete" | Issue is in a "Complete" state

## MTUSG13D-2 (AMS LSE Dispute)
|  | Script ID | MTUSG13D-2 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Dispute
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Dispute" subtype, TDSP chooses the "Unexecutable" transition, CR clicks "Accept", issue is closed.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Unexecutable | TDSP selects "Unexecutable"
|  |  | 1 | CR | CR | Unexecutable (PC) | Accept | CR selects "Accept" | Issue is in a "Complete" state

## MTUSG13D-3 (AMS LSE Dispute)
|  | Script ID | MTUSG13D-3 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Dispute
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Dispute" subtype, TDSP chooses "Return to Submitter", CR chooses "Return to Assignee", TDSP is able to accommodate CR request, issue is able to be transitioned to a normal resolution.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Return to Submitter | TDSP selects "Return to Submitter", enters comments
|  |  | 1 | CR | CR | New (All) | Begin Working | CR selects "Begin Working" | Issue is in a state of "In Progress"
|  |  | 1 | CR | TDSP | In Progress | Return to Assignee | CR selects "Return to Assignee", enters comments | Issue is in a state of "New"
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Complete | TDSP selects "Complete"
|  |  | 1 | CR | CR | Pending Complete | Complete | CR selects "Complete" | Issue is in a "Complete" state

## MTUSG13D-4 (AMS LSE Dispute)
|  | Script ID | MTUSG13D-4 |  | Power Point
|  | Script Name | Usage and Billing AMS Interval Data Dispute
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Dispute" subtype, TDSP chooses "Return to Submitter", CR chooses "Close", issue falls into a "Closed by Submitter" state
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Return to Submitter | TDSP selects "Return to Submitter", enters comments
|  |  | 1 | CR | CR | New (All) | Begin Working | CR selects "Begin Working" | Issue is in a state of "In Progress"
|  |  | 1 | CR | CR | In Progress | Close | CR selects "Close" | Issue is in a state of "Closed by Submitter"

## MTUSG13M-1 (AMS LSE Missing)
|  | Script ID | MTUSG13M-1 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Missing
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Missing" subtype, TDSP is able to accommodate request, issue is able to be transitioned to a normal resolution.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Complete | TDSP selects "Complete"
|  |  | 1 | CR | CR | Pending Complete | Complete | CR selects "Complete" | Issue is in a "Complete" state

## MTUSG13M-2 (AMS LSE Missing)
|  | Script ID | MTUSG13M-2 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Missing
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Missing" subtype, TDSP chooses the "Unexecutable" transition, CR clicks "Accept", issue is closed.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Unexecutable | TDSP selects "Unexecutable"
|  |  | 1 | CR | CR | Unexecutable (PC) | Accept | CR selects "Accept" | Issue is in a "Complete" state

## MTUSG13M-3 (AMS LSE Missing)
|  | Script ID | MTUSG13M-3 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Missing
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Missing" subtype, CR chooses "Return to Assignee", TDSP is able to accommodate CR request, issue is able to be transitioned to a normal resolution.
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Return to Submitter | TDSP selects "Return to Submitter", enters comments
|  |  | 1 | CR | CR | New (All) | Begin Working | CR selects "Begin Working" | Issue is in a state of "In Progress"
|  |  | 1 | CR | TDSP | In Progress | Return to Assignee | CR selects "Return to Assignee", enters comments | Issue is in a state of "New"
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Complete | TDSP selects "Complete"
|  |  | 1 | CR | CR | Pending Complete | Complete | CR selects "Complete" | Issue is in a "Complete" state

## MTUSG13M-4 (AMS LSE Missing)
|  | Script ID | MTUSG13M-4 |  | Power Point
|  | Script Name | Usage/ Billing AMS LSE Interval Missing
|  | Script Storyline | CR submits MarkeTrak issue under "Usage/ Billing AMS LSE Interval Missing" subtype, TDSP chooses "Return to Submitter", CR chooses "Close", issue falls into a "Closed by Submitter" state
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR | TDSP | Submit | CR enters required information, clicks OK
|  |  | 1 | TDSP | TDSP | New | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR | In Progress (Assignee) | Return to Submitter | TDSP selects "Return to Submitter", enters comments
|  |  | 1 | CR | CR | New (All) | Begin Working | CR selects "Begin Working" | Issue is in a state of "In Progress"
|  |  | 1 | CR | CR | In Progress | Close | CR selects "Close" | Issue is in a state of "Closed by Submitter"

## MTSWH19-1 (Switch Hold Removal)
|  | Script ID | MTSWH19-1 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record agrees to release switch hold, TDSP evaluates information and confirms removal of switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | CR2 | TDSP | In Progress (Assignee) | Agree | Losing CR selects "Agree"
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-2 (Switch Hold Removal)
|  | Script ID | MTSWH19-2 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP confirms no REP of Record and removes switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | TDSP | In Progress (TDSP) | No REP of Record | TDSP selects "No REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-3 (Switch Hold Removal)
|  | Script ID | MTSWH19-3 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record disagrees with release of switch hold, TDSP does final evaluation and confirms removal of switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | CR2 | TDSP | In Progress (Assignee) | Disagree | Losing CR selects "Disagree"
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-4 (Switch Hold Removal)
|  | Script ID | MTSWH19-4 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record disagrees with release of switch hold, TDSP does final evaluation and denies removal of switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | CR2 | TDSP | In Progress (Assignee) | Disagree | Losing CR selects "Disagree"
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Not Removed | TDSP selects "Switch Hold Not Removed" and enters comments
|  |  | 1 | CR1 | TDSP | Unexecutable (PC) | Complete | CR1 selects "Accept", issue falls into a "Closed" state

## MTSWH19-5 (Switch Hold Removal)
|  | Script ID | MTSWH19-5 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP confirms no REP of Record and declines to remove switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | TDSP | In Progress (TDSP) | No REP of Record | TDSP selects "No REP of Record"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Not Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Unexecutable (PC) | Complete | CR1 selects "Accept", issue falls into a "Closed" state

## MTSWH19-6 (Switch Hold Removal)
|  | Script ID | MTSWH19-6 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, unexecutes issue for reason of incomplete or incorrect documentation
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches documentation (considered incomplete by TDSP), clicks OK |  | Variation of this test case- CR1 does not attach any documentation; issue should not proceed
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP) | Unexecutable | TDSP selects "Unexecutable" and chooses one of required dropdown options
|  |  | 1 | CR1 | TDSP | Unexecutable (PC) | Complete | CR1 selects "Accept", issue falls into a "Closed" state

## MTSWH19-7 (Switch Hold Removal)
|  | Script ID | MTSWH19-7 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record does not “Begin Working” and exceeds time limit, Requesting CR notifies TDSP, TDSP removes switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | (No transition; CR2 does not Begin Working within allowed timeframe)
|  |  | 1 | CR1 | TDSP | New | Time Limit Exceeded | CR1 selects "Time Limit Exceeded" | CR1 may use this transition even though CR2 is Responsible MP; TDSP will be Responsible MP once this transition is chosen by CR1
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-8 (Switch Hold Removal)
|  | Script ID | MTSWH19-8 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record chooses “Begin Working”, but does not transition issue and exceeds time limit, Requesting CR notifies TDSP, TDSP removes switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | Begin Working | Losing CR selects "Begin Working"
|  |  | 1 | CR2 | CR2 | In Progress (Assignee) | (No transition; CR2 does not choose another transition within allowed timeframe)
|  |  | 1 | CR1 | TDSP | New | Time Limit Exceeded | CR1 selects "Time Limit Exceeded" | CR1 may use this transition even though CR2 is Responsible MP; TDSP will be Responsible MP once this transition is chosen by CR1
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-9 (Switch Hold Removal)
|  | Script ID | MTSWH19-9 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record does not “Begin Working” and exceeds time limit, Requesting CR notifies TDSP using “Time Limit Exceeded” transition, TDSP returns issue to REP of Record due to early use of “Time Limit Exceeded” transition, “Time Limit Exceeded” transition is used correctly, TDSP removes switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | (No transition; CR2 does not Begin Working)
|  |  | 1 | CR1 | TDSP | New | Time Limit Exceeded | CR1 selects "Time Limit Exceeded" | CR1 may use this transition even though CR2 is Responsible MP; TDSP will be Responsible MP once this transition is chosen by CR1
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP)- Final Review | Return to REP of Record | TDSP selects "Return to REP of Record"
|  |  | 1 | CR2 | CR2 | New | (No transition; CR2 does not Begin Working within allowed timeframe)
|  |  | 1 | CR1 | TDSP | New | Time Limit Exceeded | CR1 selects "Time Limit Exceeded" | CR1 may use this transition even though CR2 is Responsible MP; TDSP will be Responsible MP once this transition is chosen by CR1
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Pending Complete | Complete | CR1 selects "Complete", issue falls into a "Complete" state

## MTSWH19-10 (Switch Hold Removal
|  | Script ID | MTSWH19-10 |  | Power Point
|  | Script Name | Switch Hold Removal
|  | Script Storyline | Requesting CR submits MarkeTrak issue under "Switch Hold Removal" subtype, TDSP does initial evaluation, REP of Record does not “Begin Working” and exceeds time limit, Requesting CR notifies TDSP, TDSP still does not remove switch hold
Success Criteria
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential |  |  | CR1
|  | MT RQMTS |  |  | TRACK | MarkeTrak
Simulated Entity
Duns Number
|  | Number of TDSPs | 1
|  |  | ERCOT | TDSP | CR1
|  | PreTest Setup | None | None | None
Checkpoint Date |  | Calendar | Issue | Sender | Receiver | Initial State: Responsible MP | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 1 | 1 | CR1 | TDSP | Submit | CR enters required information, attaches document, clicks OK
|  |  | 1 | TDSP | TDSP | New (TDSP) | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR2 | In Progress (TDSP) | Send to REP of Record | TDSP selects "Send to REP of Record" | TDSP chooses DUNS and company name of REP of Record
|  |  | 1 | CR2 | CR2 | New | (No transition; CR2 does not Begin Working within allowed timeframe)
|  |  | 1 | CR1 | TDSP | New | Time Limit Exceeded | CR1 selects "Time Limit Exceeded" | CR1 may use this transition even though CR2 is Responsible MP; TDSP will be Responsible MP once this transition is chosen by CR1
|  |  | 1 | TDSP | TDSP | New (TDSP)- Final Review | Begin Working | TDSP selects "Begin Working"
|  |  | 1 | TDSP | CR1 | In Progress (TDSP)- Final Review | Switch Hold Not Removed | TDSP selects "Switch Hold Removed"
|  |  | 1 | CR1 | TDSP | Unexecutable (PC) | Complete | CR1 selects "Accept", issue falls into a "Closed" state