## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
November 17, 2011

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    Project Portfolio Status (Gantt Chart)
  2011 Project Spending Update p. 7
  ERCOT FTE Impact Tracking p. 8
  Multi-Year PPL Update and 2012 Release Plan p. 9-14
    Multi-Year PPL Features
    Prioritization Factors for Market Subcommittees
    2012 Release Summary

## Slide 3: Upcoming Project Implementations
Go-Lives Planned for December / (NPRR320 in an off-cycle November release)
  NPRR320 – Minimum PTP Option Bid and Settlement
    Off-cycle November release on 11/11 of settlements calculations (TOU logic)
  NPRR251 – Sync w/PRR845 – Def. of IDR Meters and Optional Removal of IDRs at a Premise…
    Code in production – market go-live is Feb. 2012
  NPRR290 – ERCOT Publication of DAM PSS/E Files
  NPRR310 – Expand Output Schedule Acceptable Range to Include HSL and LSL
  NPRR316 – Negative Self-Arranged Ancillary Services Quantity
  NPRR343 – CRR Bid and PTP Obligation Bid Criteria Change
  SCR763 – Modify COP Validation Rule for RRS
  SCR764 – Public Access to Select MIS Dashboards
    Dec. – 4th phase – LMP Contour Map
    LMP Ticker may be removed from scope (see MIS User Group comments dated 11/8/2011)
  SCR765 – Public Aggregated Wind Dashboard
  Stabilization/Deferred Defects
    Deferred Defects – Release 10
    TML Transition to MIS
    Stabilization and its sub-projects are scheduled to end on 12/31/2011
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Project Portfolio Status – as of 11/14/2011

## Slide 5: Project Portfolio Status – as of 11/14/2011

## Slide 6: Project Portfolio Status – as of 11/14/2011

## Slide 7: 2011 Project Spending Update – 11/14/2011
PPL | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 28,178,937 | $ 24,818,114 | $ 22,298,753
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 7,201,500 | $ 4,298,208
Totals | $ 41,900,000 | $ 36,363,937 | $ 32,019,614 | $ 26,596,961
* Data Center Hardware Budget reduced by the amount of purchasing accelerated from 2011 to 2010 (~$5.5M)
*

## Slide 8: ERCOT FTE Tracking
Summary of FTE Impact of Revision Requests - By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR343 | Operations | Market Analysis | 1.00 | 0 |  | Manual workaround no longer needed after project implementation in December 2011
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 |  | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 6.70 | 2 |  | 
--- In-Flight at TAC --- |  |  |  |  |  | 
None |  |  |  |  |  | 
 | In-Flight at TAC |  | 0.00 | 0 |  | 
 | Total of All Items |  | 6.70 | 2 |  | 

## Slide 9: Multi-Year PPL and 2012 Release Plan
The new Multi-Year PPL is complete and posted to ERCOT.com
  http://www.ercot.com/services/projects/index
  The format has been changed to accommodate a multi-year view (2011-2015)
  Additional data is captured that will better inform the market on delivery plans for items approved in the stakeholder process
  Upcoming slides explain changes in more detail
An initial forecast of 2012 project implementations is complete
  6 releases planned
    1 every other month, starting in February 2012
    Occasional off-cycle releases when necessary
      Example: TX SET 4.0 in early June
  Includes projects forecasted on the Board-approved PPL… plus…
  Revision Requests approved by the Board since August
  Projects in the 1st 2012 release began initiating in November

## Slide 10: Multi-Year PPL Features
Key Data Fields
  Project Category
    Business Strategy (NPRRs, SCRs, other strategic efforts)
    Efficiencies / Enhancements (Internal ERCOT operational improvements)
    Regulatory (Required by regulatory entity)
    Technical Foundation (Infrastructure maintenance and growth)
  Approval Status
    Stakeholder approval status
    “PPL” means approved and able to initiate when the timing is right
  2012 Release
    Target 2012 release (R1-R6)
    “n/a” denotes future or previous year projects
  Budget Forecasts – 2011-2015
  Project Status
    Not Started
    Initiation
  Projected Start and End Dates
    Initial timeframe projections based on Rank and resource availability
    Revised as necessary as project proceeds through the project lifecycle
    Planning
    Execution
    Closing
    Complete

## Slide 11: Multi-Year PPL Features (cont’d)
No Cutline!
  ERCOT will attempt to undertake all projects in the year(s) when they are funded
  If resource constraints prevent execution in the desired timeframe, ERCOT will determine an achievable schedule and update the “Projected End Date” on the PPL
Summary Portfolio Financials
  Budget and Spending Forecasts by Project Category and Budget Year
    See rows in the header of the PPL
  Based on actual budget and spending forecasts
Approval Logging
  “PPL Update Log” tab
  Captures changes to key fields
  Requested by COPS in 2011
  Fields that are “logged”
    Rank
    Approval Status
    Project Name
  Previous approvals from late August 2011 through current have been captured
    Project Status
    Budget Range (all years)
    Projected Start Date
    Projected End Date

## Slide 12: Multi-Year PPL – Prioritization Factors for Market Subcommittees
Priority (new definition)
  ERCOT recommends that we change the current Priority values (“Critical”, “High”, etc.) to the proposed funding year (“2012”, “2013”, etc.)
Rank (revised usage approach)
  Rank values are now assigned in increments of 10 to allow for placement of subsequent items without using decimal Ranks
  New additions to the PPL will be placed at the end of the appropriate Project Category and given the next available Rank value
  If stakeholders want to indicate that a new NPRR should be given priority over previously ranked items, the new item can be assigned a Rank in the desired area of the Project Category
    This implies that items below the assigned Rank may have their release plan reconsidered if resource contention is expected
Release Planning (enhanced process)
  ERCOT staff will regularly evaluate new projects for inclusion in the release plan
  Results of this analysis (Projected Start and End Dates) will be reflected on the PPL

## Slide 13: 2012 Release Summary – NPRRs/SCRs
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | NPRR321 NPRR322 SCR761 | NPRR313 NPRR314 NPRR361 | NPRR294 NPRR354 NPRR357 NPRR359 NPRR382 NPRR383 SCR756 SCR760 |  | NPRR207 NPRR222 NPRR260 NPRR272 NPRR360 |  | 
ERCOT | NPRR326 NPRR355 |  | NPRR348 | NPRR365 | NPRR379 |  | NPRR347 NPRR400
Counts | 5 | 3 | 9 | 1 | 6 | 0 | 2
Note 1: NPRRs/SCRs in bold were included in the original Board-approved 2012 PPL
Note 2: Release targets are subject to change
Note 3: NPRR294 and SCR756 are in an off-cycle June release (TX SET 4.0 go-live)

## Slide 14: Business Integration Update
  Questions?