## Task List
NPGRTF TASKS LIST
Protocol Section | Operating Guide Section | NERC RS | Primary Assignee | Secondary Assignee | Possible Conflict | Proposed Resolution Action | Revision Request No. | Due By | Status
3.15.2(d) | N/A | N/A | JC Culberson | Jbillo | Conflict with roles of NERC registered entities and the requirement of a self-certification | Revise 3.15.2(d) to remove conflict. | PRS / NPRR328 | 2011-05-19 | Closed
| 3.7.3 (1) | CIP-001 | Frank Owens |  | Conflict with registered entities applicability | Add TSP, QSE and any ERCOT Entity to paragragh (2) | NOGRR74 | 2011-04-19 | Active / Tabled at TAC
| 4.5.3.4 | EOP-003 | Billy Lee |  | Obligation for Load shed is by DSP. | Add directive of TO to DSP obligation language for DSP in 4.5.3.4 | NOGRR73 | 2011-04-19 | Withdraw
| 4.6.4 (2) | EOP-005 | Frank Owens |  | None |  |  | 2011-03-15 | Closed
| 4.6.1 (2) | EOP-006 R4 | Frank Owens |  | (2) ERCOT shall establish and maintain a system Black Start capability plan that shall be coordinated, as appropriate, with the Black Start capability plans of neighboring regions. Documentation of system Black Start capability plans shall be provided to the North American Electric Reliability Corporation (NERC) on request. Will be addressed by Frank Owens at the NPGRTF as a conflict for “neighboring regions”. | Delete paragraph | NOGRR76 | 2011-07-19 | Active
| 3.7 (3), (4) | EOP-008 | Frank Owens |  |  |  |  | 2011-03-15 | Closed
8.1.1.2.1.5 | 4.6 & 4.6.4 (3) | EOP-009 | Jack Thormahlen |  | Applicability of ERCOT registered entites with responsiblities pertaining to Black Start Plan | Applicability of TSPs and other Market Participants. Confidentiality issues for distribution/sharing of ERCOT Black Start plan. | Pending |  | Active
| 5.1 | FAC-002 | JC Culberson |  | None |  |  | 2011-03-15 | Closed
| 3.7.1,2 | FAC-003 | Frank Owens |  | Texas RE Website referenced is out of date | Change Texas Regional to Reliability and correct Texas RE Website. | Submitted Email to Texas Re | 2011-05-19 | Active
| 3.1 | FAC-008 | Dylan Preas |  | None |  |  | 2011-08-16
3.1.4.5 | 5.1 | FAC-009 | JC Culberson |  | Ratings must be reported, but to whom? | To synchronize with FAC-009, the ratings should be provided to ERCOT, applicable TO and applicable planning entities. |  | 2011-09-20
3.1.3.1 & 3.1.3.2 |  | IRO-004 | Brenda Hampton |  | None
3.10.7.1.4 & 3.10.7.2 | 3.3.1,2 | MOD-010, 012 | Brenda Hampton |  | None |  |  | 2011-09-20 | Closed
2.0 Definition | 1.5.2 | PER-003 or 005 | Jeff Sims | Brad, Matt |  |  |  | 2011-06-14 | Closed
| 6.2.4 (3), (4) | PRC-001 | Dylan Preas |  | None |  |  | 2011-07-19 | Closed
| 6.2.3 | PRC-004 | Small Group |  |  |  |  | 2011-09-20
| 6.2.5 & 6.2.6.3.4 | PRC-005 | Small Group |  |  |  |  | 2011-09-20
| 2.6.1 | PRC-007 | Jeff Sims |  | None |  |  | 2011-08-16
| 6.1 | PRC-018 | Frank Owens |  |  |  |  | 2011-09-20
5.5.2 | 3.1.5 &6 | TOP-002 | Jeff Sims |  |  |  |  | 2011-09-20
3.1.3.2 | 9.1.6 | TOP-003 | Jeff Sims |  | None |  |  | 2011-05-19 | Closed
| 5.1 | TPL-001 | JC Culberson |  | None |  |  | ?????? | Closed
| 5.1 | TPL-002 | JC Culberson |  | None |  |  | ?????? | Closed
| 5.1 | TPL-003 | JC Culberson |  | None |  |  | ?????? | Closed
| 5.1 | TPL-004 | JC Culberson |  | None |  |  | ?????? | Closed
3.15.2 |  | VAR-001 | Dylan Preas |  | None |  |  | 2011-06-14 | Closed
| 2.7.4.1 | VAR-002 | Dylan Preas |  | None |  |  | 2011-06-14 | Closed
3.15.2 | 2.7.4.1 (4) | VAR-001 | Frank Owens |  | 2 % of scheduled voltage vs 2% of voltage profile | No conflict found |  | 2011-07-19
6.5.4 | 2.8.1 | BAL-006 | Matt Stout |  | Inadvertent Interchange | Will submit draft NPRR/NOGRR to the group |  | 2011-10-18 | Active
| 4.5.3.3 | EOP-003 |  |  | Issue with NOGRR073 and 4.5.3.3 reference to TO,TSP and DSP for load shedd obligations |  |  | 2011-10-18 | Hold
1 | 2 thru 9 | TOP | Jeff Sims |  | TSP and TO reference to become TSO |  |  | 2011-10-18
2 | 1 | TOP | Frank Owens |  | TSP and TO reference to become TSO |  |  | 2011-10-18
3 thru 6 |  | TOP | JC Culberson |  | TSP and TO reference to become TSO |  |  | 2011-10-18
7 thru 9 |  | TOP | Matt Stout |  | TSP and TO reference to become TSO |  |  | 2011-10-18
10 thru 14 |  | TOP | Dylan Preas |  | TSP and TO reference to become TSO |  |  | 2011-10-18
15 thru 18 |  | TOP | Andy Gallo |  | TSP and TO reference to become TSO |  |  | 2011-10-18
19 thru 22 |  | TOP | Brenda Hampton |  | TSP and TO reference to become TSO |  |  | 2011-10-18
| 3.7.2 | FAC-003 | Frank Owens |  | NERC Requirements for Reporting Vegetation-Related Line Outages | Remove TO reporting requirement |  | 2011-10-18 | Active

## Timeline G
Operating Guides | Date
1
2
3
4
5
6
7
8A
8B
8C
8D
8E
8F
8G
8H
9

## Timeline P
Protocol | Date
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22A
22B
22C
22D
22E
22F
22G
22H
23
24