## TX SET V4.0 Implementation
Tuesday, May 29, 2012
Time | Task | Entity
14:00 | 1st Market Conference Call - Confirm all MPs are ready to proceed with TX SET V4.0 implementation | All MPs
Wednesday, May 30, 2012
Time | Task | Entity
12:00 | CRs suspend sending 650_01 DNP Transactions - Pending DNPs will continue to be worked according to the DNP procedures | All CRs
17:00 | TDSPs will flush systems to cancel all pending 650 DNPs and send complete unexecutables to CRs | All TDSPs
Thursday, May 31, 2012
Time | Task | Entity
16:00 | 2nd Market Conference Call - Confirm DNPs are suspended; Roll call for TDSPs only | All MPs
Friday, June 1, 2012
Time | Task | Entity
8:00 | CRs suspend sending 814 transactions to ERCOT (both EDI and through Retail portion of MIS) | All CRs
| CRs begin using Safety Net process as needed for submitting MVIs with a requested date of June 1 - June 5 | All CRs
| CRs suspend 814_PC transactions | All CRs
| CRs suspend 650_01 transactions | All CRs
| TDSPs suspend 650_04 transactions | All TDSPs
| TDSPs suspend 814_20 transactions | All TDSPs
9:00 | TDSPs suspend 867s and 814 responses | All TDSPs
| CRs suspend 824 transactions | All CRs
| TDSPs suspend 814_PD transactions | All TDSPs
| TDSPs suspend 650_02 transactions | All TDSPs
| CRs suspend 650_05 transactions | All CRs
| TDSPs to log MarkeTrak Issue with ERCOT for AMS Initial load file (excludes Sharyland and Nueces) | All TDSPs
10:00 | 3rd Market Conference Call - ERCOT confirmation of transaction suspension. Update on transaction processing. | All MPs
12:00 | TDSPs suspend 810_02 (820_03MC) transactions | All TDSPs
| CRs suspend 820_02 (810_03MC) transactions | All CRs
| 997s suspended for all transactions | All MPs
| ERCOT shuts down inbound and outbound processing and MarkeTrak | ERCOT
| ERCOT sends out System Shutdown email to market | ERCOT
Saturday, June 2, 2012
Time | Task | Entity
12:00 | 4th Market Conference Call - MP Migration Status | All MPs
18:00 | 5th Market Conference Call - MP Migration Status | All MPs
Sunday, June 3, 2012
Time | Task | Entity
10:00 | 6th Market Conference Call - MP Migration Status; Confirm Market Readiness | All MPs