## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
December 15, 2011

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    Project Portfolio Status (Gantt Chart)
  2011 Project Spending Update p. 7
  ERCOT FTE Impact Tracking p. 8
  PPL Update and 2012 Release Plan p. 9-11
    PPL Update
    2011 Release Summary
    2012 Release Plan

## Slide 3: Recent Project Implementations
Go-Lives in December / (no January release)
  NPRR251 – Sync w/PRR845 – Def. of IDR Meters and Optional Removal of IDRs at a Premise…
  NPRR290 – ERCOT Publication of DAM PSS/E Files
  NPRR310 – Expand Output Schedule Acceptable Range to Include HSL and LSL
  NPRR316 – Negative Self-Arranged Ancillary Services Quantity
  NPRR321 – Real-Time PTP Option Modeling
    MMS portion
  NPRR343 – CRR Bid and PTP Obligation Bid Criteria Change
  SCR763 – Modify COP Validation Rule for RRS
  SCR764 – Public Access to Select MIS Dashboards
    Dec. – 4th phase – LMP Contour Map
  SCR765 – Public Aggregated Wind Dashboard
  Stabilization/Deferred Defects
    Deferred Defects – Release 10
    TML Transition to MIS
    Stabilization and its sub-projects are scheduled to end on 12/31/2011
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: Project Portfolio Status – as of 12/9/2011

## Slide 5: Project Portfolio Status – as of 12/9/2011

## Slide 6: Project Portfolio Status – as of 12/9/2011

## Slide 7: Project Spending Update – 12/2/2011
PPL – 2011 | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 28,179,000 | $ 24,235,202 | $ 23,625,284
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 7,971,812 | $ 5,169,872
Totals | $ 41,900,000 | $ 36,364,000 | $ 32,207,014 | $ 28,795,156
* Data Center Hardware Budget reduced by the amount of purchasing accelerated from 2011 to 2010 (~$5.5M)
*
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,684,181 | $ 0
Regulatory |  | $ 1,600,000 | $ 1,707,418 | $ 0
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,312,813 | $ 0
Technical Foundation |  | $ 6,500,000 | $ 6,066,770 | $ 0
Totals | $ 15,000,000 | $ 16,100,000 | $ 17,771,182 | $ 0

## Slide 8: ERCOT FTE Tracking
Summary of FTE Impact of Revision Requests - By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 |  | Absorbed in 2012 budget and staffing plan
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 |  | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 5.70 | 2 |  | 
--- In-Flight at TAC --- |  |  |  |  |  | 
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | 
NPRR408 | Operations | Resource Integration | 0.10 | 0 |  | 
 | In-Flight at TAC |  | 1.10 | 1 |  | 
 | Total of All Items |  | 6.80 | 3 |  | 

## Slide 9: PPL Update and 2012 Release Plan
Updated PPL is posted on ERCOT.com
  http://www.ercot.com/services/projects/index
Additional Format Changes
  Added column for target funding year
  Added hyperlinks to related NPRRs/SCRs
See Next 2 Slides for Summary of 2011 Project Deliveries and the Proposed 2012 Release Schedule

## Slide 10: 2011 Release Summary – Projects/NPRRs/SCRs
Source | Release 1 1/2011 | Release 2 2/2011 | Release 3 3/2011 | Release 4 4/2011 | Release 5 5/2011 | Release 6 6/2011
Market / PUCT |  |  | NPRR302 |  | NPRR285(a) NPRR293 NPRR303 NPRR307 NPRR329 | NPRR285(b)
ERCOT |  |  | Met Center Disposition | Planning Model |  | NPRR339(a) NPRR341 Enterprise Records Mgmt Fire Alarm Upgrade
Source | Release 7 7/2011 | Release 8 8/2011 | Release 9 9/2011 | Release 10 10/2011 | Off-Cycle 11/2011 | Release 12 12/2011
Market / PUCT | NPRR146 NPRR282 NPRR323(a) | NPRR208 NPRR323(b) NPRR350 SCR764(a) | NPRR376 SCR764(b) | NPRR258 SCR760(a) SCR764(c) SCR766 | NPRR320 | NPRR251 NPRR290 NPRR310 NPRR316 NPRR321(a) SCR764(d) SCR765
ERCOT | NPRR339(b) | NPRR221 IT Security Infrastructure Upgrade | NPRR346 Data Research & Rptng | SCR762 Data Agg Performance Improvements |  | NPRR338 NPRR343 SCR763 TML Transition to MIS

## Slide 11: 2012 Release Plan – NPRRs/SCRs
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | NPRR321(b) SCR761 | NPRR313 NPRR314 NPRR361 | NPRR294 NPRR357 NPRR359 NPRR382 NPRR383 SCR756 SCR760 |  | NPRR207 NPRR222 NPRR260 NPRR272 NPRR360 | NPRR354 | NPRR322
ERCOT | NPRR326 NPRR355 |  |  | NPRR365 | NPRR379 | NPRR348 | NPRR347 NPRR400
Counts | 4 | 3 | 7 | 1 | 6 | 2 | 3
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Italic/underline indicates revised target release
Note 3: Release targets are subject to change