## -- PPL --
[5 empty] | Multiyear PPL - 2011-2015 | [6 empty] | 2011 |  |  | 2012 |  |  | 2013 |  | 2014 |  | 2015
[5 empty] | View/Print Options |  |  |  | 2012 Release Calendar | Project Categories |  | Sum of Budgets | Funding Level | Spend Forecast | Sum of Budgets | Funding Level | Spend Forecast | Sum of Budgets | Funding Level | Sum of Budgets | Funding Level | Sum of Budgets | Funding Level | 2011 Variance Calculations (Funding less Spend Forecast)
[6 empty] | Show 2013-2015 (S-X) |  |  | R1 -- 2/22 - 2/26 | Stabilization |  | 23400000 | 25191000 | 24300000 | [9 empty] | Stabilization | 891000
[6 empty] | Show Description (AB) |  |  | R2 -- 4/25 - 4/29 | Regulatory |  | 457799 |  | 375040 | 1012418 |  | 1012418 | 0 |  | 0 |  | 0
[6 empty] | Show Prioritization History (B-D) |  |  | R3 -- 6/24 - 6/27 | Business Strategy |  | 3211565 |  | 2806831 | 7750144 |  | 7750144 | 9245628 |  | 3000000 |  | 0
[9 empty] | R4 -- 8/26 - 8/29 | Efficiencies / Enhancements |  | 1290820 |  | 970998 | 2312813 |  | 2312813 | 3847000 |  | 250000 |  | 250000
[9 empty] | R5 -- 10/21 - 10/24 | Technical Foundation |  | 32083127 |  | 28248184 | 6460174 |  | 6460174 | 11010673 |  | 6779182 |  | 10200000
[5 empty] | Note: Print is very small if all above items are displayed |  |  |  | R6 -- 12/5 - 12/9 | PPL Totals |  | 37043311 | 36364000 | 32401053 | 17535549 | 15000000 | 17535549 | 24103301 | TBD | 10029182 | TBD | 10450000 | TBD | PPL Totals | 3962947
Project Category | 2011 Priority | 2011 Rank | Orig Rank | Priority | Rank | Source Doc | Approval Status | Project Number | Project Name | 2012 Release | Project Status | Budget | Budget Range | Spend Forecast | Budget | Budget Range | Spend Forecast | Budget | Budget Range | Budget | Budget Range | Budget | Budget Range | Projected Start Date | Projected End Date | Source | Description | Strategic Obj. Group | Strategic Objective | Cross Impacts
Business Strategy | 2-High | 10 |  | 2011 | 1 |  | PPL | 50088_01 | Data Research and Reporting | n/a | Complete |  | $500k-$1M | [10 empty] | Nov 2006 | Sept 2011 | ERCOT | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse - Final stage of project
Business Strategy | 2-High | 10.5 |  | 2011 | 2 |  | PPL | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | R2 off-cycle | Execution |  |  |  |  | $60k-$75k | [7 empty] | July 2011 | Apr 2012 | ERCOT | Update the RARF and RARF Hub database to increase the data collected for Wind and add necessary data section for Solar PV and Duration Limited Resources - 2012 PPL-funded portion | 1 - Grid Reliability | 1.4 Generation resource interconnection
Business Strategy | 2-High | 12 |  | 2011 | 3 |  | PPL | 10031_01 | Enterprise Records Management Automation (ERMA) | n/a | Complete |  | <$50k | [10 empty] | Jan 2010 | June 2011 | ERCOT | Provide a centralized record management repository for ERCOT with email integration.
Business Strategy | 2-High | 26 |  | 2011 | 4 |  | PPL | 002_01 | Impact Assessment Labor Funds | n/a | Closing |  | $98k-$100k | [10 empty] | Apr 2011 | Oct 2011 | ERCOT | Funding for ERCOT staff labor on Impact Analysis and Cost Benefit Analysis development for potential projects
Business Strategy | 1- Critical | 3 | 1 | 2012 | 10 | NPRR294 NPRR403 RMGR100 | PPL | 11002_01 | Texas SET 4.0 | R3 off-cycle | Execution |  | $1M-$2M |  |  | $600k-$700k | [7 empty] | Feb 2011 | June 2012 | PUCT / Market | TX SET project to include reconnect / disconnect, AMS, Acquisitions, Meter Tampering | 2 - Manage Markets | 2.6 Retail market design
Business Strategy | 1- Critical | 3.5 | 2 | 2012 | 20 | SCR760 | PPL | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | R3 | Execution |  |  |  |  | $500k-$600k | [7 empty] | Apr 2011 | June 2012 | Market | Proposes changes to the Information Model Manager and Topology Processor to fix a number of deficiencies with the proposed Annual Planning Model creation process. | 1 - Grid Reliability | 1.2 Transmission strategy
Business Strategy | 1- Critical | 5 | 3 | 2012 | 30 |  | PPL | 006_01 | Cyber Security Project #1 | R2 | Planning |  | $400k-$500k |  |  | $90k-$110k | [7 empty] | May 2011 | Apr 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Business Strategy | 1- Critical | 7 | 4 | 2012 | 40 |  | PPL | 005_01 | Cyber Security Project #2 | R2 | Execution |  | $150k-$200k |  |  | $160k-$180k | [7 empty] | May 2011 | Apr 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Business Strategy | 1- Critical | 7.5 |  | 2012 | 50 | NPRR365 | PPL | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | R4 | Initiation |  | <$5k |  |  | $110k-$120k | [7 empty] | Jan 2012 | Aug 2012 | ERCOT | Revises the deadline for ERCOT approval of Resource Outages from an 8-day notice to a 90-day notice while aligning the new Resource Outage timelines to match those of Transmission Outages | 1 - Grid Reliability | 1.3 Operational readiness | NPRR327
Business Strategy | 1- Critical | 8.4 |  | 2012 | 60 | NPRR348 | PPL | NPRR348 | Generation Resource Start-Up and Shut-Down Process | R6 | Not Started |  |  |  |  | $115k-$130k | [7 empty] | June 2012 | Dec 2012 | ERCOT | Removes Protocol language concerning the use of the “ONTEST” Resource Status during start-up and shut-down. Language has been added to address the start-up and shut-down processes. | 1 - Grid Reliability | 1.3 Operational readiness
Business Strategy | 1- Critical | 9.45 |  | 2012 | 70 | NPRR322 | PPL | NPRR322 | Real-Time PTP Option Modeling | TBD | Not Started |  |  |  |  | $100k-$105k | [7 empty] | TBD | TBD | Market | Modifies PTP Options in the DAM that have been declared by a NOIE before the DAM execution to be settled in Real-Time and are still held by that NOIE in Real-Time such that they are considered as PTP Obligations for purposes of the DAM model | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 5 | 2012 | 80 |  | PPL |  | TSAT Wind Model | R5 | Not Started |  |  |  |  | $100k-$200k | [7 empty] | Feb 2012 | Oct 2012 | ERCOT | Implementation of wind models in TSAT application | 1 - Grid Reliability | 1.1 Integrate emerging technologies
Business Strategy |  |  | 6 | 2012 | 90 | PRR830 NPRR269 | PPL | PRR830 NPRR269 | Reactive Power Capability Requirement | TBD | Not Started |  |  |  |  | $250k-$450k | [7 empty] | TBD | TBD | ERCOT | Potential project relating to the Reactive Power Capability Requirement of Generation Resources | 1 - Grid Reliability | 1.1 Integrate emerging technologies
Business Strategy |  |  | 7 | 2012 | 100 | NPRR351 | PPL | 012_01 | SCED Look-Ahead Step 1: Pricing | R3 | Planning |  | $60k-$75k |  |  | $500k-$750k |  | 5000000 | $4M-$6M |  |  |  |  | Sept 2011 | June 2012 | Market | Calculate Non-Binding Prices and Basepoints for Initial Research into SCED Look-Ahead and allow Consumers to have a Forward Price Projection | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy |  |  | 8 | 2012 | 110 |  | PPL |  | Facilities Project | n/a | Not Started |  |  |  |  | $1M-$2M | [7 empty] | TBD | TBD | ERCOT | Potential project relating to resolve any facilities issues relating to the Met Center
Business Strategy |  |  | 9 | 2012 | 120 |  | PPL |  | Cyber Security Project #4 | R6 | Not Started |  |  |  |  | $500k-$750k | [7 empty] | Apr 2012 | Dec 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Business Strategy |  |  | 10 | 2012 | 130 |  | PPL |  | Cyber Security Project #5 | R6 | Not Started |  |  |  |  | $500k-$700k |  | 168239 | $150k-$200k |  |  |  |  | Apr 2012 | Dec 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Business Strategy |  |  | 12 | 2012 | 140 | NPRR260 | Pending Board Approval | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | R5 | Not Started |  |  |  |  | $100k-$200k | [7 empty] | Mar 2012 | Oct 2012 | Market | Adds "Independent Market Information System Registered Entity (IMRE)" to Section 2.1 and Section 22, Attachment A | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy | 1- Critical | 9 | 13 | 2012 | 150 | SCR756 | PPL | 010_01 | MarkeTrak Enhancements for 4.0 | R3 off-cycle | Execution |  | $400k-$425k |  |  | $275k-$325k | [7 empty] | July 2011 | June 2012 | PUCT / Market | Enhance MarkeTrak application for new PUCT requirements and other enhancements requested by market participants. Examples: new subtypes for Expedited Switch Rescission and Meter Tampering, improved data validation, and AMS usage parameters | 2 - Manage Markets | 2.7 Retail data provision
Business Strategy | 1- Critical | 9 | 13 | 2012 | 155 | SCR756 | PPL |  | MarkeTrak Upgrade and Enhancements (Phase 2) | TBD | Not Started |  |  |  |  | $500k-$600k | [7 empty] | TBD | TBD | Market | MarkeTrak software upgrade and remaining deliverables from SCR756 | 2 - Manage Markets | 2.7 Retail data provision
Business Strategy |  |  | 15 | 2012 | 160 |  | PPL |  | Planning Site Transition to MIS | R6 | Not Started |  |  |  |  | $80k-$120k | [7 empty] | July 2012 | Dec 2012 | ERCOT | Increase efficiency by consolidating to a single portal and prevent the need to maintain two systems | 1 - Grid Reliability | 1.2 Transmission strategy
Business Strategy |  |  | 16 | 2012 | 170 | NPRR222 | PPL | NPRR222 | Half Hour Start Unit RUC Clawback | R5 | Not Started |  |  |  |  | $15k-$20k | [7 empty] | Aug 2012 | Oct 2012 | Market | Removes RUC Clawback on all Half-Hour Start Units (a) that participate in the DAM and (b) during EEA events. Also changes the RUC Clawback on all Half-Hour Start Units that did not participate in the DAM to 50%. | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 17 | 2012 | 180 |  | PPL |  | Cyber Security Project #6 | R3 | Not Started |  |  |  |  | $150k-$200k |  | 75389 | $50k-$100k |  |  |  |  | Apr 2012 | June 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Business Strategy | 2-High | 12.9 | 18 | 2012 | 190 | NPRR326 | PPL | 013_01 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | R1 | Execution |  | See Parent Project |  |  | See Parent Project | [7 empty] | Jan 2012 | Feb 2012 | ERCOT | Adjusts the calculation of the Real-Time Settlement Point Price for a Resource Node. The adjustment is to remove the Base Point weighting of the Real-Time Locational Marginal Prices (LMPs). | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  | 2012 | 190 | NPRR326 NPRR321 NPRR355 | PPL | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | R1 | Execution |  | $10k-$12k |  |  | $65k-$85k | [7 empty] | Nov 2011 | Feb 2012 | Various | 1st MMS release in 2012 | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 19 | 2012 | 200 | NPRR272 | PPL | NPRR272 | Definition and Participation of Quick Start Generation Resources | R5 | Not Started |  |  |  |  | $145k-$160k | [7 empty] | Aug 2012 | Oct 2012 | Market | Gray-box portion of this NPRR that enhances participation of Quick Start Generation Resources (QSGRs) in SCED | 2 - Manage Markets | 2.1 Resource adequacy
Business Strategy |  |  | 20 | 2012 | 210 | NPRR207 | PPL | NPRR207 | Unit Deselection | R5 | Not Started |  |  |  |  | $50k-$55k | [7 empty] | Aug 2012 | Oct 2012 | Market | Provides that ERCOT may deselect units from Reliability Unit Commitment (RUC) processes | 1 - Grid Reliability | 1.3 Operational readiness
Business Strategy | 2-High | 12.78 |  | 2012 | 220 | SCR761 | PPL | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | R1 | Execution |  |  |  |  | $10k-$15k | [7 empty] | Aug 2011 | Feb 2012 | Market | Requires ERCOT to: • Provide API notification of all republished corrected prices; and • Publish price corrections in XML format using the same XML Schema Definition (XSD) that it is using for regular price publication | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 13.2 |  | 2012 | 230 | NPRR321 | PPL | 013_01 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | R1 | Execution |  | See Parent Project |  |  | See Parent Project | [7 empty] | Nov 2011 | Dec 2011 | Market | Provides the ability for Resources to change the amounts of power in their Energy Offer Curves in the Adjustment Period | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 14.5 |  | 2012 | 240 | NPRR379 | PPL | NPRR379 | EILS Dispatch Sequence and Performance Criteria Upgrades | R5 | Not Started |  |  |  |  | $55k-$65k | [7 empty] | Aug 2012 | Oct 2012 | ERCOT | Improves the operational value of EILS and strengthens and clarifies a number of performance criteria for EILS | 1 - Grid Reliability | 1.3 Operational readiness
Business Strategy | 2-High | 15.4 |  | 2012 | 250 | NPRR314 | PPL | NPRR314 | Requirement to Post Generation Resources Temporal Constraints | R2 | Not Started |  |  |  |  | $32k-$39k | [7 empty] | Feb 2012 | Apr 2012 | Market | Specifies the need for ERCOT to post to the MIS Certified Area the current time since a Generation Resource last went Off-Line (in hours) and the corresponding startup time ERCOT is using for of all Off-Line Generation Resources which may be considered in any RUC process | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 19.5 |  | 2012 | 260 | NPRR395 | PPL | NPRR395 | CRR Auction Offer Award Disclosure | R2 | Initiation |  |  |  |  | $40k-$50k | [7 empty] | Dec 2011 | Apr 2012 | Market | Adds a requirement for ERCOT to post CRR Auction offer awards following each CRR Auction in the exact fashion CRR Auction bid awards are currently posted on the MIS Public Area | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 20.5 |  | 2012 | 270 | NPRR357 | PPL | NPRR357 | Revisions to Collateral Requirements Concerning CRR Auctions | R3 | Not Started |  |  |  |  | $95k-$105k | [7 empty] | Jan 2012 | June 2012 | Market | Proposes revisions to collateral requirements for CRR Auctions including a pre-CRR Auction screening process to determine the maximum potential exposure of each CRR Account Holder | 2 - Manage Markets | 2.5 Credit Requirements
Business Strategy | 2-High | 30 |  | 2012 | 280 | NPRR313 | PPL | NPRR313 | Updating the Term Resource Plan to Current Operating Plan / Availability Plan | R2 | Not Started |  |  |  |  | $80k-$85k | [7 empty] | Feb 2012 | Apr 2012 | Market | Replaces the term “Resource Plan” with the term “Current Operating Plan” or “Availability Plan”. Also adds a Black Start capable status indicator to the Availability Plan. | 1 - Grid Reliability | 1.3 Operational readiness
Business Strategy | 2-High | 31 |  | 2012 | 290 | NPRR354 | PPL | NPRR354 | Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment | R6 | Not Started |  |  |  |  | $100k-$110k | [7 empty] | June 2012 | Dec 2012 | Market | Clarifies the performance criteria for Non-Spinning Reserve (Non-Spin) Service deployments, adds language for provision of a Non-Spin deployment flag to QSEs via ICCP, and adds a requirement for XML notification to all QSEs when Non-Spin is deployed | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy | 2-High | 32 |  | 2012 | 300 | NPRR355 | PPL | 013_01 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | R1 | Execution |  | See Parent Project |  |  | See Parent Project | [7 empty] | Dec 2011 | Feb 2012 | ERCOT | Removes the energy-weighting in the current calculation for the Real-Time Settlement Point Price (RTSPP) for a Load Zone | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 32.5 |  | 2012 | 310 | NPRR360 | PPL | NPRR360 | Summary Report of HDL and LDL | R5 | Not Started |  |  |  |  | $30k-$35k | [7 empty] | May 2012 | Oct 2012 | Market | Creates a new posting for the sum of HDL and the sum of LDL and any Generation Resource instances of manual overrides of HDL or LDL to the MIS Public Area after every SCED run | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 32.6 |  | 2012 | 320 | NPRR382 | PPL | NPRR382 | Verbal RUC Committed or Decommitted Resources Report | R3 | Not Started |  |  |  |  | $25k-$30k | [7 empty] | Mar 2012 | June 2012 | Market | Creates two new reports on the MIS Secure Area for verbal Reliability Unit Commitment (RUC) commitments/decommitments | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy | 2-High | 32.7 |  | 2012 | 330 | NPRR383 | PPL | NPRR383 | Unconfirmed Trades Reports | R3 | Not Started |  |  |  |  | $25k-$30k | [7 empty] | Mar 2012 | June 2012 | Market | Creates a new report for unconfirmed trades on the MIS Certified Area | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy | 2-High | 33 |  | 2012 | 340 | NPRR359 | PPL | NPRR359 | Monthly TDSP Load Report | R3 | Not Started |  |  |  |  | $15k-$20k | [7 empty] | Mar 2012 | June 2012 | Market | Creates a new secure report to provide aggregate Load data for TSPs and DSPs in a monthly posting | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 34 |  | 2012 | 350 | NPRR361 | PPL | NPRR361 | Real-Time Wind Power Production Data Transparency | R2 | Not Started |  |  |  |  | $10k-$15k | [7 empty] | Jan 2012 | Apr 2012 | Market | Adds a new public report that provides, on both a system-wide and regional basis (West and North, South and Houston), the five-minute actual wind power production for a rolling historical 60-minute period | 2 - Manage Markets | 2.2 Market Design
Business Strategy | 2-High | 35 |  | 2012 | 360 | NPRR377 | PPL | NPRR377 | Alternate Inputs to Base Point Deviation Charge | TBD | Not Started | [12 empty] | TBD | TBD | ERCOT | Aligns the Adjusted Aggregated Base Points (AABP) formula with the inputs to the GREDP measure | 2 - Manage Markets | 2.2 Market Design | NPRR327
Business Strategy |  |  | 21 | 2013 | 370 |  | PPL |  | Certified Data Product Subscription Standardization | n/a | Not Started | [6 empty] | 100000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Standardize ERCOT’s production and posting of certified market extracts using Extract Subscriber where it can be applied | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 22 | 2013 | 380 |  | PPL |  | EPS Metering DB Redesign | n/a | Not Started | [6 empty] | 360000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | Redesign of in-house developed application to allow for more robust functions and reporting | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 23 | 2013 | 390 | NPRR181 | Pending TAC Approval | NPRR181 | FIP Definition Revision | n/a | Not Started | [6 empty] | 210000 | $100k-$250k |  |  |  |  | TBD | TBD | Market | Revises the definition of Fuel Index Price (FIP) to correctly account for the timing difference between ERCOT’s application of the FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900). | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 24 | 2013 | 400 | NPRR210 | PPL | NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | n/a | Not Started | [6 empty] | 50000 | $50k-$100k |  |  |  |  | TBD | TBD | Market | Changes the wind forecasting methodology to use a 50% probability of exceedance calculation instead of an 80% for RUC considerations | 1 - Grid Reliability | 1.1 Integrate emerging technologies
Business Strategy |  |  | 25 | 2013 | 410 | NPRR241 | PPL | NPRR241 | AIL Calculation & Credit Reports Publish Corrections | n/a | Not Started | [6 empty] | 120000 | $100k-$250k |  |  |  |  | TBD | TBD | Market | Changes the format of various credit reports from XLS to XML | 2 - Manage Markets | 2.5 Credit Requirements
Business Strategy |  |  | 26 | 2013 | 420 | NPRR256 | PPL | NPRR256 | Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards | n/a | Not Started | [6 empty] | 135000 | $100k-$250k |  |  |  |  | TBD | TBD | Market | Revises the method of calculating GREDP | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 27 | 2013 | 430 | NPRR240 | PPL | NPRR240 | Proxy Energy Offer Curve | n/a | Not Started | [6 empty] | 27000 | <$50k |  |  |  |  | TBD | TBD | Market | Marks Energy Offer Curves that were constructed in whole or in part with proxy Energy Offer Curves in all ERCOT postings or references to the energy offer | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  | 28 | 2013 | 440 |  | PPL |  | Incremental Update Capability - Phase 2 | n/a | Not Started | [6 empty] | 2000000 | $2M-$4M | 2000000 | $2M-$4M |  |  | TBD | TBD | ERCOT | Second phase of project to provide incremental update capability to all production systems for all model related data | 1 - Grid Reliability | 1.2 Transmission strategy
Business Strategy |  |  | 29 | 2013 | 450 |  | PPL |  | MP Online Data Entry - Ph 2 | n/a | Not Started | [6 empty] | 1000000 | $1M-$2M |  |  |  |  | TBD | TBD | ERCOT | Second phase of project to improve and automate the process used to update the RARF | 1 - Grid Reliability | 1.4 Generation resource interconnection
Business Strategy |  |  | 30 | 2014 | 460 |  | PPL |  | MP Online Data Entry - Ph 3 | n/a | Not Started | [8 empty] | 1000000 | $1M-$2M |  |  | TBD | TBD | ERCOT | Final phase of project to improve and automate the process used to update the RARF | 1 - Grid Reliability | 1.4 Generation resource interconnection
Business Strategy |  |  |  | 2012 | 470 | NPRR315 | Rejected | NPRR315 | Revision of Responsive Reserve Measure to High Emergency Limit | TBD | Not Started | [12 empty] | TBD | TBD | Market | Changes Responsive Reserve (RRS) Service 20% limit to check against High Emergency Limit (HEL) instead of High Sustained Limit (HSL) | 2 - Manage Markets | 2.1 Resource adequacy
Business Strategy |  |  |  | 2012 | 480 | NPRR327 | Pending TAC Approval | NPRR327 | State Estimator Data Redaction Methodology | TBD | Not Started | [12 empty] | TBD | TBD | Market | Defines a redaction methodology for the posting of State Estimator data | 1 - Grid Reliability | 1.2 Transmission strategy | NPRR327
Business Strategy |  |  |  | 2012 | 490 | NPRR334 | Pending TAC Approval | NPRR334 | Incorporate Resource Limit for the Amount of Regulation Service that may be Provided from a Generation Resource During any Operating Hour | TBD | Not Started | [12 empty] | TBD | TBD | Market | Incorporate a percentage requirement limiting the amount of Regulation Service that Generation Resources may provide | 2 - Manage Markets | 2.1 Resource adequacy
Business Strategy |  |  |  | 2012 | 500 | NPRR340 | Pending TAC Approval | NPRR340 | Introduction and Definition of Duration-Limited Resources | TBD | Not Started | [12 empty] | TBD | TBD | Market | Defines Duration-Limited Resource (DLR) and amends the General Capacity Testing Requirements to reflect operational characteristics of this type of Resource | 2 - Manage Markets | 2.3 Load participation
Business Strategy |  |  |  |  | 530 | NPRR385 | Pending PRS Approval | NPRR385 | Security Violation Analysis and Reporting and Negative Price Floor | TBD | Not Started | [12 empty] | TBD | TBD | Market | Adds review, analysis and reporting requirements to the NSA process to provide Market Participants with information related to the causes of recurring security violations and possible solutions developed by ERCOT to address those violations. Additionally, adds an administrative Real-Time Settlement Point Price floor of negative $251/MWh for Resource Nodes, Hubs and Load Zones. | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  |  | 540 | NPRR393 | Pending PRS Approval | NPRR393 | SCED Constraint Management Transparency | TBD | Not Started | [12 empty] | TBD | TBD | Market | Creates a reporting requirement to provide transparency into SCED constraint management decisions | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  |  | 550 | NPRR419 | Pending PRS Approval | NPRR419 | Revise Real-Time Energy Imbalance and RMR Adjustment Charge | TBD | Not Started | [12 empty] | TBD | TBD | ERCOT | Provides market volumetric imbalance calculations and will achieve revenue neutrality for QSEs with RMR Units | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  |  | 560 | NPRR425 | Pending PRS Approval | NPRR425 | Creation of a Wind Resource Group for GREDP and Base Point Deviation Evaluation | TBD | Not Started | [12 empty] | TBD | TBD | ERCOT | Provides that WGRs meeting registration requirements will be evaluated for GREDP and Base Point Deviation as groups of WGRs rather than individual WGRs | 1 - Grid Reliability | 1.1 Integrate emerging technologies
Business Strategy |  |  |  |  | 570 | SCR767 | Pending PRS Approval | SCR767 | Non-Spin Deployment Criteria | TBD | Not Started | [12 empty] | TBD | TBD | ERCOT | Adds the ability to deploy all On-Line Non-Spinning Reserve (Non-Spin) | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  |  | 580 | SCR768 | Pending PRS Approval | SCR768 | Automatic Non-Spin Redeployment and Deployment Based on Resource Availability | TBD | Not Started | [12 empty] | TBD | TBD | ERCOT | Modifies the MMS Automatic Redeployment function such that it accounts for the delay involved in deployment of Off-Line Non-Spinning Reserve (Non-Spin) Resources | 2 - Manage Markets | 2.2 Market Design
Business Strategy |  |  |  | 2012 | 590 | NPRR407 | Pending TAC Approval | NPRR407 | Credit Monitoring Posting Requirements | TBD | Not Started | [12 empty] | TBD | TBD | Market | Adds requirements for ERCOT to post to the MIS Certified Area, the parameters used to calculate Market Participants’ Available Credit Limits (ACLs) used in multiple market processes
Business Strategy |  |  |  | 2012 | 600 | NPRR422 | Pending TAC Approval | NPRR422 | Public DAM Shift Factors | TBD | Not Started | [12 empty] | TBD | TBD | Market | Creates a new report to provide Day-Ahead Shift Factors on the MIS Public Area
Business Strategy |  |  |  | 2012 | 610 |  | PPL |  | CIM Upgrade for NMMS | TBD | Initiation |  |  |  |  | $30k-$50k | [7 empty] | Dec 2011 | TBD | ERCOT | Update ERCOT NMMS model schema from CIM 10 to CIM 14 to be consistent with industry standards | 1 - Grid Reliability | 1.2 Transmission strategy
Business Strategy | 1- Critical | 9.21 |  | 2012 | 620 | SCR764 | PPL | SCR764 | Public Access to Select MIS Dashboards | R1 | Execution |  |  |  |  | $15k-$20k | [7 empty] | June 2011 | Feb 2012 | Market | System changes to allow public access to a graphical view of non-confidential system conditions and pricing information for a specific set of Market Information System (MIS) Dashboards
Efficiencies / Enhancements | 2-High | 23 | 16 | 2011 | 1 |  | PPL | 004_01 | Cyber Security Project #3 | R1 | Execution |  | $250k-$500k |  |  | $75k-$100k | [7 empty] | Apr 2011 | Mar 2012 | ERCOT | Enhance a specific area of ERCOT's cyber security capability | 3 - Compliance | 3.5 Security initiatives
Efficiencies / Enhancements | 2-High | 25 |  | 2011 | 2 |  | PPL | 007_01 | Cyber Security Facilities Remodeling | n/a | Execution |  | $200k-$250k | [10 empty] | June 2011 | Dec 2011 | ERCOT | Facilities buildout for consolidation of Cyber Security functions in one area
Efficiencies / Enhancements | 2-High | 25 |  | 2011 | 3 |  | PPL | 007_01 | Human Resources Facilities Remodeling | n/a | Execution |  | $200k-$250k | [10 empty] | June 2011 | Dec 2011 | ERCOT | Facilities buildout for consolidation of HR and Legal functions in one area
Efficiencies / Enhancements | 2-High | 27 |  | 2011 | 4 |  | PPL | 007_01 | Shipping/Receiving Remodeling | n/a | Execution |  | $200k-$250k | [10 empty] | June 2011 | Dec 2011 | ERCOT | Remodel portions of Blue Building to allow for a secure shipping and receiving area
Efficiencies / Enhancements |  |  |  | 2011 | 5 |  | PPL | 015_01 | Outage Capacity Calculation Tool | TBD | Planning |  | $15k-$25k |  |  | $30k-$50k | [7 empty] | Nov 2011 | TBD | ERCOT | Provide resource outage data for both daily operations and future outage coordination studies | 1 - Grid Reliability | 1.3 Operational readiness
Efficiencies / Enhancements |  |  | 1 | 2012 | 10 |  | PPL |  | Incremental Update Capability - Phase 1 | n/a | Initiation |  |  |  |  | $100k-$160k | [7 empty] | Dec 2011 | TBD | ERCOT | Initial phase of project to provide incremental update capability to all production systems for all model related data | 1 - Grid Reliability | 1.2 Transmission strategy
Efficiencies / Enhancements |  |  | 2 | 2012 | 20 |  | PPL |  | MP Online Data Entry - Ph 1 | R6 | Not Started |  |  |  |  | $750k-$850k | [7 empty] | TBD | Dec 2012 | ERCOT | Initial phase of project to improve and automate the process used to update the RARF | 1 - Grid Reliability | 1.4 Generation resource interconnection
Efficiencies / Enhancements |  |  | 3 | 2012 | 30 |  | PPL |  | CMS and MIR Replacement | R6 | Not Started |  | $200k-$250k |  |  | $200k-$300k |  | 750000 | $500k-$1M |  |  |  |  | Jan 2012 | Dec 2012 | ERCOT | Replace the two existing content management solutions with a single enterprise-level solution | 2 - Manage Markets | 2.2 Market Design
Efficiencies / Enhancements |  |  | 4 | 2012 | 40 |  | PPL |  | ERCOT Website Enhancements - 2012 | R1, R2, R3, R4, R5, R6 | Not Started |  |  |  |  | $250k-$300k | [7 empty] | Jan 2012 | Dec 2012 | ERCOT | 2012 enhancements to ERCOT.com website | 4 - External Relations | 4.1 Stakeholder communication
Efficiencies / Enhancements |  |  | 5 | 2012 | 50 |  | PPL |  | Macomber Map NERC SA/Compliance Enhancements | R6 | Not Started |  |  |  |  | $250k-$300k | [7 empty] | Jan 2012 | Dec 2012 | ERCOT | Enhance the Macomber Map in order to further address NERC control room situational awareness requirements and operational requirements in outage evaluation, planning, and training areas | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 6 | 2012 | 60 |  | PPL |  | IGRID Implementation | R2 | Not Started |  |  |  |  | $30k-$50k | [7 empty] | Jan 2012 | Apr 2012 | ERCOT | Combine various supplemental operator tools into a set of integrated dashboards | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 7 | 2012 | 70 |  | PPL |  | Contingency Functionality Enhmts. | n/a | Not Started |  |  |  |  | $30k-$50k | [7 empty] | TBD | TBD | ERCOT | Enhance NMMS capabilities to allow business owners to submit, via NOMCR, contingency group configurations with a higher level of specificity | 1 - Grid Reliability | 1.2 Transmission strategy
Efficiencies / Enhancements |  |  | 8 | 2012 | 80 |  | PPL |  | SMTNET Improvements | R5 | Not Started |  |  |  |  | $40k-$60k | [7 empty] | Feb 2012 | Oct 2012 | ERCOT | SMTNET time point improvements to troubleshoot time points | 1 - Grid Reliability | 1.3 Operational readiness
Efficiencies / Enhancements |  |  | 9 | 2012 | 90 |  | PPL |  | MP Communications Tool | TBD | Not Started |  |  |  |  | $50k-$75k | [7 empty] | TBD | TBD | ERCOT | Create a tool to be placed in Market Participant control rooms to ensure their receiving continual high-level status information (e.g., EEA status), and provide a primary means of ERCOT providing (and confirming receipt of) instructions | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 10 | 2012 | 100 |  | PPL | 011_01 | ERCOT Mobile | TBD | Planning |  | $15k-$20k |  |  | $120k-$140k | [7 empty] | Nov 2011 | TBD | ERCOT | Create a smart-device application for public consumption, showing a high-level view of system status, offering user-approved messaging for conservation calls, and creating an interface for ERCOT public relations to disseminate information | 4 - External Relations | 4.3 Grid Alert outreach
Efficiencies / Enhancements |  |  | 11 | 2012 | 110 |  | PPL |  | OA Grid Health Operator View | R4 | Not Started |  |  |  |  | $30k-$50k | [7 empty] | Jan 2012 | Aug 2012 | ERCOT | Give operators a view into overall grid health that incorporates a variety of operational parameters into a single graphical dashboard interface | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 12 | 2013 | 120 |  | PPL |  | Secure File Transfer | n/a | Not Started | [6 empty] | 50000 | $50k-$100k |  |  |  |  | TBD | TBD | ERCOT | Upgrade enterprise capability to provide a secure file transfer capability in appropriate situations | 3 - Compliance | 3.5 Security initiatives
Efficiencies / Enhancements |  |  | 13 | 2013 | 130 |  | PPL |  | EMIL and View by Protocol Enhancements | n/a | Not Started | [6 empty] | 100000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Replacement of View By Protocol application with an interactive user interface of EMIL data for market and capability for downloading | 2 - Manage Markets | 2.2 Market Design
Efficiencies / Enhancements |  |  | 14 | 2013 | 140 |  | PPL |  | Replace N2N System | n/a | Not Started | [6 empty] | 52000 | $50k-$100k |  |  |  |  | TBD | TBD | ERCOT | Upgrade component of IT infrastructure that will provide for more efficient system access control | 3 - Compliance | 3.5 Security initiatives
Efficiencies / Enhancements |  |  | 15 | 2013 | 150 |  | PPL |  | Contract Mgmt Software | n/a | Not Started | [6 empty] | 175000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Replace the in-house developed Vendor Contract Management database with a more adequate contract management solution | 3 - Compliance | 3.1 Culture of compliance
Efficiencies / Enhancements |  |  |  | 2012 | 155 |  | PPL | 016_01 | ADP-IDM Interface | TBD | Planning |  | $20k-$30k |  |  | $100k-$120k | [7 empty] | Nov 2011 | TBD | ERCOT | Eliminate duplicate data entry between corporate applications by creating an interface to provide staffing and org. hierarchy info
Efficiencies / Enhancements |  |  | 17 | 2013 | 160 |  | PPL |  | Voice Analytics | n/a | Not Started | [6 empty] | 170000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Software to eliminate the manual work of searching through hundreds of recorded audio files and the manual effort of transcribing those files that may be needed for regulatory or compliance related matters | 3 - Compliance | 3.1 Culture of compliance
Efficiencies / Enhancements |  |  | 18 | 2013 | 170 |  | PPL |  | Control Room AV Wall Upgrade | n/a | Not Started | [6 empty] | 1600000 | $1M-$2M |  |  |  |  | TBD | TBD | ERCOT | Replace the video wall system located in TCC1 with a display system matching the installation in the Bastrop Control Center | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 19 | 2013 | 180 |  | PPL |  | Control Room Console Upgrade | n/a | Not Started | [6 empty] | 300000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | Replace existing TCC1 control room consoles and add 5th console to be consistent with Alternate Control Room | 1 - Grid Reliability | 1.5 Operator visualization tools
Efficiencies / Enhancements |  |  | 20 | 2013 | 190 |  | PPL |  | Control Room Electrical/Mechanical Upgrade | n/a | Not Started | [6 empty] | 300000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | Provide enhanced electrical power redundancy to TCC1 Control Room | 1 - Grid Reliability | 1.3 Operational readiness
Efficiencies / Enhancements |  |  | 21 | 2013 | 200 |  | PPL |  | OTS Enhancements | n/a | Not Started | [6 empty] | 100000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Provide improvements and new tools that will enable the trainers, who are playing the role of 13 TOs and 30+ QSEs at any given time, to respond in more of a real-world timeframe | 5 - People | 5.3 Training
Efficiencies / Enhancements |  |  | 22 | 2013 | 210 |  | PPL |  | ERCOT Website Enhancements - 2013 | n/a | Not Started | [6 empty] | 250000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | Future year enhancements to ERCOT.com website | 4 - External Relations | 4.1 Stakeholder communication
Efficiencies / Enhancements |  |  | 23 | 2014 | 220 |  | PPL |  | ERCOT Website Enhancements - 2014 | n/a | Not Started | [8 empty] | 250000 | $250k-$500k |  |  | TBD | TBD | ERCOT | Future year enhancements to ERCOT.com website | 4 - External Relations | 4.1 Stakeholder communication
Efficiencies / Enhancements |  |  | 24 | 2015 | 230 |  | PPL |  | ERCOT Website Enhancements - 2015 | n/a | Not Started | [10 empty] | 250000 | $250k-$500k | TBD | TBD | ERCOT | Future year enhancements to ERCOT.com website | 4 - External Relations | 4.1 Stakeholder communication
Regulatory |  |  | 2 | 2012 | 10 |  | PPL |  | CTFC Compliance | TBD | Not Started |  | <$50k |  |  | $150k-$250k | [7 empty] | TBD | TBD | ERCOT | Funding reserved for projects relating to CFTC compliance | 2 - Manage Markets | 2.4 CFTC Requirements
Regulatory | 1- Critical | 9.44 |  | 2012 | 10 | NPRR347 NPRR400 | PPL | 014_01 | Implementation of NPRR347 and NPRR400 | TBD | Planning |  | <$50k |  |  | $660k-$715k | [7 empty] | Nov 2011 | TBD | ERCOT | CFTC, Single Daily Settlement Invoice | 2 - Manage Markets | 2.4 CFTC Requirements
Regulatory |  |  | 3 | 2012 | 20 |  | PPL | 009-01 | Compliance Software Tool | R1 | Execution |  | $375k-$425k |  |  | $110k-$140k | [7 empty] | July 2011 | Feb 2012 | ERCOT | Purchase and implement Security and Reliability Compliance Business Enterprise Tracking and Support Software | 3 - Compliance | 3.1 Culture of compliance
Regulatory |  |  |  | 2012 | 40 |  | PPL |  | Quality Training Database | TBD | Initiation |  |  |  |  | $50k-$55k | [7 empty] | Dec 2011 | TBD | ERCOT | Implementation of tool for compliance with NERC PER-005 (System Personnel Training)
Stabilization | 2-High | 10.5 |  | 2011 | 3 |  | Post Go-Live | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | R2 off-cycle | Execution |  | $80k-$100k | [10 empty] | July 2011 | Apr 2012 | ERCOT | Update the RARF and RARF Hub database to increase the data collected for Wind and add necessary data section for Solar PV and Duration Limited Resources - 2011 Stabilization-funded portion
Stabilization | 1- Critical | 0.1 |  | 2011 | 10 |  | Post Go-Live |  | Nodal Stabilization | n/a | Execution |  | $10M-$12M | [10 empty] | Dec 2010 | Dec 2011 | Nodal Post Go-Live | Evaluate and remediate ERCOT Nodal Operational Issues including higher than normal: production outages, issue analysis, software defect remediation, stakeholder support, and request for information volumes
Stabilization | 1- Critical | 0.11 |  | 2011 | 20 | NPRR302 | Post Go-Live | NPRR302 | Correct Fuel Type Language for Mitigated Offer Cap | n/a | Complete |  | <$5k | [10 empty] | Jan 2011 | Mar 2011 | Market | Revises the language for the Mitigated Offer Cap to eliminate use of the Fuel Oil Price (FOP) in the calculation.
Stabilization | 1- Critical | 0.12 |  | 2011 | 30 |  | Post Go-Live |  | Planning Model | n/a | Complete | [12 empty] | 2010 | Apr 2011 | Nodal Post Go-Live | Stabilization effort to take Option 2 to go-live
Stabilization | 1- Critical | 3.5 |  | 2011 | 40 | SCR760 | Post Go-Live | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | n/a | Execution |  | $500k-$600k | [10 empty] | Apr 2011 | June 2012 | Market | Proposes changes to the Information Model Manager and Topology Processor to fix a number of deficiencies with the proposed Annual Planning Model creation process.
Stabilization | 1- Critical | 8.5 |  | 2011 | 50 | NPRR258 | Post Go-Live | NPRR258 | Sync with PRR824 and PRR833 | n/a | Complete |  | $55k-$60k | [10 empty] | Aug 2011 | Oct 2011 | Parking Deck | PARKING DECK - Synchronizes the Nodal Protocols with PRR824, Primary Frequency Response from WGRs, and PRR833, Primary Frequency Response Requirement from Existing WGRs
Stabilization | 1- Critical | 9.2 |  | 2011 | 60 | NPRR329 | Post Go-Live | NPRR329 | Security Classification Changes for Extracts/Reports | n/a | Complete |  | $5k-$10k | [10 empty] | Apr 2011 | May 2011 | Market | Changes the security classification to public for extracts/reports that are currently classified in the Nodal Protocols as secure.
Stabilization | 1- Critical | 9.21 |  | 2011 | 70 | SCR764 | Post Go-Live | SCR764 | Public Access to Select MIS Dashboards | n/a | Execution |  | $60k-$80k | [10 empty] | June 2011 | Dec 2011 | Market | System changes to allow public access to a graphical view of non-confidential system conditions and pricing information for a specific set of Market Information System (MIS) Dashboards
Stabilization | 1- Critical | 9.22 |  | 2011 | 80 | NPRR350 | Post Go-Live | NPRR350 | Change to the Security Classification of the System Ancillary Service Capacity Monitor Dashboard | n/a | Complete |  | $5k-$10k | [10 empty] | June 2011 | Aug 2011 | Market | Changes the posting category of items that make up the System Ancillary Service Capacity Monitor Dashboard from Market Information System (MIS) Secure Area to MIS Public Area
Stabilization | 1- Critical | 9.25 |  | 2011 | 90 | SCR765 | Post Go-Live | SCR765 | Public Aggregated Wind Dashboard | n/a | Closing |  | $37k-$45k | [10 empty] | Aug 2011 | Dec 2011 | Market | Provides a public graphical representation of the amount of wind generation forecasted and produced in the ERCOT Transmission Grid for all markets
Stabilization | 1- Critical | 9.3 |  | 2011 | 100 | NPRR339 | Post Go-Live | NPRR339 | Modifications to Heuristic Rules to Determine LMP at De-energized Electrical Bus and Treatment of CRR Offers at De-energized Settlement Points | n/a | Complete |  | <$100k | [10 empty] | June 2011 | Sept 2011 | ERCOT | (a) Extends the heuristic rules to determine the Locational Marginal Price (LMP) at de-energized Electrical Buses; and (b) Changes the treatment of Congestion Revenue Right (CRR) offers when either the source or sink Settlement Point is de-energized in the DAM.
Stabilization | 1- Critical | 9.41 |  | 2011 | 110 | NPRR285 | Post Go-Live | NPRR285 | Generation Resource Base Point Deviation Charge Corrections | n/a | Complete |  | $30k-$40k | [10 empty] | Apr 2011 | May 2011 | Market | Various corrections to the calculation of Generation Resource Base Point Deviation Charges
Stabilization | 1- Critical | 9.42 |  | 2011 | 120 | NPRR282 | Post Go-Live | NPRR282 | Dynamic Ramp Rates Use in SCED | n/a | Complete |  | $18k-$22k | [10 empty] | May 2011 | July 2011 | Market | Revisions intended to result in more reasonable Dispatch of Generation Resources when a telemetered Base Point requires the Resource to employ technologies that in turn change the Resource’s ramp rate.
Stabilization | 1- Critical | 9.43 |  | 2011 | 130 |  | Post Go-Live |  | Deferred Defects and Workaround Processes | n/a | Execution |  | $1.5M-$2.0M | [10 empty] | Dec 2010 | Dec 2011 | Nodal Post Go-Live | Evaluate and remediate the priority 3 defects that were deferred from the Nodal Project
Stabilization | 1- Critical | 9.46 |  | 2011 | 140 | NPRR376 | Post Go-Live | NPRR376 | CRR Volume Limitation Enhancements | n/a | Complete |  | $50k-$55k | [10 empty] | July 2011 | Sept 2011 | Market | Establishes that CRR Account Holders are not included in the CRR transaction volume limitation process if they do not own open CRR positions or have credit allocated to the CRR Auction
Stabilization | 2-High | 9.5 |  | 2011 | 150 | NPRR307 | Post Go-Live | NPRR307 | Change SASM Offer Procedures | n/a | Complete |  | $10k-$12k | [10 empty] | Apr 2011 | May 2011 | Market | Deletes the requirement of valid SASM offers to be at or below the value of the offers in the Day Ahead Market (DAM)
Stabilization | 2-High | 9.5 |  | 2011 | 160 | NPRR341 | Post Go-Live | NPRR341 | Remove Ancillary Service Offers from SASM that do not Meet the Lead Time | n/a | Complete |  | $10k-$15k | [10 empty] | June 2011 | June 2011 | ERCOT | Proposes to modify input data processing of Supplemental Ancillary Services Markets (SASMs) to remove offers that do not meet the lead time for each hour in the SASM study period.
Stabilization | 2-High | 12.75 |  | 2011 | 170 | NPRR323 | Post Go-Live | NPRR323 | Correct DAM Credit Exposure Language and Enable Qualified Expiring CRRs to Offset PTP Bid Exposure | n/a | Complete |  | $375k-$475k | [10 empty] | Apr 2011 | Aug 2011 | Market | Corrects discrepancies between current Protocol language and implemented DAM credit exposure calculations and better reflects the risk and costs of DAM participation.
Stabilization | 2-High | 12.76 |  | 2011 | 180 | NPRR310 | Post Go-Live | NPRR310 | Expand Output Schedule Acceptable Range to Include HSL and LSL | n/a | Execution |  | $10k-$15k | [10 empty] | Aug 2011 | Dec 2011 | Market | Updates the criteria by which Output Schedules are deemed valid to include Output Schedules that are equal in value to the Resource High Sustained Limit (HSL) and Low Sustained Limit (LSL).
Stabilization | 2-High | 12.77 |  | 2011 | 190 | SCR762 | Post Go-Live | SCR762 | Enable a Single Step Cancel/Resubmit of Trades | n/a | Complete |  | $25k-$30k | [10 empty] | Aug 2011 | Oct 2011 | ERCOT | Modifies MMS such that submission of a trade that has already been confirmed causes the confirmed trade to be overwritten by the new submission and marked as unconfirmed
Stabilization | 2-High | 12.78 |  | 2011 | 200 | SCR761 | Post Go-Live | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | R1 | Execution |  | $40k-$48k | [10 empty] | Aug 2011 | Feb 2012 | Market | Requires ERCOT to: • Provide API notification of all republished corrected prices; and • Publish price corrections in XML format using the same XML Schema Definition (XSD) that it is using for regular price publication
Stabilization | 2-High | 12.79 |  | 2011 | 210 | SCR763 | Post Go-Live | SCR763 | Modify COP Validation Rule for RRS | n/a | Execution |  | $10k-$15k | [10 empty] | Aug 2011 | Dec 2011 | ERCOT | Modifies the existing COP validation to use the highest Emergency Ramp Rate value from the registered Emergency Ramp Rate curve as an input to the COP validation check of Responsive Reserve (RRS) responsibility
Stabilization | 2-High | 12.8 |  | 2011 | 220 | NPRR320 | Post Go-Live | NPRR320 | Minimum PTP Option Bid and Settlement | n/a | Execution |  | $110k-$120k | [10 empty] | June 2011 | Nov 2011 | Market | Enhance the CRR system to include Minimum Bid and Award fees. Enhance Settlements system and related integration to account for the new fees. Update statements, invoices, and extracts.
Stabilization | 2-High | 13 |  | 2011 | 230 | NPRR290 | Post Go-Live | NPRR290 | ERCOT Publication of DAM PSS/E Files | n/a | Execution |  | $25k-$30k | [10 empty] | July 2011 | Dec 2011 | Market | Requires ERCOT to publish certain data files in Power System Simulator for Engineering (PSS/E) format
Stabilization | 2-High | 13.1 |  | 2011 | 240 | NPRR343 | Post Go-Live | NPRR343 | CRR Bid and PTP Obligation Bid Criteria Change | n/a | Execution |  | $300k-$350k | [10 empty] | June 2011 | Dec 2011 | ERCOT | Remove the ability to bid for CRRs in the CRR auction or bid for PTP Obligations in the DAM that exist entirely within a station.
Stabilization | 2-High | 14 |  | 2011 | 250 | NPRR293 | Post Go-Live | NPRR293 | Requirement to Post PTP Obligation Quantities Awarded in DAM | n/a | Complete |  | $12k-$15k | [10 empty] | Apr 2011 | May 2011 | Market | Adds language to specify the need for ERCOT to post quantities of PTP Obligations that were awarded in the Day-Ahead Market (DAM).
Stabilization | 2-High | 14 |  | 2011 | 260 | NPRR303 | Post Go-Live | NPRR303 | Requirement to Post PTP Options Cleared in the DAM or Taken to Real Time | n/a | Complete |  | <$5k | [10 empty] | Apr 2011 | May 2011 | Market | Requires ERCOT to post quantities of Point-to-Point (PTP) Options and PTP Options with Refund that were not cleared in the Day-Ahead Market (DAM) and taken to Real-Time for Settlement
Stabilization | 2-High | 15 |  | 2011 | 270 |  | Post Go-Live |  | Parking Deck Initiatives | n/a | Execution | [12 empty] | Feb 2011 | Mar 2012 | Nodal Post Go-Live | 1) Implementation of Parking Deck items that can be fit into the planned 2011 release schedule 2) Planning the first major Nodal system enhancement release (Nodal 2.0)
Stabilization | 2-High | 15.1 |  | 2011 | 280 | NPRR208 | Post Go-Live | NPRR208 | Registration & Settlement of Distributed Generation (DG) <1 MW | n/a | Complete |  | $5k-$10k | [10 empty] | Apr 2011 | Aug 2011 | Parking Deck | Incorporate PRR756 changes, clarify registration requirements for DG to allow all DG to be settled as negative Load, and raise the threshold for DG that can be settled as negative Load.
Stabilization | 2-High | 15.2 |  | 2011 | 290 | NPRR251 | Post Go-Live | NPRR251 | Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | n/a | Execution |  | $10k-$15k | [10 empty] | Sept 2011 | Dec 2011 | Parking Deck | Implement grey boxed language for reporting requirements in Sections 18.6.1 and 18.6.2, to be implemented post Nodal Implementation
Stabilization | 2-High | 15.3 |  | 2011 | 300 | NPRR316 | Post Go-Live | NPRR316 | Negative Self-Arranged Ancillary Services Quantity | n/a | Execution |  | $15k-$20k | [10 empty] | June 2011 | Dec 2011 | Market | Allows QSEs to enter a negative value for Ancillary Service self-arrangement.
Stabilization | 2-High | 16 |  | 2011 | 310 |  | Post Go-Live |  | Decommissioning Efforts | n/a | Execution |  | $275k-$325k | [10 empty] | Jan 2011 | Dec 2011 | Nodal Post Go-Live | The complete decommission (hardware, software, network, data, instances) of all systems that will no longer be used after Nodal Go-Live.
Stabilization | 2-High | 17 |  | 2011 | 320 |  | Post Go-Live |  | Program Risk Items | n/a | Execution |  | $1M-$2M | [10 empty] | Mar 2011 | Dec 2011 | Nodal Post Go-Live | Post Nodal Audit Phase 1 and 2
Stabilization | 2-High | 19 |  | 2011 | 330 |  | Post Go-Live |  | Hardware and Software Systems License & Maintenance | n/a | Execution |  | $6M-$7M | [10 empty] | Jan 2011 | Dec 2011 | Nodal Post Go-Live | 1st year of hardware and software systems licensing and maintenance costs for Nodal systems
Stabilization | 2-High | 20 |  | 2011 | 340 | NPRR221 | Post Go-Live | NPRR221 | Automate Default Invoice | n/a | Complete |  | $50k-$75k | [10 empty] | Apr 2011 | Aug 2011 | ERCOT | Modify the existing Lodestar uplift functionality to support uplift of defaults on DAM Invoices and RTM Invoices through a Default Uplift Invoice, in an automated fashion.
Stabilization | 2-High | 21 |  | 2011 | 350 | NPRR338 | Post Go-Live | NPRR338 | Modifications to Support Revenue Neutrality | n/a | Complete |  | $0k | [10 empty] | Dec 2011 | Dec 2011 | ERCOT | Deducts the amount collected for the shortfall charges for CRR Owners from the amount received on all Real-Time Market (RTM) Invoices prior to prorating the payout to the RTM Invoice Recipients
Stabilization | 2-High | 22 |  | 2011 | 360 | NPRR346 | Post Go-Live | NPRR346 | Removal of Redundant Posting Requirement Related to Electrical Bus Changes | n/a | Complete |  | <$2.5k | [10 empty] | Aug 2011 | Sept 2011 | ERCOT | Removes a redundant requirement for ERCOT to produce a report regarding Electrical Bus changes
Stabilization | 2-High | 36 |  | 2011 | 370 |  | Post Go-Live | 001-43 | EDW Platform Evaluation | n/a | Planning |  | $125k-$150k | [10 empty] | June 2011 | Feb 2012 | ERCOT | Strategic effort to define current and future EDW requirments, assess the EDW platform against those requirements and recommend an appropriate solution if needed
Stabilization | 2-High | 40 |  | 2011 | 380 | SCR766 NPRR384 | Post Go-Live | SCR766 | Load Zone Price Distributed by ICCP | n/a | Complete |  | $13k-$15k | [10 empty] | Aug 2011 | Oct 2011 | Market | Allows price data to be transferred to EMS for distribution over ICCP links, as soon as the five-minute Load Zone and Hub prices are calculated in Real-Time
Stabilization |  |  | 14 | 2011 | 390 |  | Post Go-Live | 001-51 | TML Transition to MIS | n/a | Closing |  | $50k-$75k | [10 empty] | Aug 2011 | Dec 2011 | ERCOT | Increase efficiency by consolidating to a single portal and prevent the need to maintain two systems
Stabilization |  |  |  | 2011 | 400 |  | Post Go-Live | 001-52 | IT Infrastructure Upgrade #1 | n/a | Execution |  | $350k-$400k | [10 empty] | Sept 2011 | Dec 2011 | ERCOT | Simplify and improve manageability of server environment that was installed during the Nodal program
Technical Foundation | 1- Critical | 1.5 |  | 2011 | 1 |  | PPL | 80001_01 | Met Center Disposition | n/a | Complete |  | <$20k | [10 empty] | 2009 | Jan 2011 | ERCOT | Final costs relating to the facilities projects that resulted in the construction of the Bastrop Control Center and TCC3
Technical Foundation | 1- Critical | 2 |  | 2011 | 2 |  | PPL | 99911 | Minor Cap - Critical - 2011 | n/a | Execution |  | $500k-$1M | [10 empty] | Jan 2011 | Dec 2011 | ERCOT | Critical priority Minor Cap purchases
Technical Foundation | 1- Critical | 8 |  | 2011 | 3 |  | PPL | 003_01 | IT Infrastructure Upgrade #2 | n/a | Complete |  | $100k-$250k | [10 empty] | May 2011 | Aug 2011 | ERCOT | Upgrade a specific component of the IT security infrastructure
Technical Foundation | 2-High | 11 |  | 2011 | 4 |  | PPL | 10055_01 | Data Agg Performance Improvements | n/a | Planning |  | $250k-$500k | [10 empty] | Sept 2010 | Oct 2011 | ERCOT | Project to address data aggregation processing performance risk Expected to start in 2010 and conclude in 2011
Technical Foundation | 2-High | 12.5 |  | 2011 | 5 |  | PPL | 11009_01 | Fire Alarm System Upgrade | n/a | Complete |  | $100k-$250k | [10 empty] | Feb 2011 | June 2011 | ERCOT | Upgrade fire alarm system for ERCOT facilities and provide the supporting workstations, processes, procedures and training.
Technical Foundation | 2-High | 18 |  | 2011 | 6 |  | PPL | 10018_01 | Annual Storage Growth | n/a | Execution |  | <$50k | [10 empty] | Jan 2011 | Apr 2011 | ERCOT | Unplanned Carryover. Remaining labor to complete installation of data storage purchased in 2010.
Technical Foundation | 1- Critical | 1 | 1 | 2012 | 10 |  | PPL | 11000_01 10015 10016 | Data Center Buildout | n/a | Execution |  | $25M-$30M |  |  | $500k-$600k | [7 empty] | Oct 2009 | Feb 2012 | ERCOT | Data Center Buildout Project - 3 subprojects addressing servers, storage, tape backup, telecommunication, and network gear
Technical Foundation |  |  | 2 | 2012 | 20 |  | PPL |  | Minor Cap - Critical - 2012 | n/a | Not Started |  |  |  |  | $500k-$750k | [7 empty] | Jan 2012 | Dec 2012 | ERCOT | Critical priority Minor Cap purchases
Technical Foundation | 1- Critical | 4 | 3 | 2012 | 30 |  | PPL | 90006_02 | Information Lifecycle Mgmt – Mkt Systems, Archive, Reporting | R5 off-cycle | Execution |  | $1M-$2M |  |  | $750k-$1M | [7 empty] | Jan 2010 | Jan 2012 | ERCOT | Subproject of 90006_01 - optimizing data storage requirements for our commercial systems
Technical Foundation | 1- Critical | 6 | 4 | 2012 | 40 |  | PPL | 10052_01 | Settlement System Upgrade | R4, future years | Planning |  | $800k-$1M |  |  | $1M-$1.2M |  | 1115000 | $1M-$2M |  |  |  |  | Mar 2010 | 2013 | ERCOT | Replace the current Settlements application code with an optimized, self-supported solution. Includes only the conversion of code -- no enhancements.
Technical Foundation |  |  | 5 | 2012 | 50 |  | PPL | 017_01 | Oracle 11g Upgrade | R2, R3, R4, R5, R6 | Initiation |  | $250k-$300k |  |  | $1M-$1.2M | [7 empty] | Nov 2011 | Dec 2012 | ERCOT | Upgrade database software
Technical Foundation |  |  | 6 | 2012 | 60 |  | PPL |  | EMS Upgrade | n/a | Not Started |  |  |  |  | $1M-$1.2M |  | 3000000 | $2M-$4M | 1000000 | $1M-$2M |  |  | TBD | TBD | ERCOT | Upgrade core vendor EMS application
Technical Foundation |  |  | 7 | 2012 | 70 |  | PPL | 001-43 | Enterprise DW Platform Transition | n/a | Planning |  |  |  |  | $50k-$100k |  | 0 | $0M | 500000 | $500k-$750k | 4000000 | $3M-$5M | June 2011 | Feb 2012 | ERCOT | Analysis and resulting actions to address potential performance issues as volume of data increases
Technical Foundation |  |  | 8 | 2012 | 80 |  | PPL |  | UC4 (AppWorx) Automation Upgrade v8 | TBD | Not Started |  |  |  |  | $150k-$250k | [7 empty] | TBD | TBD | ERCOT | Upgrade users on older version of job scheduling to prepare for future enterprise upgrade to latest version
Technical Foundation |  |  | 9 | 2012 | 90 |  | PPL |  | Siebel Upgrade 8.x | TBD | Not Started |  |  |  |  | $350k-$450k | [7 empty] | TBD | TBD | ERCOT | Upgrade core vendor Siebel application
Technical Foundation |  |  | 10 | 2012 | 100 |  | PPL |  | NMMS Upgrade | R6 | Not Started |  |  |  |  | $120k-$150k | [7 empty] | Jan 2012 | Dec 2012 | ERCOT | Upgrade core vendor NMMS application
Technical Foundation |  |  | 11 | 2012 | 110 |  | PPL |  | Data Center Growth & Asset Replacement - 2012 | n/a | Not Started |  |  |  |  | $500k-$750k |  | 0 | [5 empty] | Jan 2012 | Dec 2012 | ERCOT | 2102 data center hardware needs
Technical Foundation |  |  | 1 | 2012 | 115 |  | PPL |  | REC Enhancements | n/a | Not Started |  |  |  |  | $0k |  | 750000 | $500k-$1M |  |  |  |  | TBD | TBD | PUCT | Project to ensure compliance with any PUCT directives in the area of Renewable Energy Credits | 2 - Manage Markets | 2.1 Resource adequacy
Technical Foundation |  |  | 12 | 2013 | 120 |  | PPL |  | CRR Upgrade to v12.3 | n/a | Not Started | [6 empty] | 100000 | $100k-$250k |  |  |  |  | TBD | TBD | ERCOT | Upgrade core vendor CRR application
Technical Foundation |  |  | 13 | 2013 | 130 |  | PPL |  | Cognos 10.x Upgrade | n/a | Not Started | [6 empty] | 565491 | $500k-$1M |  |  |  |  | TBD | TBD | ERCOT | Upgrade reporting application
Technical Foundation |  |  | 14 | 2013 | 140 |  | PPL |  | Capacity growth - storage/comp. | n/a | Not Started | [6 empty] | 276000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | 2102 storage and computing needs
Technical Foundation |  |  | 15 | 2013 | 150 |  | PPL |  | UC4 Automation Upgrade v9 | n/a | Not Started | [6 empty] | 325000 | $250k-$500k |  |  |  |  | TBD | TBD | ERCOT | Upgrade job scheduling application
Technical Foundation |  |  | 17 | 2013 | 170 |  | PPL |  | Replace Sun DSEE | n/a | Not Started | [6 empty] | 527182 | $500k-$1M | 527182 | $500k-$1M |  |  | TBD | TBD | ERCOT | Replace or upgrade
Technical Foundation |  |  | 18 | 2013 | 180 |  | PPL |  | Replace Sun IDM | n/a | Not Started | [6 empty] | 552000 | $500k-$1M | 552000 | $500k-$1M |  |  | TBD | TBD | ERCOT | Replace or upgrade identity management software
Technical Foundation |  |  | 19 | 2013 | 190 |  | PPL |  | Minor Cap - Critical - 2013 | n/a | Not Started | [6 empty] | 1000000 | $1M-$2M |  |  |  |  | Jan 2013 | Dec 2013 | ERCOT | Future year critical priority Minor Cap purchases
Technical Foundation |  |  | 20 | 2014 | 200 |  | PPL |  | Minor Cap - Critical - 2014 | n/a | Not Started | [8 empty] | 1000000 | $1M-$2M |  |  | Jan 2014 | Dec 2014 | ERCOT | Future year critical priority Minor Cap purchases
Technical Foundation |  |  | 21 | 2015 | 210 |  | PPL |  | Minor Cap - Critical - 2015 | n/a | Not Started | [10 empty] | 1000000 | $1M-$2M | Jan 2015 | Dec 2015 | ERCOT | Future year critical priority Minor Cap purchases
Technical Foundation |  |  | 22 | 2013 | 220 |  | PPL |  | Data Center Growth & Asset Replacement - 2013 | n/a | Not Started | [6 empty] | 2800000 | $2M-$4M |  |  |  |  | Jan 2013 | Dec 2013 | ERCOT | Future year data center hardware needs
Technical Foundation |  |  | 23 | 2014 | 230 |  | PPL |  | Data Center Growth & Asset Replacement - 2014 | n/a | Not Started | [8 empty] | 3200000 | $2M-$4M |  |  | Jan 2014 | Dec 2014 | ERCOT | Future year data center hardware needs
Technical Foundation |  |  | 24 | 2015 | 240 |  | PPL |  | Data Center Growth & Asset Replacement - 2015 | n/a | Not Started | [10 empty] | 5200000 | $4M-$6M | Jan 2015 | Dec 2015 | ERCOT | Future year data center hardware needs
Note on B9: Anderson, Troy: Priority from 2011 PPL
Note on C9: Anderson, Troy: Rank from 2011 PPL
Note on D9: Anderson, Troy: Rank from Board-approved 2012 PPL

## PPL Update Log
Summary of PPL Changes to Key Fields
Approval Date | Project Category | Rank | Project Number | Project | Field Changed | New Value | Comments
2011-08-24 | Business Strategy | 20 | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | 2012 Budget Range | $500k-$600k | ER Approval
2011-08-24 | Business Strategy | 20 | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 40 | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | 2011 Budget Range | $500k-$600k | ER Approval
2011-08-24 | Stabilization | 40 | SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 180 | NPRR310 | Expand Output Schedule Acceptable Range to Include HSL and LSL | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 180 | NPRR310 | Expand Output Schedule Acceptable Range to Include HSL and LSL | Projected End Date | 2011-12-01 | ER Approval
2011-08-24 | Stabilization | 190 | SCR762 | Enable a Single Step Cancel/Resubmit of Trades | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 190 | SCR762 | Enable a Single Step Cancel/Resubmit of Trades | Projected End Date | 2011-10-01 | ER Approval
2011-08-24 | Stabilization | 210 | SCR763 | Modify COP Validation Rule for RRS | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 210 | SCR763 | Modify COP Validation Rule for RRS | Projected End Date | 2011-12-01 | ER Approval
2011-08-24 | Stabilization | 300 | NPRR316 | Negative Self-Arranged Ancillary Services Quantity | Project Status | Execution | ER Approval
2011-08-24 | Stabilization | 300 | NPRR316 | Negative Self-Arranged Ancillary Services Quantity | Projected End Date | 2011-12-01 | ER Approval
2011-08-24 | Stabilization | 310 | n/a | Decommissioning Efforts | Projected End Date | 2011-12-01 | ER Approval
2011-08-31 | Stabilization | 390 | 001-51 | TML Transition to MIS | 2011 Budget Range | $50k-$75k | ER Approval
2011-08-31 | Stabilization | 390 | 001-51 | TML Transition to MIS | Project Status | Execution | ER Approval
2011-08-31 | Stabilization | 390 | 001-51 | TML Transition to MIS | Projected End Date | 2011-12-01 | ER Approval
2011-09-01 | Business Strategy | 50 | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | Approval Status | Pending Board Approval | TAC Approval
2011-09-07 | Business Strategy | 2 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | 2012 Budget Range | $10k-$15k | ER Approval
2011-09-07 | Business Strategy | 2 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | Project Status | Execution | ER Approval
2011-09-07 | Business Strategy | 2 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | Projected End Date | 2012-02-01 | ER Approval
2011-09-07 | Stabilization | 3 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | 2011 Budget Range | $100k-$125k | ER Approval
2011-09-07 | Stabilization | 3 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | Project Status | Execution | ER Approval
2011-09-14 | Efficiencies / Enhancements | 2 | 007_01 | Cyber Security Facilities Remodeling | Project Status | Execution | ER Approval
2011-09-14 | Efficiencies / Enhancements | 2 | 007_01 | Cyber Security Facilities Remodeling | Projected End Date | 2011-12-01 | ER Approval
2011-09-14 | Efficiencies / Enhancements | 3 | 007_01 | Human Resources Facilities Remodeling | 2011 Budget Range | $200k-$250k | ER Approval
2011-09-14 | Efficiencies / Enhancements | 3 | 007_01 | Human Resources Facilities Remodeling | Project Status | Execution | ER Approval
2011-09-14 | Efficiencies / Enhancements | 3 | 007_01 | Human Resources Facilities Remodeling | Projected End Date | 2011-12-01 | ER Approval
2011-09-14 | Efficiencies / Enhancements | 4 | 007_01 | Shipping/Receiving Remodeling | Project Status | Execution | ER Approval
2011-09-14 | Efficiencies / Enhancements | 4 | 007_01 | Shipping/Receiving Remodeling | Projected End Date | 2011-12-01 | ER Approval
2011-09-14 | Stabilization | 240 | NPRR343 | CRR Bid and PTP Obligation Bid Criteria Change | 2011 Budget Range | $300k-$350k | ER Approval
2011-09-14 | Stabilization | 240 | NPRR343 | CRR Bid and PTP Obligation Bid Criteria Change | Project Status | Execution | ER Approval
2011-09-20 | Business Strategy | 50 | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 60 | NPRR348 | Generation Resource Start-Up and Shut-Down Process | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 170 | NPRR222 | Half Hour Start Unit RUC Clawback | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 200 | NPRR272 | Definition and Participation of Quick Start Generation Resources | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 210 | NPRR207 | Unit Deselection | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 240 | NPRR379 | EILS Dispatch Sequence and Performance Criteria Upgrades | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 290 | NPRR354 | Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 310 | NPRR360 | Summary Report of HDL and LDL | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 400 | NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 410 | NPRR241 | AIL Calculation & Credit Reports Publish Corrections | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 420 | NPRR256 | Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards | Approval Status | PPL | Board Approval
2011-09-20 | Business Strategy | 430 | NPRR240 | Proxy Energy Offer Curve | Approval Status | PPL | Board Approval
2011-09-22 | Business Strategy | 390 | NPRR181 | FIP Definition Revision | Approval Status | Pending TAC Approval | PRS Approval
2011-09-28 | Stabilization | 290 | NPRR251 | Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | 2011 Budget Range | $10k-$15k | ER Approval
2011-09-28 | Stabilization | 290 | NPRR251 | Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | Project Status | Execution | ER Approval
2011-09-28 | Stabilization | 290 | NPRR251 | Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | Projected End Date | 2011-12-01 | ER Approval
2011-10-05 | Business Strategy | 220 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | 2012 Budget Range | $10k-$15k | ER Approval
2011-10-05 | Business Strategy | 220 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | Project Status | Execution | ER Approval
2011-10-05 | Business Strategy | 220 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | Projected End Date | 2012-02-01 | ER Approval
2011-10-05 | Stabilization | 200 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | 2011 Budget Range | $40k-$48k | ER Approval
2011-10-05 | Stabilization | 200 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | Project Status | Execution | ER Approval
2011-10-05 | Stabilization | 200 | SCR761 | Provide Price Republication Notifications via API and Provide Price Corrections via XML | Projected End Date | 2012-02-01 | ER Approval
2011-10-06 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | Approval Status | Pending Board Approval | TAC Approval
2011-10-06 | Regulatory | 10 | NPRR400 | Eliminate Unsecured Credit for CRR Auctions and for Future Credit Exposure and Eliminate Netting of FCE and CCE | Approval Status | Pending Board Approval | TAC Approval
2011-10-18 | Regulatory | 10 | NPRR400 | Eliminate Unsecured Credit for CRR Auctions and for Future Credit Exposure and Eliminate Netting of FCE and CCE | Approval Status | PPL | Board Approval
2011-10-20 | Business Strategy | 520 | NPRR381 | Registration Requirements for Interconnecting Entities | Approval Status | Withdrawn | Info Only
2011-10-20 | Business Strategy | 360 | NPRR377 | Alternate Inputs to Base Point Deviation Charge | Approval Status | Pending TAC Approval | PRS Approval
2011-10-21 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | 2011 Budget Range | <$50k | ER Approval
2011-10-21 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | Project Status | Initiation | ER Approval
2011-10-26 | Business Strategy | 4 | 002_01 | Impact Assessment Labor Funds | 2011 Budget Range | $98k-$100k | Info Only
2011-10-26 | Business Strategy | 150 | 010_01 | MarkeTrak Upgrade and Enhancements | 2011 Budget Range | $400k-$425k | ER Approval
2011-10-26 | Business Strategy | 150 | 010_01 | MarkeTrak Upgrade and Enhancements | 2012 Budget | 298135 | ER Approval
2011-10-26 | Business Strategy | 150 | 010_01 | MarkeTrak Upgrade and Enhancements | 2012 Budget Range | $275k-$325k | ER Approval
2011-10-26 | Business Strategy | 150 | 010_01 | MarkeTrak Upgrade and Enhancements | Project Status | Execution | ER Approval
2011-10-26 | Business Strategy | 4 | 002_01 | Impact Assessment Labor Funds | Project Status | Closing | Info Only
2011-10-26 | Business Strategy | 4 | 002_01 | Impact Assessment Labor Funds | Projected End Date | 2011-10-01 | Info Only
2011-10-26 | Technical Foundation | 3 | 003_01 | IT Security Infrastructure Upgrade | Project Status | Closing | Info Only
2011-11-02 | Efficiencies / Enhancements | 100 | 011_01 | MyGrid | 2011 Budget Range | <$5k | ER Approval
2011-11-02 | Efficiencies / Enhancements | 100 | 011_01 | MyGrid | Project Name | MyGrid | ER Approval
2011-11-02 | Efficiencies / Enhancements | 100 | 011_01 | MyGrid | Project Status | Initiation | ER Approval
2011-11-02 | Efficiencies / Enhancements | 100 | 011_01 | MyGrid | Projected Start Date | 2011-11-01 | ER Approval
2011-11-03 | Business Strategy | 360 | NPRR377 | Alternate Inputs to Base Point Deviation Charge | Approval Status | Pending Board Approval | TAC Approval
2011-11-09 | Business Strategy | 2 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | 2012 Budget Range | $60k-$75k | ER Approval
2011-11-09 | Business Strategy | 2 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | Projected End Date | 2012-04-01 | ER Approval
2011-11-09 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | 2011 Budget Range | $60k-$75k | ER Approval
2011-11-09 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | Project Status | Planning | ER Approval
2011-11-09 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | Projected End Date | 2012-06-01 | ER Approval
2011-11-09 | Business Strategy | 100 | 012_01 | Demand Response (Look Ahead SCED) | Projected Start Date | 2011-09-01 | ER Approval
2011-11-09 | Business Strategy | 190 | NPRR326 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | 2011 Budget Range | $4k-$6k | ER Approval
2011-11-09 | Business Strategy | 190 | NPRR326 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | 2012 Budget Range | $13k-$16k | ER Approval
2011-11-09 | Business Strategy | 190 | NPRR326 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | Project Status | Planning | ER Approval
2011-11-09 | Business Strategy | 190 | NPRR326 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | Projected End Date | 2012-02-01 | ER Approval
2011-11-09 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | 2011 Budget Range | $10k-$12k | ER Approval
2011-11-09 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | 2012 Budget Range | $40k-$48k | ER Approval
2011-11-09 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | Project Status | Planning | ER Approval
2011-11-09 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | Projected End Date | 2012-02-01 | ER Approval
2011-11-09 | Business Strategy | 300 | NPRR355 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | 2011 Budget Range | $5k-$6k | ER Approval
2011-11-09 | Business Strategy | 300 | NPRR355 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | 2012 Budget Range | $50k-$60k | ER Approval
2011-11-09 | Business Strategy | 300 | NPRR355 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | Project Status | Planning | ER Approval
2011-11-09 | Business Strategy | 300 | NPRR355 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | Projected End Date | 2012-02-01 | ER Approval
2011-11-09 | Stabilization | 3 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | 2011 Budget Range | $80k-$100k | ER Approval
2011-11-09 | Stabilization | 3 | 001-47 | RARF Upgrade for Wind, Solar, and Storage Resources | Projected End Date | 2012-04-01 | ER Approval
2011-11-09 | Stabilization | 400 | 001-52 | IT Infrastructure Upgrade | 2011 Budget Range | $350k-$400k | ER Approval
2011-11-09 | Stabilization | 400 | 001-52 | IT Infrastructure Upgrade | Project Name | IT Infrastructure Upgrade | ER Approval
2011-11-09 | Stabilization | 400 | 001-52 | IT Infrastructure Upgrade | Project Status | Execution | ER Approval
2011-11-09 | Stabilization | 400 | 001-52 | IT Infrastructure Upgrade | Projected End Date | 2011-12-01 | ER Approval
2011-11-09 | Technical Foundation | 3 | 003_01 | IT Security Infrastructure Upgrade | Project Status | Complete | Info Only
2011-11-16 | Business Strategy | 70 | NPRR322 | Real-Time PTP Option Modeling | Projected End Date | TBD | Reforecast
2011-11-16 | Business Strategy | 70 | NPRR322 | Real-Time PTP Option Modeling | Projected Start Date | TBD | Reforecast
2011-11-16 | Business Strategy | 230 | NPRR321 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | Projected End Date | 2011-12-01 | Reforecast
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | n/a | NEW PROJECT | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | 2011 Budget Range | $15k-$25k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | 2012 Budget Range | $30k-$50k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | Approval Status | PPL | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | Priority | 2011 | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | Project Status | Planning | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | Projected Start Date | 2011-11-01 | ER Approval
2011-11-16 | Efficiencies / Enhancements | 5 | 015_01 | Outage Capacity Calculation Tool | Rank | 5 | ER Approval
2011-11-16 | Efficiencies / Enhancements | 100 | 011_01 | ERCOT Mobile | 2011 Budget Range | $15k-$20k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 100 | 011_01 | ERCOT Mobile | 2012 Budget Range | $120k-$140k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 100 | 011_01 | ERCOT Mobile | Project Name | ERCOT Mobile | ER Approval
2011-11-16 | Efficiencies / Enhancements | 100 | 011_01 | ERCOT Mobile | Project Status | Planning | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | n/a | NEW PROJECT | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | 2011 Budget Range | $20k-$30k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | 2012 Budget Range | $100k-$120k | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | Approval Status | PPL | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | Priority | 2012 | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | Project Status | Planning | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | Projected Start Date | 2011-11-01 | ER Approval
2011-11-16 | Efficiencies / Enhancements | 155 | 016_01 | ADP-IDM Interface | Rank | 155 | ER Approval
2011-11-16 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | 2011 Budget Range | <$50k | ER Approval
2011-11-16 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | 2012 Budget Range | $660k-$715k | ER Approval
2011-11-16 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | Project Name | Impl. NPRR347/NPRR400 | ER Approval
2011-11-16 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | Project Status | Initiation | ER Approval
2011-11-16 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | Projected Start Date | 2011-11-01 | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | n/a | NEW PROJECT | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | 2012 Budget Range | $50k-$55k | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | Priority | 2012 | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | Project Status | Initiation | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | Projected Start Date | 2011-12-01 | ER Approval
2011-11-16 | Regulatory | 40 | TBD | Quality Training Database | Rank | 40 | ER Approval
2011-11-16 | Stabilization | 370 | 001-43 | EDW Platform Evaluation | 2011 Budget Range | $125k-$150k | ER Approval
2011-11-16 | Stabilization | 370 | 001-43 | EDW Platform Evaluation | Projected End Date | 2012-02-01 | ER Approval
2011-11-16 | Technical Foundation | 50 | 017_01 | Oracle 11g Upgrade | Project Status | Initiation | ER Approval
2011-11-16 | Technical Foundation | 50 | 017_01 | Oracle 11g Upgrade | Projected Start Date | 2011-11-01 | ER Approval
2011-11-16 | Technical Foundation | 70 | 001-43 | Enterprise DW Platform Transition | 2012 Budget Range | $50k-$100k | ER Approval
2011-11-16 | Technical Foundation | 70 | 001-43 | Enterprise DW Platform Transition | 2013 Budget Range | $0M | ER Approval
2011-11-16 | Technical Foundation | 70 | 001-43 | Enterprise DW Platform Transition | 2014 Budget Range | $500k-$750k | ER Approval
2011-11-16 | Technical Foundation | 70 | 001-43 | Enterprise DW Platform Transition | 2015 Budget Range | $3M-$5M | ER Approval
2011-11-16 | Technical Foundation | 70 | 001-43 | Enterprise DW Platform Transition | Projected End Date | 2012-02-01 | ER Approval
2011-11-29 | Business Strategy | 100 | NPRR351 | Calculate and Post Projected Non-Binding LMPs for the Next 15 Minutes | Rank | 100 | PRS Approval
2011-11-29 | Business Strategy | 480 | NPRR327 | State Estimator Data Redaction Methodology | Priority | 2012 | PRS Approval
2011-11-29 | Business Strategy | 480 | NPRR327 | State Estimator Data Redaction Methodology | Rank | 480 | PRS Approval
2011-11-29 | Business Strategy | 510 | NPRR351 | Calculate and Post Projected Non-Binding LMPs for the Next 15 Minutes | Priority | 2012 | PRS Approval
2011-11-30 | Regulatory | 20 | 009-01 | Compliance Software Tool | 2012 Budget | 123379 | ER Approval
2011-11-30 | Regulatory | 20 | 009-01 | Compliance Software Tool | 2012 Budget Range | $110k-$140k | ER Approval
2011-11-30 | Regulatory | 20 | 009-01 | Compliance Software Tool | Project Status | Execution | ER Approval
2011-11-30 | Technical Foundation | 40 | 10052_01 | Settlement System Upgrade | 2011 Budget Range | $800k-$1M | ER Approval
2011-11-30 | Technical Foundation | 160 | n/a | Upgrade Siteminder | 2013 Budget Range | $0k | ER Approval
2011-11-30 | Technical Foundation | 160 | n/a | Upgrade Siteminder | Project Status | Deleted | ER Approval
2011-12-01 | Business Strategy | 100 | NPRR351 | Calculate and Post Projected Non-Binding LMPs for the Next 15 Minutes | Approval Status | Pending Board Approval | TAC Approval
2011-12-01 | Business Strategy | 470 | NPRR315 | Revision of Responsive Reserve Measure to High Emergency Limit | Approval Status | Rejected | TAC Approval
2011-12-07 | Business Strategy | 1 | 50088_01 | Data Research and Reporting | Project Status | Complete | Info Only
2011-12-07 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | 2012 Budget | 674039 | ER Approval
2011-12-07 | Regulatory | 10 | 014_01 | Implementation of NPRR347 and NPRR400 | Project Status | Planning | ER Approval
2011-12-08 | Business Strategy | 180 | TBD | Cyber Security Project #6 | 2012 Budget Range | $150k-$200k | ER Approval
2011-12-08 | Business Strategy | 180 | TBD | Cyber Security Project #6 | 2013 Budget Range | $50k-$100k | ER Approval
2011-12-08 | Efficiencies / Enhancements | 1 | 004_01 | Cyber Security Project #3 | 2012 Budget | 75389 | ER Approval
2011-12-08 | Efficiencies / Enhancements | 1 | 004_01 | Cyber Security Project #3 | 2012 Budget Range | $75k-$100k | ER Approval
2011-12-08 | Efficiencies / Enhancements | 1 | 004_01 | Cyber Security Project #3 | Project Status | Execution | ER Approval
2011-12-08 | Efficiencies / Enhancements | 1 | 004_01 | Cyber Security Project #3 | Projected End Date | 2012-03-01 | ER Approval
2011-12-08 | Stabilization | 350 | NPRR338 | Modifications to Support Revenue Neutrality | 2011 Budget Range | $0k | Info Only
2011-12-08 | Stabilization | 350 | NPRR338 | Modifications to Support Revenue Neutrality | Project Status | Complete | Info Only
2011-12-08 | Stabilization | 350 | NPRR338 | Modifications to Support Revenue Neutrality | Projected End Date | 2011-12-01 | Info Only
2011-12-08 | Stabilization | 350 | NPRR338 | Modifications to Support Revenue Neutrality | Projected Start Date | 2011-12-01 | Info Only
2011-12-09 | Business Strategy | 60 | NPRR348 | Generation Resource Start-Up and Shut-Down Process | Projected End Date | 2012-12-01 | Reforecast
2011-12-09 | Business Strategy | 60 | NPRR348 | Generation Resource Start-Up and Shut-Down Process | Projected Start Date | June 2012 | Reforecast
2011-12-09 | Business Strategy | 290 | NPRR354 | Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment | Projected End Date | 2012-12-01 | Reforecast
2011-12-09 | Business Strategy | 290 | NPRR354 | Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment | Projected Start Date | 2012-06-01 | Reforecast
2011-12-12 | Business Strategy | 100 | NPRR351 | Calculate and Post Projected Non-Binding LMPs for the Next 15 Minutes | Approval Status | PPL | Board Approval
2011-12-12 | Business Strategy | 100 | 012_01 | SCED Look-Ahead Step 1: Pricing | Project Name | SCED Look-Ahead Step 1: Pricing | Board Approval
2011-12-12 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | Approval Status | PPL | Board Approval
2011-12-12 | Business Strategy | 360 | NPRR377 | Alternate Inputs to Base Point Deviation Charge | Approval Status | PPL | Board Approval
2011-12-12 | Business Strategy | 50 | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | 2012 Budget Range | $110k-$120k | Correction
2011-12-12 | Business Strategy | 60 | NPRR348 | Generation Resource Start-Up and Shut-Down Process | 2012 Budget Range | $115k-$130k | Correction
2011-12-14 | Business Strategy | 50 | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | 2011 Budget Range | <$5k | ER Approval
2011-12-14 | Business Strategy | 50 | NPRR365 | Change in Resource Outage Approvals from Eight to 90 Days | Project Status | Initiation | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node | Project Status | Execution | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | n/a | NEW PROJECT | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | 2011 Budget Range | $10k-$12k | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | 2012 Budget Range | $65k-$85k | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | Project Status | Execution | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | Projected End Date | 2012-02-01 | ER Approval
2011-12-14 | Business Strategy | 190 | 013_01 | MMS 2012 Release 1: NPRR321/NPRR326/NPRR355 | Projected Start Date | 2011-11-01 | ER Approval
2011-12-14 | Business Strategy | 230 | 013_01 | Allow Change to Energy Offer Curve MW Amounts in the Adjustment Period for Qualifying Facilities | Project Status | Execution | ER Approval
2011-12-14 | Business Strategy | 300 | 013_01 | Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone | Project Status | Execution | ER Approval
2011-12-14 | Stabilization | 90 | SCR765 | Public Aggregated Wind Dashboard | Project Status | Closing | Info Only
2011-12-14 | Stabilization | 390 | 001-51 | TML Transition to MIS | Project Status | Closing | Info Only
2011-12-15 | Business Strategy | 480 | NPRR327 | State Estimator Data Redaction Methodology | Approval Status | Pending TAC Approval | PRS Approval
2011-12-15 | Business Strategy | 590 | NPRR407 | Credit Monitoring Posting Requirements | Approval Status | Pending TAC Approval | PRS Approval
2011-12-15 | Business Strategy | 590 | NPRR407 | Credit Monitoring Posting Requirements | Priority | 2012 | PRS Approval
2011-12-15 | Business Strategy | 590 | NPRR407 | Credit Monitoring Posting Requirements | Rank | 590 | PRS Approval
2011-12-15 | Business Strategy | 600 | NPRR422 | Public DAM Shift Factors | Approval Status | Pending TAC Approval | PRS Approval
2011-12-15 | Business Strategy | 600 | NPRR422 | Public DAM Shift Factors | Priority | 2012 | PRS Approval
2011-12-15 | Business Strategy | 600 | NPRR422 | Public DAM Shift Factors | Rank | 600 | PRS Approval
2011-12-16 | Business Strategy | 30 | 006_01 | Cyber Security Project #1 | 2011 Budget Range | $400k-$500k | Correction
2011-12-19 | Technical Foundation | 10 | 11000_01 10015 10016 | Data Center Buildout | 2012 Budget Range | $500k-$600k | ER Approval
2011-12-21 | Business Strategy | 40 | 005_01 | Cyber Security Project #2 | 2011 Budget Range | $150k-$200k | ER Approval
2011-12-21 | Business Strategy | 40 | 005_01 | Cyber Security Project #2 | 2012 Budget Range | $160k-$180k | ER Approval
2011-12-21 | Business Strategy | 40 | 005_01 | Cyber Security Project #2 | Project Status | Execution | ER Approval
2011-12-21 | Business Strategy | 130 | TBD | Cyber Security Project #5 | 2012 Budget Range | $500k-$700k | ER Approval
2011-12-21 | Business Strategy | 130 | TBD | Cyber Security Project #5 | 2013 Budget Range | $150k-$200k | ER Approval
2011-12-21 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | 2012 Budget Range | $40k-$50k | ER Approval
2011-12-21 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | Project Status | Initiation | ER Approval
2011-12-21 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | Projected End Date | 2012-04-01 | ER Approval
2011-12-21 | Business Strategy | 260 | NPRR395 | CRR Auction Offer Award Disclosure | Projected Start Date | Dec 2011 | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | n/a | NEW PROJECT | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | 2011 Budget Range | <$5k | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | 2012 Budget Range | $30k-$50k | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | Priority | 2012 | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | Project Status | Initiation | ER Approval
2011-12-21 | Business Strategy | 610 | TBD | CIM Upgrade for NMMS | Projected Start Date | Dec 2011 | ER Approval
2011-12-21 | Business Strategy | 620 | SCR764 | Public Access to Select MIS Dashboards | n/a | STABILIZATION CARRYOVER | ER Approval
2011-12-21 | Business Strategy | 620 | SCR764 | Public Access to Select MIS Dashboards | 2012 Budget Range | $15k-$20k | ER Approval
2011-12-21 | Business Strategy | 620 | SCR764 | Public Access to Select MIS Dashboards | Priority | 2012 | ER Approval
2011-12-21 | Business Strategy | 620 | SCR764 | Public Access to Select MIS Dashboards | Projected End Date | 2012-02-01 | ER Approval
2011-12-21 | Efficiencies / Enhancements | 10 | TBD | Incremental Update Capability - Phase 1 | Project Status | Initiation | ER Approval
2011-12-21 | Stabilization | 70 | SCR764 | Public Access to Select MIS Dashboards | 2011 Budget Range | $60k-$80k | ER Approval
2011-12-21 | Technical Foundation | 115 | TBD | REC Enhancements | 2012 Budget Range | $0k | ER Approval
2011-12-21 | Technical Foundation | 115 | TBD | REC Enhancements | 2013 Budget Range | $500k-$1M | ER Approval
2011-12-21 | Technical Foundation | 115 | TBD | REC Enhancements | Rank | 115 | ER Approval
Types of Changes Captured on This Report |  |  |  |  | Comment Descriptions
- New additions |  | - Change in project start and end target date |  |  | ER Approval | Executive Review approval
- Rank changes |  | - Change in budget range |  |  | Board/TAC/PRS Approval | Self-explanatory
- Approval changes |  | - Status changes (project phase) |  |  | Info Only | Item that does not require approval

## Parking Deck
After reconsideration by the Board of each Parking Deck item, it is removed from this list and appears in the appropriate place on the PPL
Priority | Rank | Current Status | Source Document | Description | Sort Char | Release Year | Systems Impacted | Target Release | Source | IA Phase | Estimated Cost | Estimated Effort | Estimated Duration | Work-arounds | Submitter | Submission Date | Actual Implementation Date | Prioritization Source | Additional Information
2 - High | 4 | Board Approved | NPRR181 | FIP Definition Revision | 99 | 2013+ | MMS, COMS, Integration | TBD | Parking Deck | 3 |  |  |  |  | Luminant | 2009-06-10 |  |  | Revises the definition of Fuel Index Price (FIP) to correctly account for the timing difference between ERCOT’s application of FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900).
3 - High / Medium |  | Board Approved | NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | 99 | Various | EIS | TBD | Parking Deck | 4 |  |  |  |  | ERCOT Staff | 2010-07-23 |  |  | Greyboxes multiple sections to align with Nodal Operating Guide Section 9, Monitoring Programs
4 - Medium |  | Board Approved | NPRR164 | Resubmitting Ancillary Service Offers in SASM | 9 | TBD | MMS, EIF, EIS, CDR | Release 2.0 | Parking Deck | TBD |  |  |  |  | TPTF | 2008-11-11 |  |  | Allows QSEs to take full advantage of A/S and energy co-optimization in the DAM and participate in the Supplemental Ancillary Service Market (SASM) by being able to resubmit A/S Offers at the higher of DAM MCPC or its offer price in the DAM.
4 - Medium |  | Board Approved | NPRR153 | Generation Resource Fixed Quantity Block Offer | 12 | TBD | MMS, EIF, EIS, CDR | Future Release | Parking Deck | 4 |  |  |  |  | TPTF | 2008-09-12 |  |  | Allows a fixed quantity and time block bid for Offline Non-Spin with the contingency that all hours be purchased in the block
4 - Medium |  | Board Approved | NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | 99 | TBD |  | TBD | Parking Deck | 4 |  |  |  |  | ERCOT Staff | 2010-01-22 |  |  | Grey-boxes language that allows QSE and TSPs to request removal of telemetry from Telemetry Standard performance metrics when certain situations exist.
4 - Medium |  | Board Approved | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | 99 | TBD | Siebel, MPIM, MIS, MIR, EWS, EIF | TBD | Parking Deck | 4 |  |  |  |  | Crescent Power | 2010-08-05 |  |  | Makes it possible for consultants, power marketers, aggregators, consumers and universities to get access to the MIS Secure area (without doing so by getting a digital certificate through a registered Market Participant)
4 - Medium |  | Board Approved | SCR755 | ERCOT.com Website Enhancements | 99 | TBD | ERCOT.com | TBD | Parking Deck | 4 |  |  |  |  | CCWG | 2009-02-25 |  |  | Implementation of 10 improvements to ERCOT.com received in the 2008 Market Participant Survey. Includes document archiving, search improvements, training, meeting calendar enhancements, and RSS feeds.

## Market-Facing Defects
Defect ID | Summary | Market Description | Production Target Date | System | Counts
5963 | OS Core: for MP UI: The NewPlanned and New latest End dates should be extended one more time | Once an outage has been extended it can't be extended again. | 2011-01-19 | Outage Scheduler | Congestion Revenue Rights | 13
6879 | OS: Core: Transmission M1 - Withdrawn outages which are not active should not be ended | A withdrawn Outage does not require an Actual End even though the UI will display the field. | 2011-01-19 | Outage Scheduler | Current Day Reports | 23
7077 | OS Core: RUI-PL_GRP_Status-Study-poor error message when trying to add notes | When an outage has a status of Study and the user attempts to add a note, the error message needs to be more specific. | 2011-01-19 | Outage Scheduler | Energy Management System | 3
8755 | OS UI: Usability: Associated Equipment Table: Select All for the check boxes | When the user views associated equipment they must select each piece of the line in a check box. A "Select All" button is needed. | 2011-01-19 | Outage Scheduler | Enterprise Data Warehouse | 3
10276 | OS UI Usability: When your right click from Print, Export.xml or Export.csv you get a blank page | When the user clicks on the "Print summary information", "Export.xml or Export.csv, they may receive a blank page. | 2011-01-19 | Outage Scheduler | Enterprise Integration | 6
10512 | OS UI Print Summary Information link screen shares the same title as the Summary Screen | The "Print Summery Information" window has the same title in the title bar at the top of the screen as Summery screen. | 2011-01-19 | Outage Scheduler | Enterprise Web Services | 19
13039 | OS Core: When an outage is at PComp state, Actual End is not editable | Enter the required supporting notes then the Actual End becomes editable. | 2011-01-19 | Outage Scheduler | Market Information System | 21
13575 | OS Core: Outage past its end date cannot be extended gives an invalid error message | Once an outage has passed the Planned End Date/time the user can't extend the outage. If the MP attempts to extend the outage, the error message they receive is misleading. | 2011-01-19 | Outage Scheduler | Market Management System | 14
13588 | OS UI TSP WRN column - arrows do not highlight asc or dec when clicked | The arrows on the summary columns do not indicate if the column is sorted ascending or descending | 2011-01-19 | Outage Scheduler | Market Management System UI | 4
15186 | DST-NP6-235 - System-Wide Demand report output does not have enough data during CDT time. | .NP6-235 - System-Wide Demand report output does not have enough data during CDT time. | 2011-01-19 | Reports | Market Manager | 16
15267 | DST-NP3-217-Temperature Adjusted Dynamic Ratings - Report output has 2.00 hour on CDT day. | .NP3-217-Temperature Adjusted Dynamic Ratings - Report output has 2.00 hour on CDT day. Fixes putting '*' by extra hour during Fall DST transition. | 2011-01-19 | Reports | Market Participant Identity Management | 6
17781 | OS Core: The OS needs to auto populate the Actual Start/Actual End on an outage with the "Nature of Work" of "New Equipment Energization" | When a MP is putting a new piece of equipment in service they are suppose to enter an outage with a Planned Start date of a network model load prior to the date the equipment we be energized. Since the model load will be around MN they have asked that the system auto populate the Actual Start. When a MP is retiring a piece of equipment they are suppose to enter an outage with a Planned End date of a network model load after the equipment is removed from service. Since the model load will be around MN they have asked that the system auto populate the Actual End. | 2011-01-19 | Outage Scheduler | MIS Dashboard | 1
17922 | OS Core: MP is unable to extend an outage a second time | The MPs are unable to extend an outage more than one time. | 2011-01-19 | Outage Scheduler | Network Model Management System | 7
18006 | Self Energy Trade Net Trade of Letter Other Than 'P' or 'S' Not Handled Properly | Characters outside of 'P' and 'S' for a self energy trade are not handled properly by the MMS Market Manager. | 2011-01-19 | Market Manager | Outage Scheduler | 40
18038 | Self energy trade submission formed incorrectly when value changes on Int End 30 or 45 | Self energy trades will fail from the MMS MM when the MW value or P/S value of one hour carries over into the next hour and changes on either the 30 or 45 minute interval | 2011-01-19 | Market Manager | Outage Scheduler UI | 37
18039 | Clicking to see details of partially confirmed trade from unconfirmed trade is read-only | Clicking to view the details of the unconfirmed portion of a partially confirmed trade entered by the user brings up a read-only screen. This screen should be editable | 2011-01-19 | Market Manager | Registration | 13
18069 | MIS - Dashboard - LF vs Actual label change | On the Load Forecast vs Actual dashboard, the labels will be changed to more accurately reflect the data given. 'Online Generation - Actual' will become 'Current Day COP HSLs for Online Generation', and 'Online Generation - Planned' will become 'Day-Ahead COP HSLs for Online Generation'. | 2011-01-19 | MIS Dashboard | Reports | 13
18467 | OS UI: Remove from the OS UI the 3 day rule for NPE as of OS core release 2.3.0 | The User can wait to extend the outage until 3 days before the PE date. The user may also extend the outage using the API without the limitation. | 2011-01-19 | Outage Scheduler | Total | 239
18472 | NPRR261: PTC: Summer: Remove restriction for interim update to make it simple 90 days for all cases | The user needs to be able to submit model information for each month in the summer and not the summer as a block model update. | 2011-01-19 | Network Model Management System
18307 | DC Ties incorrectly show up as a QSE in the Market Manager | DC Ties are incorrectly listed on the drop down list for QSEs (for example, when creating an energy trade, one of the options on the drop down for 'seller' is 'DC_E'). | 2011-01-20 | Market Management System
18357 | Wrong DELIVERY_HOUR in HRUC Message | The hour in the text of the HRUC alert that is available to all MPs is offset by one hour. Startup/Shutdown Instructions for individual QSE awards are correct. Example: HRUC-AWD-RPT Reports on HRUC Awards for operating date 12/06/2010 hr 21 are available. Should say hr 20. | 2011-01-20 | Market Management System
14113 | EWS Sync Response loses correlation with async for schema errors | When inbound submissions fail to validate to the schema, ensure that the mRIDs associated to that submission are returned in the Notification message. | 2011-01-21 | Enterprise Web Services
15195 | SHORT DST - Market Info: SystemLoad, the time of EWS response is incorrect when the TimeEnding of CDR report is 3:00 on short day (CST->CDT). | SystemLoad has incorrect time after Daylight Savings Time transition. | 2011-01-21 | Enterprise Web Services
15220 | SHORT DST - Market Info: SPPs_DAM, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15235 | SHORT DST - Market Info: TotalEnergys, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15276 | SHORT DST - Market Info: MarketTotals, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15277 | SHORT DST - Market Info: BindingConstraints, the deliveryTime of EWS response is incorrect when the HourEnding of CDR report is 2:00 or RUCTimeStamp of CDR report is 14:xx:xx on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15278 | SHORT DST - Market Info: AggregatedASOfferCurves, the endTime of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15292 | SHORT DST - Market Info: ASServicePlan, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15293 | SHORT DST - Market Info: TotalASOffers, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15314 | SHORT DST - Market Info: SPPs_RTM, both time and ending of EWS response are incorrect when the DeliveryDate of CDR report is short day (CST->CDT). | For the day in which CST to CDT takes place, the SPP reports are reported with a -06:00 offset when it should be -05:00 after the CDT transition. | 2011-01-21 | Enterprise Web Services
15348 | SHORT DST - Market Info: DynamicRatings, the createTime of EWS response is incorrect when CreateTime of CDR report is short day (CST->CDT). | Market Info: DynamicRatings, the createTime of EWS response is incorrect when CreateTime of CDR report is short day 3/14/2010 (CST->CDT). | 2011-01-21 | Enterprise Web Services
15353 | SHORT DST - Market Info: LoadRatioShares, both time and ending of EWS response are incorrect when DeliveryDate of CDR report is short day (CST->CDT) and HourEnding of CDR report is 24:00. | Market Info: LoadRatioShares, both time and ending of EWS response are incorrect when DeliveryDate of CDR report is short day 3/14/2010 (CST->CDT) and HourEnding of CDR report is 24:00. | 2011-01-21 | Enterprise Web Services
15368 | SHORT DST - Market Info: LoadForecasts, both time and ending of EWS response are incorrect when the HourEnding of CDR report is 1:00 and 2:00 and DeliveryDate of CDR report is short day (CST->DST). | Market Info: LoadForecasts (LOAD, SYSTEM and WEATHER), both time and ending of EWS response are incorrect when the HourEnding of CDR report is 1:00 and 2:00 and DeliveryDate of CDR report is short day 3/14/2010 (CST->DST). | 2011-01-21 | Enterprise Web Services
15392 | SHORT DST - Market Info: TotalLoad, the time of EWS response is incorrect when the TimeEnding of CDR report is 03:XX and the DeliveryDate is short day (CST->DST). | For the TotalLoad report, the time in the response is incorrect when the TimeEnding of CDR report is 03:XX and the DeliveryDate is short day 3/14/2010 (CST->DST). | 2011-01-21 | Enterprise Web Services
17670 | Invalid time values for TotalLoad market info service. | Total Load report available via EWS is reporting at an incorrect time interval. | 2011-01-21 | Enterprise Web Services
17821 | Support disabling of individual adapters in EWS | Provide method to return accurate information on the availability of the EWS transaction. | 2011-01-21 | Enterprise Web Services
17266 | MPIM - ITEST - Enhancement - Certificate Renewal Emails Do Not Contain the DUNS | The MP will not see a DUNs within the email they receive to renew their digital certificate. | 2011-01-23 | Market Participant Identity Management
15269 | DST-NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. | .NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. Fixes putting '*' by extra hour during Fall DST transition. | 2011-02-23 | Current Day Reports
18423 | CRR: MUI Downloads: Error message "System is experiencing difficulties" during market results posting | Market Participants are unable to download Private Results after market posting due to a resource conflict in the application. | 2011-02-23 | Congestion Revenue Rights
18424 | CRR: MUI Downloads: Time Stamp of the Network and Market download files is earlier than when the market is first posted | Download files are using GMT time in the MUI rather than CPT; in some instances, the files appear to have been written prior to when the market results were posted. | 2011-02-23 | Congestion Revenue Rights
18425 | CRR: MUI Downloads: Market Results download files were not generated after an auction was posted | Download files were not created as a result of resource conflict while market participants were attempting to download files as the system was trying to write them. A separate process is now dedicated to the writing of the files; this is related to defect 18423. | 2011-02-23 | Congestion Revenue Rights
18619 | CRR: MUI Portfolio Editor: Auction Portfolio allows users to enter a 0 price for Options and save the Portfolio | CRR portfolio editor allows a zero priced OPTION to be saved and submitted to an auction. Minimum price for an Option should be $0.01. | 2011-02-23 | Congestion Revenue Rights
18622 | CRR: MUI Downloads: Monitored lines and transformer download file was not checking the last modified date to know when to display new data | When updates to the limits were made in the Market Operator interface, the timestamp on the datacase was not updated to reflect the changes, and hence, the monitored lines and transformers file was not updated for the Market Participant. | 2011-02-23 | Congestion Revenue Rights
18654 | Two State Estimator - ER reports not available on MIS SE Reports portlet | These EDW reports are available via the MIS Reports and Extracts page, but not on the SE Reports and Index portlet. | 2011-02-23 | Market Information System
18664 | CRR: MUI Credit Limit Editor: Unable to open credit limit editor page due to missing parameter (for both Market Participant and Counterparty) | System not available message was displayed for the credit limit editor due to a missing parameter in the system. | 2011-02-23 | Congestion Revenue Rights
18665 | Add new link to Data Aggregation page: NP9-288-SG, IDR Protocol Compliance Verification for Disputes | Missed requirement | 2011-02-23 | Market Information System
18745 | Urgent request for FERC Data Requests link to be added to MIS in a new certified portlet Compliance - FERC | Without adding the new role, the new portlet and the new link, these data requests will not be available to FERC certificates. | 2011-02-25 | Market Information System
18329 | CDR NP7-464 - Day Ahead Point-to-Point Option Price Report - Retry Creation Time stamp is incorrect | Fix to correct retry creation time stamp. | 2011-02-28 | Current Day Reports
18485 | NP7-807 - RealTime Point To Point Prices Options report - Lacks Automated Retry Funtionality. | This fix will create automated retry funtionality. | 2011-02-28 | Current Day Reports
18541 | New CDR report needed: NP6-627 State Estimator Bus Voltages | New CDR report needed. | 2011-02-28 | Current Day Reports
18543 | NP6-619-CD Hourly SE Transmission Line Flows: Update list of lines to be posted | Update list of lines to be posted. | 2011-02-28 | Energy Management System
18544 | PUCT Rule requires a new report posting: NP6-627-CD, State Estimator Bus Voltages | PUCT required new report, SE Bus Voltages; must be available by 3/1. | 2011-02-28 | Market Information System
18555 | NP7-464 Updates to Run Time and Query Logic | When DAM is delayed and results are not published by 1500, then the previous day's data is published. Changing the posting to be published at 1800 should account for most days when DAM is delayed. Also, adding logic to the query for the posting to look for sysdate+1 will ensure that the previous day's DAM data is not posted for this report. | 2011-02-28 | Current Day Reports
18593 | NP6787 - LMPs by Electrical Buses: Fix Spring DST date logic | NP6787 - LMPs by Electrical Buses | 2011-02-28 | Current Day Reports
18594 | NP6788 - LMPs by Resource Nodes, Load Zones: Fix Spring DST date logic | NP6788 - LMPs by Resource Nodes, Load Zones | 2011-02-28 | Current Day Reports
18595 | NP7807 - SPP Real Time Point to Point Option Price Report: Fix Spring DST date logic | NP7807 SPP Real Time Point to Point Option Price Report | 2011-02-28 | Current Day Reports
18596 | NP5200 - Contingencies Deselected in RUC: Fix Spring DST date logic | NP5200 Contingencies Deselected in RUC | 2011-02-28 | Current Day Reports
18597 | NP5649 - Temporarily Removed Contingencies: Fix Spring DST date logic | NP5649 - Temporarily Removed Contingencies | 2011-02-28 | Current Day Reports
18598 | NP5752 - Hourly RUC Committed or Decommitted Resources: Fix Spring DST date logic | NP5752 - Hourly RUC Committed or Decommitted Resources | 2011-02-28 | Current Day Reports
18599 | NP5755 - Hourly RUC Active and Binding Transmission Cons.: Fix Spring DST date logic | NP5755 - Hourly RUC Active and Binding Transmission Cons. | 2011-02-28 | Current Day Reports
18600 | NP686 - SCED Shadow Prices and Binding Transmission Constr.: Fix Spring DST date logic | NP686 - SCED Shadow Prices and Binding Transmission Constr. | 2011-02-28 | Current Day Reports
18601 | SYS608 - Shift Factors: Fix Spring DST date logic | SYS608 - Shift Factors: Fix Spring DST date logic | 2011-02-28 | Current Day Reports
18602 | NP6635CDB - Online Generation Actual (Load Forecast vs Actual): Fix Spring DST date logic | NP6635CDB - Online Generation Actual (Load Forecast vs Actual) | 2011-02-28 | Current Day Reports
18607 | NPR6635EDB - Actual Load (Load Forecast vs Actual): Fix Spring DST date logic | NPR6635EDB - Actual Load (Load Forecast vs Actual): | 2011-02-28 | Current Day Reports
18653 | NP6-905 Add delivery time timestamp to end of file name | Add delivery time timestamp to end of file name. | 2011-02-28 | Current Day Reports
18670 | CDR NP3-129 - Daily Competitive Constraints. Enhancement to have the report shall pull and post competitive constraints only. | Enhancement to have the report pull and post competitive constraints only. | 2011-02-28 | Current Day Reports
18758 | CDR NP4-183 - Fix the re-try functionality of this report | Fix re-try functionality | 2011-02-28 | Current Day Reports
10610 | OS UI All: Group: Sections reopen when I click though the linked Outage ID in a group table | In the details of a group outage, if the user collapses one of the areas of the outage information then clicks on another outage in the "Equipment in Group" section, the collapsed area reopens. | 2011-03-23 | Outage Scheduler UI
12022 | All price within a CRR offer/PTP Bid Hour Block should be Same | The system accepts submissions of PTP Bids and CRR Offers that are blocked across time and have different MW and Price values within the time block. These are not valid offers and bids and should be rejected. The defect fix will remove the ability to specify different MW and price for time-blocked offers and bids. | 2011-03-23 | Market Management System
12337 | OS Core:: TSP: Forced Submit -missing fields from screen | The forced outage submit does not display the primary and secondary phone numbers | 2011-03-23 | Outage Scheduler UI
17848 | NER63 MIS - ITEST - "Load Forecast vs. Actual" dashboard - Graph Truncates on Landing Page | Market will see graph as is | 2011-03-23 | Market Information System
17943 | OS UI Copy when going from a PL to a FR you should not include a ES on the create | When an MP copies a Planned Outage and then changes the copied outage to a Forced outage when submitted they receive an error message then the Earliest Start should be equal to or less than the Planned Start. | 2011-03-23 | Outage Scheduler UI
18554 | Self Energy Trade Net Trade of Letter Other Than 'P' or 'S' Not Handled Properly | If the letter for the Net Trade is entered as say a 'D' as opposed to a 'P' or an 'S' during the creation of a self energy trade, the UI gives an appropriate error message, but not all bad fields are highlighted. This fix will highlight all the fields in error. | 2011-03-23 | Market Management System
18644 | Notices tab cannot display special characters | This fix displays any special characters entered in the Notices Tab. | 2011-03-23 | Market Management System
18729 | TDSP role missing for the Settlement Reports and Extracts (Certified) portlet | Added TDSP_Extracts role for the RTM CODE on the Settlements page in MIS. | 2011-03-23 | Market Information System
18730 | RE role missing for the QSE Real Time Market portlet | Certificates with an RE_Extracts role cannot access the Manual Over-riding of HDLs and LDLs in MIS. | 2011-03-23 | Market Information System
18742 | Day-Ahead Market Credit Requirements Procedure for eFactors not posting to collage | Link name change Link name changed to Day Ahead Market (DAM) Collateral Parameters Process (eFactors) on the DAM page. | 2011-03-23 | Market Information System
18819 | UFE Analysis Report is pointing to a Report Typd ID in MIR when it should point to an ERCOT.com URL | Link pointed to a report type ID and it should be directed to ercot.com. | 2011-03-23 | Market Information System
18833 | NP6905 - Change the retry functionality for this report from batch id to execution timestamp | NP6905 - Change the retry for this report from batch id to execution timestamp | 2011-03-23 | Current Day Reports
18846 | EWS Submissions fail with Nouns: BidSetNotifications, ResParameterSetNotifications, VDIsNotifications | TBD | 2011-03-23 | Enterprise Web Services
18848 | Link name change for 'Day-Ahead Market Credit Requirements Procedure for eFactors' | Link name changed to Day Ahead Market (DAM) Collateral Parameters Process (eFactors) | 2011-03-23 | Market Information System
18849 | NPRR 276 adds an MIS public posting requirement for Network Operations Model Load Schedule | Added a public portlet on the Grid - Long-Term Planning Page with one link: Network Operations Model Load Schedule | 2011-03-23 | Market Information System
18171 | EIP Spec Doc Update - Add 3 new notifications that NoticeBuilder recently added (in NCR184) | EIP Spec Doc needs updates | 2011-03-25 | Enterprise Web Services
18287 | Itest MPIM - Tracking defect for updating the MP email correspondence | The MP is receiving an email that is prompting them to contact their DC USAs. This is a miscommunication delivered in the automatic generated email notification from MPIM. | 2011-03-27 | Market Participant Identity Management
18518 | Siebel - New Sub types for Service Request under type Registration | the MP's whom have a valid DC and can access SR/SD will be able to view and access the additional SR types via MIS/TML | 2011-03-27 | Registration
18534 | Siebel - eService Screen is not refreshing the Charge Type Values when we Select other Dispute sub-Type value | eService is viewable to the MP's that have a valid DC and has the correct role to access nodal settlement disputes via MIS and/or TML | 2011-03-27 | Registration
18559 | MPIM - MPIM screen displays Some Frame Page | The USA's can access MPIM and see the tab labeled Some Frame Page. | 2011-03-27 | Market Participant Identity Management
18124 | NP3-987 7-Day Event Trigger Posting when LMP exceeds 50xFIP - Fix Fall DST time issue | NP3-987 7-Day Event Trigger Posting when LMP exceeds 50xFIP - Fix is on Fall DST | 2011-03-31 | Enterprise Data Warehouse
8777 | OS UI Usability: Warnings:column headings are not visable with the data | Once you have more than 6 warnings, and you scroll down the page, you can no longer see the column headings. | 2011-04-20 | Outage Scheduler UI
8883 | OS UI : Show Hide columns: Listed issues when logged in as a TSP/QSE | The OS UI show hide column "Check All"/"UNCheck All" isn't checking or unchecking all the boxes. | 2011-04-20 | Outage Scheduler UI
9761 | OS UI: Copying an outage from the Success screen does not copy Notes | When the MP copies an existing outage that has Requestor Notes, the original notes are being copied. | 2011-04-20 | Outage Scheduler UI
10343 | OS UI Usability: When the Custom Filter is open sort of a colum in the table should not close the filter | When the MP sorts a column the filter closes the MP must reopen the filter to see their current choices for the flter. | 2011-04-20 | Outage Scheduler UI
17943 | OS UI Copy when going from a PL to a FR you should not include a ES on the create | When an MP copies a Planned Outage and then changes the copied outage to a Forced outage when submitted they recieve an error message then the Earliest Start should be equal to or less than the Planned Start. | 2011-04-20 | Outage Scheduler UI
18203 | OS UI - QSE equipment cannot be deleted without causing an application error. | The user may refresh the page, after deleting any equipment, and then re-enter the equipment row. | 2011-04-20 | Outage Scheduler UI
18525 | OS: Extensions to 2.3.0 | For the Nature of work Retirement Old Equipment outages are auto ended on their end date For the Nature of work New Equipment Energization outages are auto started on their start date | 2011-04-20 | Outage Scheduler
18538 | OS: NPE can't move a NPE inward for both QSE and TSP all outage types | New Planned End cannot be moved inward. This should be allowed as long as none of the original date rules are broken. | 2011-04-20 | Outage Scheduler
18683 | OS: Do not auto populate the AE when the Nature of Work New Engerization is selected | The AE is not auto-populated when the user selects New Equipment Energization | 2011-04-20 | Outage Scheduler
19015 | EILS Posting Name Changes | Business name changes - change in link names on MIS for EILS Load Submission Form-Approved, EILS Award Notification for Upcoming Contract Period, EILS Preliminary Baseline Review Results, EILS Load Submission Form-Error Reports, EILS Load Event Performance Evaluation Results, EILS Pre Populated ELID Forms | 2011-04-20 | Market Information System
19017 | 60 Day Disclosure Reports bundled | Change the one MIS link for 60 Day Disclosures into two : 60 Day SCED Disclosure Reports and 60 Day DAM Disclosure Reports | 2011-04-20 | Market Information System
19023 | 48 Hour Disclosure Reports bundled into four groups & consistency of link formats | Change the one MIS link for 48-hour Disclosure Reports into four: 48 Hour DAM and SCED Energy Curves Reports, 48 Hour DAM Bids and Offers Reports, 48 Hour Real Time Gen and Load Data Reports and 48 Hour Ancillary Services Reports | 2011-04-20 | Market Information System
7826 | OS Core Res PL: InService - Can successfully submit an outage when its duration (Start and End date/time) is spanning the Inservice date of the equipment | the user can enter an outage on a new piece of equipment with a Planned Start before the Inservice date of the equipment. | 2011-04-21 | Outage Scheduler
7922 | TSP Issues List: OS Core All: TSP: From Station is assigned to only one end of a line. | When the user is entering an outage on a Line, the From Station is only assigned to one end of the line. Both "to" and "from" station will now be avaiable to select from in the Outage | 2011-04-21 | Outage Scheduler
8693 | OS Core Withdrawn Active outages: Should be able to enter notes along with Actual End | When the MP is entering the Actual End, they are not able to enter notes at the same time. | 2011-04-21 | Outage Scheduler
8883 | OS UI : Show Hide columns: Listed issues when logged in as a TSP/QSE | The OS UI show hide column "Check All"/"UNCheck All" isn't checking or unchecking all the boxes. | 2011-04-21 | Outage Scheduler UI
9476 | OS UI Planned: Recurring Outages: One extra outage is scheduled, than expected | When entering a recurring outage, the system is adding one extra outage to the recurring outage list. | 2011-04-21 | Outage Scheduler UI
9489 | OS UI: Planned: Recurring Outages: Cannot enter '50' in the Repeat Times field if Days field has more than 1 | When entering a recurring outage, if the user tries to enter 50 recurrences, the system is adding one extra outage to the recurring outage list making the total 51 and gives the user the error "Enter the number of times. The number of times multiplied by the days cannot exceed 50. Use whole numbers, but not characters or ()&@" | 2011-04-21 | Outage Scheduler UI
17502 | NP3-579 - MW Residuals - SE vs RTCA Base Case for Congested Transmission Elements Report - Column order change | Enhancements to change column order and description tab information only for NP3-579 - MW Residuals - SE vs RTCA Base Case for Congested Transmission Elements Report . | 2011-04-21 | Reports
17503 | NP3-580 - MW Residuals - SE vs Telemetry for Congested Transmission Elements Report - Column order change. | Enhancements to change column order and description tab information only for NP3-580 - MW Residuals - SE vs Telemetry for Congested Transmission Elements Report. | 2011-04-21 | Reports
17504 | NP3-581 - MW Residuals - SE vs Telemetry for Major Transmission Elements Report - Report description change. | Enhancements to change column order and description tab information only for 'NP3-581 - MW Residuals - SE vs Telemetry for Major Transmission Elements Report . | 2011-04-21 | Reports
18214 | Once an outage is submitted the TSP should be able to shorten an outage to less than the outages restoration time. | TSP is not able to shorten an outage to be less than the outage restoration time. | 2011-04-21 | Outage Scheduler
18252 | 60 Day disclosure reports - SCED Curves | 60-Day reports broken into two: SCED reports are bundled in one extract. | 2011-04-22 | Reports
18253 | 60 day disclosure reports - DAM Curves | 60-Day reports broken into two: DAM reports are bundled in one extract. | 2011-04-22 | Reports
18190 | Deferred - SYS-608-CD - Shift Factors | Change report to pull active binding and violated constraints only. No longer pulling non-binding constraints. | 4/25-4/26/2011 | Reports
18669 | Stabilization - NP6788DB - Option to include retries on report or just inserting 1 data row but also updating previous hours/day | Enhancement to dashboard to include ability to update prior hour/day | 4/25-4/26/2011 | Reports
18921 | Change Posting of NP8-142 from being Date/Time Driven to being Event Driven | Change frequency of NP8-142-CD to Event Driven following close of DRUC | 4/25-4/26/2011 | Reports
8801 | OS UI Show Hide Column: Check all does not uncheck when you uncheck all of the supporting fields | In the OS UI show hide columns, when the user unchecks the items from the list the top control check box stays checked even when all of the items from the list are unchecked. | 2011-05-18 | Outage Scheduler UI
16566 | OS UI 0.12.13 Missing required field validaion on the TOO OP from | Using the OS UI, when the requestor is trying to submit a Transmission Opportunity Outage (TOO) and some of the required fields are missing, i.e. Operating Company for the designated Resource, Opportunity Window, the OS UI client side validation isn't catching the missing data. The missing data is caught by the Outage Scheduler rules engine. | 2011-05-18 | Outage Scheduler UI
18512 | MMS MM - VDI screen not sorting correctly | When clicking on the column header on the VDI screen on the Market Manager, the columns do not sort properly. | 2011-05-18 | Market Management System UI
18638 | Market Manager Query of Energy-Only Offers Can Yield Incorrect From Hr End | This could be misleading to a Market Participant where they think an offer or bid was entered for more hours than was their intention. Drilling down to the details of the offer or bid yields what hours are actually in the offer or bid. | 2011-05-18 | Market Management System UI
18912 | Automate Generation and Posting of CDR Report NP4-194 NPRR293/303 | Currently, only a csv of this report is posted but automating this will also generate an xml version of the report. | 2011-05-18 | Current Day Reports
18980 | Each search of MP moves returned data to the right of the screen | An MP who has a USA dc can terminate users. | 2011-05-19 | Market Participant Identity Management
19004 | Misspelling of Participant in MPIM | The MP USA DC holders have the same view. | 2011-05-19 | Market Participant Identity Management
13910 | (SER135) OS UI 19: Summary - XML - voltage is in scientific notation | The xml stores the voltage field in scientific notation instead of a whole number; this will now be stored as a whole number. | 2011-05-20 | Outage Scheduler UI
17962 | Enable SCED Completion alerts to MPs | ERCOT will be adding a new alert to notify QSEs every time SCED completes. You can view the details of this alert in section 5.3.1.1 of the External Interfaces Specification posted at http://www.ercot.com/services/mdt/xsds/index | 2011-05-20 | Market Management System
18873 | (SER135) Three Part Offers Fail mapping when time offset is +00:00 | Three Part Offers are failing if the expirationTime contains a time stamp where the time offset is +00:00. While this is an unusual time format to use, it is a valid timestamp. | 2011-05-20 | Enterprise Web Services
17268 | Display Name not Referenced in the Reports | When running a report, the user will see the ROLE_ID listed. | 2011-05-22 | Market Participant Identity Management
18689 | Siebel - Emails to MP's on rejected Nodal Disputes | An email notification will be sent to the MP's when the dispute status is updated. | 2011-05-22 | Registration
8378 | OS Core TOO: Editing the dates on a resource submission to fall with in the Opportunity window of an exisiting TOO should get a TOO match message. | When dates on a resource outage are edited to fall within the Opportunity window of an exisitng TOO, TSP and ERCOT will receive a TOO match message. | 2011-06-22 | Outage Scheduler
10398 | OS Core Usability - All Group - Error messages don't need to be repeated at the top for the same reason. | Group outage will only display one error message for each error type. | 2011-06-22 | Outage Scheduler
11631 | Row headers are no longer visible after scrolling to the right. | When viewing bid/offer details, the row headers will stay visible when scrolling to the right. | 2011-06-22 | Market Management System UI
15536 | OS Core OS 2.2.0 TOO Designated Resource does not rematch when the length of the designated resource is shortend and then re-lengthened. | Changing the duration of a Resource Outage to less than the duration of the Transmission Outage will cause the TOO to reset. Lengthening the Resource Outage duration again to be within the window of the TOO will rematch the TOO and and Resource Outage. | 2011-06-22 | Outage Scheduler
16849 | OS UI 0.12.17 TOO screen is missing client side validation on Opportunity Window End and HSL. | Client-side validation is being expanded to look at any missing fields and force entry before proceeding with a TOO. | 2011-06-22 | Outage Scheduler UI
17230 | OS UI 0.12.18 - Take Opportunity is displaying on non ROO grouped outages. | The take opportunity radio buttons will only display when a resource opportunity exists. | 2011-06-22 | Outage Scheduler UI
17231 | OS UI 0.12.18 QSE - When you delete a row from a group on create, it will clear the group name causing the user to have to re-enter group name before submitting. | Deleting an equipment row from a grouped Resource Outage while creating will maintain the group name. This only affects the QSE resource outages. | 2011-06-22 | Outage Scheduler UI
18201 | OS UI - Requestor Phone number - adding a 0 to the end of the phone number causes a communication error. | Client-side validation is being added to the format of the phone number to force the user to make correction before submitting the outage. | 2011-06-22 | Outage Scheduler UI
18897 | ACL Summary External report - Collateral section data | Previous day Collateral transactions will be displayed in this section. | 2011-06-22 | Reports
18898 | ACL Summary Report - Prepayment section data | Previous day Prepayment transactions will be displayed in thise section. | 2011-06-22 | Reports
19033 | MMSUI notice tab display doesn't work if priority field is not entered through notice builder application. | The Notice tab will not require priority to display a Notice in the MMS MM UI. | 2011-06-22 | Market Management System UI
19146 | CDR Report NP5-753 (Weekly RUC Active and Binding Transmission Constraints) is not pulling the records for a published WRUC results. | Changing the CDR Report to be event triggered. | 2011-06-22 | Reports
19241 | Development of two new MIS Secure reports (Daily and Hourly) that list any changes made by ERCOT to the DRUC or HRUC recommended commitments along with an explanation of the change | Two missed protocol requirements to post list of any changes made by ERCOT to the DRUC or HRUC recommended commitments along with an explanation of the change. | 2011-07-22 | Current Day Reports
19285 | CDR Reports NP4-19 & NP4-179 Not Posting Normally | In its current state, these two reports (DAM Aggregated Ancillary Service Offer Curve & DAM Total Ancillary Service Offers) will not post with the rest of the DAM reports right after DAM is published. |  | Current Day Reports
3554 | Siebel E-services Screen Help information not updated Nodal settlement disputes | When the MP access the Help option under the eService view covering Nodal Settlement disputes, it does not list the new fields for Nodal Disputes, only have the information pertaining to Zonal disputes. | 2011-08-28 | Registration
3614 | Siebel E-Service Market Type field not available on the Find Nodal Settlement Dispute screen to Query Market Type and Status | Market Participants can use other search features. Searching by status or id number | 2011-08-28 | Registration
3554 | Siebel E-services Screen Help information not updated Nodal settlement disputes | When the MP access the Help option under the eService view covering Nodal Settlement disputes, it does not list the new fields for Nodal Disputes, only have the information pertaining to Zonal disputes. | 2011-08-28 | Registration
3614 | Siebel E-Service Market Type field not available on the Find Nodal Settlement Dispute screen to Query Market Type and Status | Market Participants can use other search features. Searching by status or id number | 2011-08-28 | Registration
14895 | Siebel - Add a URL link to the SR# that opens directly to the SR through eService | The MP's will be able to click on the link and it will take them to the Dispute data via MIS/TML. | 2011-10-21 | Registration
18623 | Siebel - Multiday dispute not populating end trade date with the valid date | Multiday disputes are submitted by the Market Participants via MIS or TML using eService. |  | Registration
18850 | Service Request sub-type QSE Acknowledge | MP's with valid digital certificates that have access to MP ASSESTS will be able to access the new drop down option via eServices =>Create or view Service Requests |  | Registration
14895 | Siebel - Add a URL link to the SR# that opens directly to the SR through eService | The MP's will be able to click on the link and it will take them to the Dispute data via MIS/TML. | 2011-10-21 | Registration
18623 | Siebel - Multiday dispute not populating end trade date with the valid date | Multiday disputes are submitted by the Market Participants via MIS or TML using eService. | 2011-08-28 | Registration
18850 | Service Request sub-type QSE Acknowledge | MP's with valid digital certificates that have access to MP ASSESTS will be able to access the new drop down option via eServices =>Create or view Service Requests | 2011-08-28 | Registration
19182 | CRR MUI and MOI: 4MB file upload limit | File uploads to Application interface are limited to 4MB in size. |  | Congestion Revenue Rights
19183 | CRR MUI: do not want Allocation network files to be visible | Network files for Allocation market are created. |  | Congestion Revenue Rights
19217 | No negative prices in MUI or MOI binding constraint reports | Requires market notice beforehand as it would change our Market Results reports. |  | Congestion Revenue Rights
19235 | CRR MUI: Multiple bid id's for a sell offer in the same portfolio is not allowed | Sell offers, when offered in separate segments, cannot be placed in the same portfolio. Each offer for the CRR must be in a separate portfolio. |  | Congestion Revenue Rights
19236 | CRR MUI: Sell OPT offer does not allow 0.00 bid price | Cannot enter a SELL bid in the Portfolio Editor for a $0.00 OPT |  | Congestion Revenue Rights
19237 | CRR MUI: Existing CRR's dropdown disappears when market is targeted in portfolio editor | Portfolio editor loses memory of existing crr's when a new portfolio is 'targeted' to an auction. |  | Congestion Revenue Rights
19274 | MUI: Monthly and Annual Private Results contain pricingFactor and priceFactor in XML tags and csv files | Private Downloads for Allocation market results show PriceFactor for the Annual results, and PricingFactor for the monthly results. |  | Congestion Revenue Rights
18248 | Changes on 48-Hour DAM and SCED Energy Curves Reports | 48-Hour Disclosure reports with SCED curves are bundled in one extract. | 2011-08-24 | Enterprise Data Warehouse
18250 | Changes on 48-Hour Real Time Gen and Load Data Reports | 48-Hour Disclosure reports with SCED non-curves are bundled in one extract. | 2011-08-24 | Enterprise Data Warehouse
14215 | Cancellation of Output Schedule not allowed for DSR in the middle of an hour | Cancellation of individual 5-minute intervals within an hour of an Output Schedule is not possible. Output Schedules can only be canceled in whole hour increments only. |  | Enterprise Integration
14988 | OS Station is displaying the Station Acronym | When the MP is entering an outage or looking at the summary page the From Station is displaying the Station Acronym. |  | Enterprise Integration
17386 | OS UI 0.12.19 - Associated Equipment Table needs to be sorted From Station, Type and then Name | When the MP is entering an outage on a line using the OS UI, they have an option to show related equipment. This equipment list should be sorted by the "From Station" then "Equipment Type". | 2011-08-24 | Enterprise Integration
14215 | Cancellation of Output Schedule not allowed for DSR in the middle of an hour | Cancellation of individual 5-minute intervals within an hour of an Output Schedule is not possible. Output Schedules can only be canceled in whole hour increments only. |  | Enterprise Integration
14988 | OS Station is displaying the Station Acronym | When the MP is entering an outage or looking at the summary page the From Station is displaying the Station Acronym. | 2011-09-23 | Enterprise Integration
17386 | OS UI 0.12.19 - Associated Equipment Table needs to be sorted From Station, Type and then Name | When the MP is entering an outage on a line using the OS UI, they have an option to show related equipment. This equipment list should be sorted by the "From Station" then "Equipment Type". | 2011-08-24 | Enterprise Integration
17221 | Gaps in EMS external Alerts - 3 Issues ( 1 fixed, 2 pending) | Notification of insufficient AS Supply Responsibility if detected between EMS and MMS systems. | 2011-08-24 | Energy Management System
18108 | NP5-649: Temporarily Removed Contingencies: EMS table view needs to show a record for each removed contingency for each RTCA execution in the hour | NP5-649: Temporarily Removed Contingencies: EMS table view needs to be fixed to show records for removed contingencies for ALL RTCA executions in the hour. Currently only one record per contingency is showing for each hour. | 2011-09-21 | Energy Management System
16556 | MIS - Find ESIID page displays differently in MIS than it does via TML | Once the retail apps via MIS are live the market participants can view txns details. At this time they are currently using TML. | TBD | Market Information System
16557 | MIS - Find ESIID page displays 'Some frame page' on the window frame header bar | Market Participants use this screen via the UI to verify txns data. | TBD | Market Information System
17688 | NER63 MIS - ITEST - SCED Up Down dashboard - Missing Hover Capability To Drill Into Data Points | the information available in the dashboard will be missing | TBD | Market Information System
17689 | NER63 MIS - ITEST - Day-Ahead and Real-Time LMPs dashboard - Modify to move from individual screen/graph per LMP to a single graph with up to 10 LMPs overlaid together. | the information available in the dashboard will be missing |  | Market Information System
18558 | MIS Notices - Operator notices should remain available for 14 days | Operator notices are currently only available for 7 days. This defect is exploring the ability to increase this availability. | TBD | Market Information System
18818 | eService is displaying Texas Market Link in window | eService is viewable to the MP who currently has a valid DC and has access to create/submit/view SD or SR. |  | Market Information System
18872 | Move QSE Availability and Performance Summary for EILS Contract Period from the RTM page to the Services page | This certified link displays on the wrong page. Should be on the Services Landing page in the EILS Certified Data portlet. | 2011-07-22 | Market Information System
7426 | TEST FIRST: MMS - DST MI BackgrProcs SPP Calculation fails in Long Day | SPP Calculation fails in Long Day (i.e., fails during the repeated hour in the DST transition day from CDT to CST) | 2011-09-21 | Market Management System
7426 | TEST FIRST: MMS - DST MI BackgrProcs SPP Calculation fails in Long Day | SPP Calculation fails in Long Day (i.e., fails during the repeated hour in the DST transition day from CDT to CST) | 2011-09-21 | Market Management System
16850 | Need to add notification to participants for AS Capacity Monitoring | ERCOT is required to continuously compare the sum of the QSE's Resource AS Responsibilities in the EMS (already calculated within the EMS) with the QSE's total AS Supply Responsibility in the MMS system. This comparison should be done separately for Regulation Up, Regulation Down, RRS, and NSRS, and then noticed via web service alerts and MIS Certified postings for instances in which the comparison indicates that the EMS value for any of the four services is less than the MMS value. This issue has been logged to track progress toward building the EMS notification into web services. | 2011-07-22 | Market Management System
19138 | TPO resubmission validation rule not properly enforced when DRUC_POST | Between the time that DRUC publishes results and the adjustment period opens, Three-Part Offer updates are allowed for DAM- and RUC-committed intervals. QSEs need to be cautious not to update their offers DAM- or RUC- committed intervals during this time unless a protocol-required appropriate reason code is given. | 2011-07-22 | Market Management System
19250 | app_sced failed to create mitigated offer curve when the mitigated cap doesn't cover entire curve | Mitigated offer curve will not be created if mitigated cap doesn't cover the entire offer curve or if the resource is OFFLINE. | 2011-06-22 | Market Management System
16850 | Need to add notification to participants for AS Capacity Monitoring | ERCOT is required to continuously compare the sum of the QSE's Resource AS Responsibilities in the EMS (already calculated within the EMS) with the QSE's total AS Supply Responsibility in the MMS system. This comparison should be done separately for Regulation Up, Regulation Down, RRS, and NSRS, and then noticed via web service alerts and MIS Certified postings for instances in which the comparison indicates that the EMS value for any of the four services is less than the MMS value. This issue has been logged to track progress toward building the EMS notification into web services. | 2011-07-25 | Market Management System
19138 | TPO resubmission validation rule not properly enforced when DRUC_POST | Between the time that DRUC publishes results and the adjustment period opens, Three-Part Offer updates are allowed for DAM- and RUC-committed intervals. QSEs need to be cautious not to update their offers DAM- or RUC- committed intervals during this time unless a protocol-required appropriate reason code is given. | 2011-07-25 | Market Management System
19250 | app_sced failed to create mitigated offer curve when the mitigated cap doesn't cover entire curve | Mitigated offer curve will not be created if mitigated cap doesn't cover the entire offer curve or if the resource is OFFLINE. | 2011-06-22 | Market Management System
2749 | All: Submissions for the Operating day : Feb 29 is giving error notification | No workaround, but not needed until Feb 29, 2012 |  | Market Manager
11631 | Row headers are no longer visible after scrolling to the right. | When viewing bid/offer details, the row headers do not stay visible when scrolling to the right, so the user may lose track of what each row is for. | 2011-06-22 | Market Manager
14472 | Verbose Error Messages | Some error messages returned by the MMS UI may contain technical implementation details (such as java exceptions). | 2011-09-21 | Market Manager
14473 | Cross-Site Request Forgery (CSRF) | The MMS UI is vulnerable to cross-site request forgery. | 2011-09-21 | Market Manager
18512 | MMS MM - VDI screen not sorting correctly | When clicking on the column header on the VDI screen on the Market Manager, the columns do not sort properly. |  | Market Manager
18860 | SASM AS Awards Being Displayed in MM for a run on DST Short Day are shifted an hour later | If an MP looks only at the Market Manager to verify their SASM awards for a SASM run on the DST Short Day, their award will show up an hour later than it should. An award for HE 08 shows up in HE 09. The associated XML is displays the award for the right hour. | 2011-07-22 | Market Manager
18874 | In Market Manager for DST Short Day, HE 0200 is displayed as HE 0300 | For QSEs viewing bids, offers, and awards only via the Market Manager, there could be confusion as to which hour they are looking at on the DST Short Day. Instead of the Market Manager showing HE 0200 as 0200, it is displayed as HE 0300. | 2011-07-22 | Market Manager
14472 | Verbose Error Messages | Some error messages returned by the MMS UI may contain technical implementation details (such as java exceptions). | 2011-09-21 | Market Manager
14473 | Cross-Site Request Forgery (CSRF) | The MMS UI is vulnerable to cross-site request forgery. | 2011-09-21 | Market Manager
18512 | MMS MM - VDI screen not sorting correctly | When clicking on the column header on the VDI screen on the Market Manager, the columns do not sort properly. | 2011-07-25 | Market Manager
18860 | SASM AS Awards Being Displayed in MM for a run on DST Short Day are shifted an hour later | If an MP looks only at the Market Manager to verify their SASM awards for a SASM run on the DST Short Day, their award will show up an hour later than it should. An award for HE 08 shows up in HE 09. The associated XML is displays the award for the right hour. | 2011-07-25 | Market Manager
18874 | In Market Manager for DST Short Day, HE 0200 is displayed as HE 0300 | For QSEs viewing bids, offers, and awards only via the Market Manager, there could be confusion as to which hour they are looking at on the DST Short Day. Instead of the Market Manager showing HE 0200 as 0200, it is displayed as HE 0300. | 2012-02-01 | Market Manager
19033 | MMSUI notice tab display doesn't work if priority field is not entered through notice builder application. | The Notice tab will not require priority to display a Notice in the MMS MM UI | 2011-06-22 | Market Manager
14377 | NP4-731: Wind Generation Resource Power Potential Forecast: Report must be in .csv as well as .xml | Report is market facing for MT3. | 2011-10-21 | Network Model Management System
18216 | PTC: Name Service filter apparently not working correctly | The user can filter an alternative way | 2011-07-25 | Network Model Management System
18218 | PTC: Import of NameRegistration does not import completely | The user can upload smaller files | 2011-07-25 | Network Model Management System
14377 | NP4-731: Wind Generation Resource Power Potential Forecast: Report must be in .csv as well as .xml | Report is market facing for MT3. | 2011-10-21 | Network Model Management System
18216 | PTC: Name Service filter apparently not working correctly | The user can filter an alternative way | 2011-08-24 | Network Model Management System
18218 | PTC: Import of NameRegistration does not import completely | The user can upload smaller files | 2011-08-24 | Network Model Management System
6777 | OS Core: Ungroup - RUI- Rejected and Canceled outages are allowed to be ungrouped. | When a grouped outage has been Canceled or Rejected the user is able to ungroup the equipment. |  | Outage Scheduler
8378 | OS Core TOO: Editing the dates on a resource submission to fall with in the Opportunity window of an existing TOO should get a TOO match message | When dates on a resource outage are edited to fall with in the Opportunity window of an existing TOO; TSP and Ercot should receive a TOO match message | 2011-06-22 | Outage Scheduler
9077 | OUI Warn: Group Warnings: There should only be one message per Group, instead of multiple messages for each outage in the group | When the user gets a warning message on a group outage, they get a warning for each outage in the group. | 2011-08-24 | Outage Scheduler
9500 | OS Core: Unable to enter Grouped Recurring Planned Transmission outages. | The MPs are not able to enter a recurring Planned Grouped outage. | 2011-08-24 | Outage Scheduler
10398 | OS Core Usability - All Group - Error messages don't need to be repeated at the top for the same reason | When a error message comes in on a group outage, the user gets a error for each outage in the group. | 2011-06-22 | Outage Scheduler
6777 | OS Core: Ungroup - RUI- Rejected and Canceled outages are allowed to be ungrouped. | When a grouped outage has been Canceled or Rejected the user is able to ungroup the equipment. |  | Outage Scheduler
8378 | OS Core TOO: Editing the dates on a resource submission to fall with in the Opportunity window of an existing TOO should get a TOO match message | When dates on a resource outage are edited to fall with in the Opportunity window of an existing TOO; TSP and Ercot should receive a TOO match message | 2011-06-22 | Outage Scheduler
9077 | OUI Warn: Group Warnings: There should only be one message per Group, instead of multiple messages for each outage in the group | When the user gets a warning message on a group outage, they get a warning for each outage in the group. |  | Outage Scheduler
9500 | OS Core: Unable to enter Grouped Recurring Planned Transmission outages. | The MPs are not able to enter a recurring Planned Grouped outage. | 2011-07-25 | Outage Scheduler
10398 | OS Core Usability - All Group - Error messages don't need to be repeated at the top for the same reason | When a error message comes in on a group outage, the user gets a error for each outage in the group. | 2011-06-22 | Outage Scheduler
12334 | OS Core Grouped: ENYS: Display/Paint on success does not capture all Outage ID's in the table | The outage ID are not displayed on the confirmation when two or more of the equipment have the same name. |  | Outage Scheduler
13037 | OS Core For an outage in active state, could change the actual start and planned end separately but not at same time in HGUI. | The user is unable to make a change to both the Actual Start and the Planned End in the same update. |  | Outage Scheduler
15536 | OS Core OS 2.2.0 TOO DR does not rematch when the length of the dr is shortened and then re-lengthened | Once a Transmission Opportunity Outage matches and before the resource outage starts, the QSE shortens the resource outage to less than the requested duration of the TOO, the TOO resets back to the status before the match. If the QSE updates the resource outage again extending the duration long enough for the TOO to take place, the TOO isn't re-matching with the resource outage. | 2011-06-22 | Outage Scheduler
16735 | Config Issue: OS 2.2.3 - Warnings that do not require an action are not being removed from the warnings table | Some warnings do not have an action, such as add a supporting note, to clear a warning. These warnings are removed by a batch program that runs every 12 hours. The batch program has not yet been configured correctly at ERCOT to remove the warnings | 2011-07-25 | Outage Scheduler
12334 | OS Core Grouped: ENYS: Display/Paint on success does not capture all Outage ID's in the table | The outage ID are not displayed on the confirmation when two or more of the equipment have the same name. | 2011-08-24 | Outage Scheduler
13037 | OS Core For an outage in active state, could change the actual start and planned end separately but not at same time in HGUI. | The user is unable to make a change to both the Actual Start and the Planned End in the same update. |  | Outage Scheduler
15536 | OS Core OS 2.2.0 TOO DR does not rematch when the length of the dr is shortened and then re-lengthened | Once a Transmission Opportunity Outage matches and before the resource outage starts, the QSE shortens the resource outage to less than the requested duration of the TOO, the TOO resets back to the status before the match. If the QSE updates the resource outage again extending the duration long enough for the TOO to take place, the TOO isn't re-matching with the resource outage. | 2011-06-22 | Outage Scheduler
16735 | Config Issue: OS 2.2.3 - Warnings that do not require an action are not being removed from the warnings table | Some warnings do not have an action, such as add a supporting note, to clear a warning. These warnings are removed by a batch program that runs every 12 hours. The batch program has not yet been configured correctly at ERCOT to remove the warnings | 2011-07-25 | Outage Scheduler
8872 | OS UI Fix: Custom Filter: HG UI vs ABB -- the HG UI does not allow filtering of warnings | The user can only sort their outage warnings by the column header on the warnings tab. | 2011-10-21 | Outage Scheduler UI
8914 | OS UI: Usability: 30 rows of eq user doesn't have a visual of when they have reached 30 | The grouped outages do not give the user any indication that the limit of 30 has been reached until they submit and get an error message. | 2011-08-24 | Outage Scheduler UI
8936 | OS UI : QSE: Resource does not have Equipment; column names should say Resource and Resource Type instead of Equipment Type and Equipment Name | The OS UI summary page column for the resource name is displaying "Equipment" and should display "Resource". The Type column is displaying "Equipment" and should display "Resource Type". |  | Outage Scheduler UI
8872 | OS UI Fix: Custom Filter: HG UI vs ABB -- the HG UI does not allow filtering of warnings | The user can only sort their outage warnings by the column header on the warnings tab. | 2011-10-21 | Outage Scheduler UI
8914 | OS UI: Usability: 30 rows of eel user doesn't have a visual of when they have reached 30 | The grouped outages do not give the user any indication that the limit of 30 has been reached until they submit and get an error message. | 2011-08-24 | Outage Scheduler UI
8936 | OS UI : QSE: Resource does not have Equipment; column names should say Resource and Resource Type instead of Equipment Type and Equipment Name | The OS UI summary page column for the resource name is displaying "Equipment" and should display "Resource". The Type column is displaying "Equipment" and should display "Resource Type". |  | Outage Scheduler UI
11212 | OS UI : TSP - M1 - Version ID is missing on the error screen | The version of the outage does not display on the screen after an error. The MP can refresh and see the version number of the outage. |  | Outage Scheduler UI
12337 | OS Core:: TSP: Forced Submit -missing fields from screen | The forced outage submit does not display the primary and secondary phone numbers |  | Outage Scheduler UI
14631 | OS UI Usability: Requesting Company & Operating Company - the user can see their selected choices causing them to query on un wanted parameters. | When using the OS UI Custom Filter, the user may not be able to see the selected Operating Company and Requesting Company choice. This could cause the user to filter for more data than is wanted. |  | Outage Scheduler UI
17778 | The OS UI needs to be able to filter on the "Nature of Work" | The OS UI needs the ability to filter on the "Nature of Work" field. | 2011-09-21 | Outage Scheduler UI
17780 | The OS UI needs to display the "Nature of Work" on the Summary Screen and the Warnings Tab | The OS UI Summary page and the Warnings Tab need to display the "Nature of Work". | 2011-09-21 | Outage Scheduler UI
18204 | OS UI - API submission: Notes field when larger than 1000, the eip layer throws a saxon error | The submission of the notes tag in the OS outage submission should not be longer than 1000 characters. The MP can reduce the number of characters in the notes section to less than 1000. |  | Outage Scheduler UI
11212 | OS UI : TSP - M1 - Version ID is missing on the error screen | The version of the outage does not display on the screen after an error. The MP can refresh and see the version number of the outage. |  | Outage Scheduler UI
12337 | OS Core:: TSP: Forced Submit -missing fields from screen | The forced outage submit does not display the primary and secondary phone numbers | 2011-10-21 | Outage Scheduler UI
14631 | OS UI Usability: Requesting Company & Operating Company - the user can see their selected choices causing them to query on un wanted parameters. | When using the OS UI Custom Filter, the user may not be able to see the selected Operating Company and Requesting Company choice. This could cause the user to filter for more data than is wanted. | Deferred until 2012 | Outage Scheduler UI
17778 | The OS UI needs to be able to filter on the "Nature of Work" | The OS UI needs the ability to filter on the "Nature of Work" field. | Deferred until 2012 | Outage Scheduler UI
17780 | The OS UI needs to display the "Nature of Work" on the Summary Screen and the Warnings Tab | The OS UI Summary page and the Warnings Tab need to display the "Nature of Work". | Deferred until 2012 | Outage Scheduler UI
18204 | OS UI - API submission: Notes field when larger than 1000, the eip layer throws a saxon error | The submission of the notes tag in the OS outage submission should not be longer than 1000 characters. The MP can reduce the number of characters in the notes section to less than 1000. | 2011-10-21 | Outage Scheduler UI

## Lookup Tables
Delivery Groups | Target Delivery Timeframe | Focus Area | Comments | Sort Char | Release Year | IA Phase | Project Category |  | Pending Action Types | Strategic Objective Groups |  | Objective Group | Detail Objectives
Deferred Defects - G1 - Jan 11 | January 2011 | DST, Planning Go-Live | Targeted for January 2011 | 1 | 2011 | 1 | Regulatory | 1 | 1 - ER Action | 1 - Grid Reliability | 1 | 1 - Grid Reliability | 1.1 Integrate emerging technologies
Deferred Defects - G2 - Mar 11 | March 2011 | Various | Targeted for March 2011 | 2 | 2012 | 2 | Business Strategy | 2 | 2 - BI Action | 2 - Manage Markets | 2 | 1 - Grid Reliability | 1.2 Transmission strategy
Deferred Defects - G3 - May 11 | May 2011 | Various | Targeted for May 2011 | 3 | 2013+ | 3 | Efficiencies / Enhancements | 3 | 3 - Watch | 3 - Compliance | 3 | 1 - Grid Reliability | 1.3 Operational readiness
Deferred Defects - G4 - Jun 11 | June 2011 | Various | Targeted for June 2011 | 4 | TBD | 4 | Technical Foundation | 4 | 4 - Future Action | 4 - External Relations | 4 | 1 - Grid Reliability | 1.4 Generation resource interconnection
Deferred Defects - G5 - Jul 11 | July 2011 | Various | Targeted for July 2011 | 5 | Future Year TBD | TBD |  |  | 5 - PPL Design | 5 - People | 5 | 1 - Grid Reliability | 1.5 Operator visualization tools
Deferred Defects - G6 - Aug 11 | August 2011 | EMS | Targeted for August 2011 | 6 | [7 empty] | 2 - Manage Markets | 2.1 Resource adequacy
Deferred Defects - G7 - Sept 11 | Sept 2011 | EMS | Targeted for September 2011 | 7 | [7 empty] | 2 - Manage Markets | 2.2 Market Design
Release 2.0 | March 2012 | TBD | First major enhancement release | 9 | [7 empty] | 2 - Manage Markets | 2.3 Load participation
Maintenance Release | July 2012 | TBD |  | 10 | [7 empty] | 2 - Manage Markets | 2.4 CFTC Requirements
Maintenance Release | Oct 2012 | TBD |  | 11 | [7 empty] | 2 - Manage Markets | 2.5 Credit Requirements
Future Release | TBD | TBD | Deferred to future release | 12 | [7 empty] | 2 - Manage Markets | 2.6 Retail market design
Standalone Project | Various | N/A | Projects not subject to the release schedule | 8 | [7 empty] | 2 - Manage Markets | 2.7 Retail data provision
N/A | N/A | N/A | Prioritization not required | 13 | [7 empty] | 2 - Manage Markets | 2.8 Smart Meter Texas
TBD |  |  | Yet to be defined | 99 | [7 empty] | 3 - Compliance | 3.1 Culture of compliance
[12 empty] | 3 - Compliance | 3.2 Protocol ownership
[12 empty] | 3 - Compliance | 3.3 Industry participation
[12 empty] | 3 - Compliance | 3.4 Stakeholder collaboration
[12 empty] | 3 - Compliance | 3.5 Security initiatives
[12 empty] | 4 - External Relations | 4.1 Stakeholder communication
[12 empty] | 4 - External Relations | 4.2 Expand ERCOT exposure
[12 empty] | 4 - External Relations | 4.3 Grid Alert outreach
[12 empty] | 4 - External Relations | 4.4 Legislative communication
[12 empty] | 4 - External Relations | 4.5 Risk management
[12 empty] | 5 - People | 5.1 Organization structure
[12 empty] | 5 - People | 5.2 Performance management
[12 empty] | 5 - People | 5.3 Training
[12 empty] | 5 - People | 5.4 Succession planning
[12 empty] | 5 - People | 5.5 Recruiting and retention
[12 empty] | 5 - People | 5.6 Reward and Recognition