| Proposed MarkeTrak Phase 3 Activity and Meeting Schedule Release 1 for Phase III |  |  |
| --- | --- | --- |
| ACTIVITY | ## LOCATION | ## CALENDAR DATE |
| MarkeTrak Taskforce Meeting: Define, Review and Approve 1st draft of Use Cases | #### ERCOT – Room 168 | Nov 01, 2010 |
| RMS Approval and Endorsement of Project Prioritization Schedule | #### ERCOT – Room 206 | #### Jun 22, 2011 |
| Approval and Endorsement by TAC for the Project Prioritization Schedule | #### ERCOT | #### Jul 07, 2011 |
| Project Approval by Board | #### ERCOT | #### Jul 19, 2011 |
| MarkeTrak Taskforce Meeting: ALL Use Cases FINALIZED, Respond to MT Survey concerns and Finalized RMGRevisions – sent out August 29th, 2011 to “RevisionRequest@Ercot.com”. | #### ERCOT – Room 168 | #### Aug 23, 2011 |
| ERCOT Project update for Critical issues from Troy Anderson **No official Project number** | #### ERCOT – Room 168 | #### Aug 23, 2011 |
| MT Script Team review first draft of scripts | #### ERCOT – Room 168 | #### Aug 24, 2011 |
| ERCOT BUSINESS REQUIREMENTS for RELEASE 1 | #### ERCOT due date Sep 7 | #### Mon Sep 26, 2011 |
| CONCEPTUAL DESIGN REVIEW for RELEASE 1 | #### ERCOT due date Sep 16 | #### Mon Sep 26, 2011 |
| ERCOT presents Conceptual Design to Task Force | #### ERCOT – Room 168 | #### Tue Sep 27, 2011 |
| Task Force review and Comments period | #### ERCOT – Room 168 | #### Tue Sep 27, 2011 |
| ERCOT revisions to Conceptual Design | #### ERCOT – Room 168 | #### Fri Sept 27, 2011 |
| ERCOT presents Business Requirements to Task Force | #### ERCOT – Room 168 | #### Sep 27, 2011 |
| MarkeTrak Taskforce Meeting: Review proposed activity and meeting schedule and test plan document for Release bucket 1. | #### ERCOT – Room 168 | #### Tue Sept 27, 2011 |
| DETAILED DESIGN REVIEW (95% CONFIDENCE) for RELEASE 1 | #### ERCOT due date Sep 30 | #### Mon Oct 17, 2011 |
| ERCOT presents Detail Design (100% CONFIDENCE) to Task Force | #### ERCOT – Room 168 | #### Tue Oct 25, 2011 |
| TEST PLAN FOR RELEASE 1 | #### ERCOT due date Oct 12 | #### Tue Oct 25, 2011 |
| ERCOT presents Test Plan to Task Force | #### ERCOT – Room 168 | #### Tue Oct 25, 2011 |
| MarkeTrak Taskforce Meeting: Review proposed ERCOT testing execution plan, other agenda items and test plan document for Release bucket 1. | #### ERCOT – Room 168 | #### Tue Oct 25, 2011 |
| Script Sub Team review second draft of scripts | #### AEP - Austin | #### Wed Oct 26, 2011 |
| ERCOT sent V1 draft of WSDL for release 1 |  | #### Tue Nov 15, 2011 |
| MarkeTrak Taskforce Meeting: Review test scripts from sub team, other agenda items and test plan document for Release bucket 1. | #### ERCOT – Room 168 | #### Thu Nov 17, 2011 |
| MarkeTrak AdHOC meeting for market to discuss SWHold Work Around Process for June 1st, 2012 | #### WebEX | #### Wed Nov 30, 2011 |
| Deadline for feedback for MarkeTrak Release 1 test scripts |  | #### Fri Dec 2, 2011 |
| MarkeTrak Taskforce Meeting: Review test scripts from sub team, other agenda items and test plan document for Release bucket 1. Finalized Release 1 test scripts and sent to the market for review until 01.06.2012 | #### ERCOT – Room 168 | #### Tue Dec 6, 2011 |
| ERCOT Migration for release 1 |  | ## Thur Dec 8, 2011 |
| MarkeTrak Taskforce Meeting: Modify test scripts if applicable comments received, project update, other agenda items and test plan document for Release bucket 1. | #### ERCOT – Room 209 | #### Wed Jan 11, 2012 |
| MarkeTrak Task Force present Phase III Release 1 scripts to TXSET/MTC for review and approval - DEADLINE for approval for Flight 1 2012 – 01.31.2012 | ## Austin | ## Wed Jan 24, 2012 |
| ## TX SET V4.0 FLIGHT 0312 ORIENTATION (MarkeTrak SWHold WorkAround process) included in presentation | Austin | ## Wed Jan 25, 2012 |
| MarkeTrak Task Force Meeting – amendment to release 1 scripts if any recommendations from TXSET/MTC - DEADLINE for approval for Flight 1 2012 – 01.31.2012 | WebEX if needed | ## Fri Jan 27, 2012 |
| MarkeTrak Taskforce Meeting: Project update, other agenda items and test plan document for Release bucket 1. | #### ERCOT – Room 168 | #### Tue Feb 28, 2012 – Wed Feb 29, 2012 |
| ERCOT – ITEST (Internal/Functional Testing Complete) |  | #### Mon Mar 12, 2012 |
| MarkeTrak Taskforce Meeting: Project update, Test plan execution and other agenda items for Release bucket 1. | #### ERCOT – Room 168 | #### Tue Mar 27, 2012 – Wed Mar 28, 2012 |
| MarkeTrak Taskforce Meeting: Project update, Test plan execution update and other agenda items for Release bucket 1. | #### ERCOT – Room 168 | #### Apr 2012 |
| MarkeTrak Taskforce Meeting: Project update, Test plan execution update and other agenda items for Release bucket 1. | #### ERCOT – Room 168 | #### May 2012 |
| MARKETRAK SHUTDOWN FOR RELEASE 1 @NOON |  | #### Fri Jun 01, 2012 |
| MARKETRAK PR010_01 RELEASE 1 GO-LIVE |  | #### Mon Jun 04, 2012 |