## Slide 1
Project Priority List (PPL) Update
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
January 2011

## Slide 2: Project Priority List (PPL) Update – Agenda
  Multi-Year PPL Update and 2012 Release Plan
    Multi-Year PPL Highlights p. 3
    Prioritization Factors for Market Subcommittees p. 4
    Approval/Change Logging p. 5
    2012 Release Plan p. 6-7
  Appendix
    Key PPL Data Fields p. 9
    2011 Release Summary p. 10
    2011/2012 Project Spending Update p. 11
    ERCOT FTE Impact Tracking p. 12

## Slide 3: Multi-Year PPL Highlights
The new Multi-Year PPL is complete and posted to ERCOT.com
  http://www.ercot.com/services/projects/index
  The format has been changed to accommodate a multi-year view (2011-2015)
  Additional data is captured that will better inform the market on delivery plans for items approved in the stakeholder process
  Refreshed on a monthly (or more frequent) basis
No Cutline!
  ERCOT will attempt to undertake all projects in the year(s) when they are funded
  If resource constraints prevent execution in the desired timeframe, ERCOT will determine an achievable schedule and update the “Projected End Date” on the PPL
Summary Portfolio Financials
  Budget and Spending Forecasts by Project Category and Budget Year
    See rows in the header of the PPL
  Summary information is based on individual budget and spending forecasts

## Slide 4: Prioritization Factors for Market Subcommittees
Priority (new definition)
  Priority values (“Critical”, “High”, etc.) have been changed to the proposed funding year (“2012”, “2013”, etc.)
Rank (revised usage approach)
  Rank values are now assigned in increments of 10 to allow for placement of subsequent items without using decimal value Ranks
  New additions to the PPL will be placed at the end of the appropriate Project Category and given the next available Rank value
  If stakeholders want to indicate that a new NPRR should be given priority over previously ranked items, the new item can be assigned a Rank in the desired area of the Project Category
    This implies that items below the assigned Rank may have their release plan reconsidered if resource contention is expected
    ERCOT assists in the ranking process by providing input into potential resource conflicts
Release Planning (enhanced process)
  ERCOT staff will regularly evaluate new NPRRs, SCRs, and projects for inclusion in the release plan
  Results of this analysis (Projected Start and End Dates) will be reflected on the PPL

## Slide 5: PPL Approval/Change Logging
Approval/Change Logging
  “PPL Update Log” tab
  Captures changes to key fields
  Fields that are “logged”
    Priority
    Rank
    Approval Status
  Comment column notes the source of the change
    Stakeholder committees – Board, TAC, PRS
    Executive Review (ER) – internal ERCOT approving authority
    Other – Project Reforecast, Information Only, etc.
  Previous approvals from late August 2011 through current have been captured
    Project Name
    Project Status
    Budget Range (all years)
    Projected Start Date
    Projected End Date

## Slide 6: 2012 Release Plan
An initial forecast of 2012 project implementations is complete
  6 releases planned
    1 every other month, starting in February 2012
    Occasional off-cycle releases when necessary
      Example: TX SET 4.0 in early June
  Includes projects forecasted on the Board-approved PPL… plus…
  Revision Requests approved by the Board since August
  Projects in the 1st 2012 release began initiating in November 2011

## Slide 7: 2012 Release Targets – Board-Approved NPRRs/SCRs
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | NPRR321(b) SCR761 SCR764(e) | NPRR313 NPRR314 NPRR361 NPRR395 | NPRR294 NPRR351 NPRR357 NPRR359 NPRR382 NPRR383 NPRR403 SCR756(a) SCR760(b) |  | NPRR207 NPRR222 NPRR260 NPRR272 NPRR360 | NPRR354 | NPRR322 SCR756(b)
ERCOT | NPRR326 NPRR355 |  |  | NPRR365 | NPRR379 | NPRR348 | NPRR347 NPRR377 NPRR400
Counts | 5 | 4 | 9 | 1 | 6 | 2 | 5
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Italic/underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change

## Slide 8: Business Integration Update
  Appendix
  Additional Information

## Slide 9: Multi-Year PPL
Key Data Fields
  Project Category
    Business Strategy (NPRRs, SCRs, other strategic efforts)
    Efficiencies / Enhancements (Internal ERCOT operational improvements)
    Regulatory (Required by regulatory entity)
    Technical Foundation (Infrastructure maintenance and growth)
  Approval Status
    Stakeholder approval status
    “PPL” means approved and able to initiate when the timing is right
  2012 Release
    Target 2012 release (R1, R2, R3, R4, R5, R6 or off-cycle)
    “n/a” denotes future or previous year projects
  Budget Forecasts – 2011-2015
  Project Status
    Not Started
    Initiation
  Projected Start and End Dates
    Initial project timeframe projections based on Rank and resource availability
    Revised as necessary as the project proceeds through the project lifecycle
    Planning
    Execution
    Closing
    Complete

## Slide 10: 2011 Release Summary – Projects/NPRRs/SCRs
Source | Release 1 1/2011 | Release 2 2/2011 | Release 3 3/2011 | Release 4 4/2011 | Release 5 5/2011 | Release 6 6/2011
Market / PUCT |  |  | NPRR302 |  | NPRR285(a) NPRR293 NPRR303 NPRR307 NPRR329 | NPRR285(b)
ERCOT |  |  | Met Center Disposition | Planning Model |  | NPRR339(a) NPRR341 Enterprise Records Mgmt Fire Alarm Upgrade
Source | Release 7 7/2011 | Release 8 8/2011 | Release 9 9/2011 | Release 10 10/2011 | Off-Cycle 11/2011 | Release 12 12/2011
Market / PUCT | NPRR146 NPRR282 NPRR323(a) | NPRR208 NPRR323(b) NPRR350 SCR764(a) | NPRR376 SCR764(b) | NPRR258 SCR760(a) SCR764(c) SCR766 | NPRR320 | NPRR251 NPRR290 NPRR310 NPRR316 NPRR321(a) SCR764(d) SCR765
ERCOT | NPRR339(b) | NPRR221 IT Security Infrastructure Upgrade | NPRR346 Data Research & Rptng | SCR762 Data Agg Performance Improvements |  | NPRR338 NPRR343 SCR763 TML Transition to MIS

## Slide 11: Project Spending Update – 12/29/2011
PPL – 2011 | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 28,179,000 | $ 24,235,202 | $ 23,625,284
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 7,971,812 | $ 5,169,872
Totals | $ 41,900,000 | $ 36,364,000 | $ 32,207,014 | $ 28,795,156
* Data Center Hardware Budget reduced by the amount of purchasing accelerated from 2011 to 2010 (~$5.5M)
*
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,750,144 | $ 0
Regulatory |  | $ 1,600,000 | $ 1,012,418 | $ 0
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,312,813 | $ 0
Technical Foundation |  | $ 6,500,000 | $ 6,460,174 | $ 0
Totals | $ 15,000,000 | $ 16,100,000 | $ 17,535,549 | $ 0
**
** Through 11/30/2011

## Slide 12: ERCOT FTE (Full Time Equivalent) Tracking
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 5.70 | 2 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
NPRR327 | Operations | Operations Support | 1.00 | 1 | $125k-$135k | Up for consideration at 1/5/2012 TAC meeting
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Tabled for 1 month at 12/1/2011 TAC meeting
 | In-Flight at TAC |  | 1.10 | 1 |  | 
 | Total of All Items |  | 6.80 | 3 |  | 
This slide documents additional staff required to support ongoing ERCOT operations activities