## Slide 1
Business Integration Update to PRS
January 19, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-10
    Upcoming Project Implementations
    Project Portfolio Status (Gantt Chart)
    2012 Release Targets
    Project Spending Update
  ERCOT FTE Tracking p. 11
  Market Rules Update p. 12-15

## Slide 3: Recent Project Implementations
Go-Lives in December
  NPRR251 – Sync w/PRR845 – Def. of IDR Meters and Optional Removal of IDRs at a Premise…
  NPRR290 – ERCOT Publication of DAM PSS/E Files
  NPRR310 – Expand Output Schedule Acceptable Range to Include HSL and LSL
  NPRR316 – Negative Self-Arranged Ancillary Services Quantity
  NPRR321 – Real-Time PTP Option Modeling
    MMS portion
  NPRR343 – CRR Bid and PTP Obligation Bid Criteria Change
  SCR763 – Modify COP Validation Rule for RRS
  SCR764 – Public Access to Select MIS Dashboards
    Dec. – 4th phase – LMP Contour Map
  SCR765 – Public Aggregated Wind Dashboard
  Stabilization/Deferred Defects
    Deferred Defects – Release 10
    TML Transition to MIS
    Stabilization and its sub-projects are scheduled to end on 12/31/2011
Go-Lives in January (no integrated software release)
  Data Center Migration
  Taylor Facilities Remodel
    Build-out of shipping/receiving area and conversion of 2 team rooms into office space for Security and HR
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4
Project Portfolio Status – as of 1/6/2012

## Slide 5
Project Portfolio Status – as of 1/6/2012

## Slide 6
Project Portfolio Status – as of 1/6/2012

## Slide 7
Project Portfolio Status – as of 1/6/2012

## Slide 8
Project Portfolio Status – as of 1/6/2012

## Slide 9: 2012 Release Targets – Board-Approved NPRRs/SCRs
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | NPRR321(b) SCR760(b) SCR761 SCR764(e) | NPRR313 NPRR314 NPRR359 NPRR361 NPRR395 | NPRR294 NPRR351 NPRR382 NPRR383 NPRR403 SCR756(a) SCR760(c) | NPRR322 NPRR354 NPRR357 | NPRR207 NPRR222 NPRR260 NPRR272 NPRR360 |  | SCR756(b)
ERCOT | NPRR326 NPRR355 |  |  | NPRR348 NPRR365 | NPRR379 |  | NPRR347 NPRR377 NPRR400
Counts | 6 | 5 | 7 | 5 | 6 | 0 | 4
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change

## Slide 10: Project Spending Update – 12/31/2011
PPL – 2011 | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 28,179,000 | $ 25,651,833 | $ 25,651,833
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 6,141,842 | $ 6,141,842
Totals | $ 41,900,000 | $ 36,364,000 | $ 31,793,675 | $ 31,793,675
* Data Center Hardware Budget reduced by the amount of purchasing accelerated from 2011 to 2010 (~$5.5M)
*
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,750,144 | $ 0
Regulatory |  | $ 1,600,000 | $ 1,012,418 | $ 0
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,325,813 | $ 0
Technical Foundation |  | $ 6,500,000 | $ 6,460,174 | $ 0
Totals | $ 15,000,000 | $ 16,100,000 | $ 17,548,549 | $ 0
**
** Preliminary 2011 Results
ERCOT Public

## Slide 11: ERCOT FTE (Full Time Equivalent) Tracking
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 5.70 | 2 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
NPRR327 | Operations | Operations Support | 1.00 | 1 | $125k-$135k | Up for consideration at 1/5/2012 TAC meeting
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Tabled for 1 month at 12/1/2011 TAC meeting
 | In-Flight at TAC |  | 1.10 | 1 |  | 
 | Total of All Items |  | 6.80 | 3 |  | 
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public

## Slide 12: Market Rules Update
The number of new guide revision requests filed in 2011 was comparable to 2010; however, 30 more NPRRs were filed in 2011 than 2010.
Market Rules staff managed an average of 78 revisions each month during 2011.
ERCOT Public

## Slide 13: Market Rules Update
* The 2006-2007 stats are deceiving as ERCOT staff was often taking NPRRs to the Transition Plan Task Force to get their endorsement and then TPTF would submit the NPRR.
This helped to speed the process as PRS was sending all NPRRs through TPTF prior to considering the language.
ERCOT Public

## Slide 14: Market Rules Update
Information based on NPRR Impact Analyses presented to the Board.
Per Protocol, the Impact Analysis captures the impact to ERCOT, Inc.
ERCOT Public

## Slide 15: Market Rules Update
ERCOT submitted 71 NPRRs (or 55% of total) in 2011 .
Over half of the NPRRs submitted by ERCOT resulted in no impact to ERCOT, Inc.
Stakeholders submitted 59 NPRRs (or 45%) in 2011.
Three percent of the Market submitted NPRRs resulted in an impact of greater than $125,000 to ERCOT, Inc.
ERCOT Public