## 2012 DSWG Goals Ranking
Goal Description | Deliverable | Scheduled Completion | Market Champion | Contributors | Average Rank
Modify EILS Rules to Increase Available Capacity | PUCT Rule Change and corresponding NPRR |  | Ed Echols | Tim C, Mark S, Betty M, Joel O | 3.0667
Load Participation in SCED | Requirements Defined for SCED 2.0 Effort |  |  | Tim C, Jay Z, Mark S, Floyd T, Eric R, Parviz A, Joel O, Ed E | 3.7333
Integrate DR and emerging demand side technologies into the Transmission Planning Process | LTST Update |  |  | Tim C, Jay Z, Ed E | 10.4667
Develop proposals for DR Products with different ramp periods | Functional requirements develop and pilot projects proposed | 2012-05-01 |  | Tim C, Mark S, Eric R, Joel O, John T, Ed E | 5
Increase DR being provided by temperature sensitive loads | Proposals for market changes (may lead to NPRR) |  |  | Ed E | 8.2
Energy Payments for DR Deployments | Potential NPRR |  |  | Tim C, Betty M, Joel O | 8.8
Adjust DR Capacity for T&D Losses | Potential NPRR to bring DR impacts up to a wholesale level | 3rd Quarter | Tim Carter | Ed E | 9.8667
Explore Settlement Improvements for Price Sensitive Loads | Five minute settlement option |  | Mark Smith Floyd Trefny | Eric R, Parviz A, Ed E | 10.3333
Proof of Concept Test for Aggregated Small Load Resources | Report w/ Rule Changes Identified | 2012-05-01 | Ed Echols | Jay Z, Eric R, Parviz A, John T | 9.1333
Improve access to ERCOT market data to assist in DR business decisions | Proposed changes to MIS Reports | 2012-05-01 | Eric Rothschild | Mark S, Floyd T, Parviz A | 7.8
Update Load Participation in ERCOT Markets document | Revised and Updated Document |  |  | Eric R, Joel O | 9.8667
Increase Percentage of RRS provided by Load Resources | Update DWG Study |  |  | Jay Z, Ed E | 9.4667
Increase AS Participation by CLRs | Add Case Studies to Load for Dummies (above) |  |  | Parviz A, Ed E | 10.6667
ERS Trades | Proposed changes to ERS Rules |  |  |  | 10.3333
Expand Sources of Frequency Data for UFR Events | Additional Data for UFR Deployment Analysis |  |  | Eric R, Ed E | 12.9333
4CP / Price Response Study | Report |  |  | Jay Z, Eric R, Ed E | 11.8
Explore complementarities between ERCOT DR and TDSP LM SOPs | Report |  |  | Jay Z, Betty M, Joel O, Ed E | 10.2667
Establish a DR program for small customer loads (load resources less than 100 kW). Pay as a fixed price contract based on the avoided cost of capacity. | Functional requirements develop and pilot projects proposed | Preferably by June 2012, but not later than May 2013 | Need to Identify a REP that would lead this effort | Parviz A | New Proposed Goal