|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report January 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 124 active generation interconnection requests totaling over 33,000 MW. This includes almost 18,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $33.1 Million - Transmission Projects endorsed in 2012 total $319.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $10.0 Billion - Transmission Projects energized in 2011 total about 817.8 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies	4

1.6	Wind Generation	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	12

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

New – 10INR0023 Baker Ranch Wind – 400 MW in Haskell County

## New Generation Registering for Commercial Operations

08INR0062 Trinity Hills Wind – 225 MW in Young County

10INR0082 FRV AE Solar – 30 MW in Travis County

The total installed wind capacity is now reported as 9,829 MW by the resource owners through the registration process. Capacity by North, South and West is 232 MW,  2066 MW, and 7531 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 164 generation interconnection or change requests |  |  |  |  |
| As of January 31, 2012 | North | South | West | Total |
| Security Screening Study | 1 | 1 | 3 | 5 |
| SSS Completed | 3 | 4 | 8 | 15 |
| Full Interconnect Study | 8 | 19 | 49 | 76 |
| FIS Completed | 1 | 2 | 5 | 8 |
| Suspended Studies | 8 | 4 | 28 | 40 |
| Capacity of Suspended Study Projects | 6,486 | 3,338 | 11,273 | 21,097 |
| Interconnect Agreement Completed | 7 | 10 | 3 | 20 |
| Capacity under Interconnection Agreements | 4,577 | 4,336 | 550 | 9,463 |
| Capacity for Grid, MW | 8,587 | 10,164 | 14,476 | 33,227 |
| Wind Capacity, MW | 2,634 | 3,326 | 11,973 | 17,933 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 547 |
| Gas-CombinedCycle |  |  | 4,732 | 2,890 | 10,660 |
| Total Gas | 1,465 | 2,120 | 4,732 | 2,890 | 11,207 |
| Nuclear |  |  |  | 5,900 | 5,900 |
| Coal |  | 850 | 2,785 |  | 3,635 |
| Wind | 1,529 | 14,358 | 2,046 | 11,904 | 29,837 |
| Solar | 285 | 511 | 60 | 353 | 1,209 |
| Biomass |  |  | 100 | 50 | 150 |
| Storage | 560 | 346 |  |  | 906 |
| Other |  | 240 | 1,240 |  | 1,480 |
| Grand Total | 3,839 | 18,425 | 10,963 | 21,097 | 54,324 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

## (Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of January 31, 2012 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 |  | Biomass |  | 100 |  |
| 10INR0060 | Magic Valley Wind Project | IA | Willacy | South | Jun-12 |  | Wind |  | 202 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 |  | Solar |  | 60 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-12 |  | Wind |  | 150 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 |  | Wind |  | 100 |  |
| 10INR0023 | Baker Ranch Windfarm | IA | Haskell | West | Dec-12 |  | Wind |  | 400 | New |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 |  | Wind |  | 92 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 |  | Wind |  | 50 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 |  | Coal |  | 925 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC |  | 1,792 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 |  | Wind |  | 120 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Jan-15 |  | Gas-CC |  | 780 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other |  | 620 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jan-16 |  | Gas-CC |  | 1,380 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Jan-16 |  | Gas-CC |  | 780 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other |  | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
|  |  |  |  |  |  |  | Total |  | 9,463 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1,200 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 11INR0054 | San Patricio | 161 | TBD | Wind |
| 10INR0062a | Pecos | 80 | TBD | Wind |  | 11INR0094 | Kent | 100 | TBD | Solar |
| 12INR0075 | Wilbarger | 499 | Apr-12 | Wind |  | 12INR0086 | Harris | 89 | Jun-12 | Gas |
| 12INR0053 | Crockett | 615 | Jun-12 | Wind |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0050 | King | 332 | Jun-12 | Wind |  | 11INR0085 | Nolan | 106 | Jul-12 | Wind |
| 12INR0079 | Kenedy | 200 | Aug-12 | Wind |  | 12INR0082 | Pecos | 30 | Aug-12 | Solar |
| 12INR0076 | Winkler | 36 | Sep-12 | Other |  | 13INR0036 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0071 | Caldwell | 30 | Dec-12 | Wind |  | 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |
| 12INR0067 | Webb | 94 | Dec-12 | Wind |  | 11INR0093 | San Patricio | 41 | Dec-12 | Wind |
| 11INR0079a | Clay | 200 | Dec-12 | Wind |  | 12INR0059 | Pecos | 50 | Dec-12 | Solar |
| 12INR0057 | Ector | 50 | Dec-12 | Solar |  | 12INR0060 | Schleicher | 58 | Dec-12 | Wind |
| 12INR0055 | Baylor | 80 | Dec-12 | Wind |  | 09INR0048 | Jack | 113 | Dec-12 | Wind |
| 11INR0081 | Live Oak | 72 | Dec-12 | Wind |  | 12INR0085 | Stonewall | 25 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 12INR0081 | Upton | 113 | Dec-12 | Wind |
| 13INR0040 | Harris | 0 | Jan-13 | Gas |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0050 | Crosby | 149 | Mar-13 | Wind |  | 09INR0051 | Borden | 249 | Mar-13 | Wind |
| 12INR0018 | Gray | 500 | Apr-13 | Wind |  | 12INR0070 | Knox | 300 | Apr-13 | Wind |
| 10INR0089 | Harris | 40 | May-13 | Other |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 10INR0085 | Ector | 40 | May-13 | Solar |
| 13INR0031 | Austin | 30 | Jun-13 | Solar |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 13INR0032 | Andrews | 30 | Jun-13 | Solar |  | 13INR0023 | Ector | 240 | Jul-13 | Other |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 11INR0083A | Crockett | 50 | Sep-13 | Wind |
| 11INR0082A | Val Verde | 50 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 13INR0038 | Swisher | 300 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 13INR0044 | Wilacy | 400 | Dec-13 | Wind |
| 13INR0039 | Castro | 500 | Dec-13 | Wind |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 12INR0058 | San Patricio | 50 | Dec-13 | Wind |  | 11INR0057 | Cameron | 165 | Dec-13 | Wind |
| 12INR0034 | Borden | 342 | Dec-13 | Wind |  | 14INR0014 | Val Verde | 100 | Jan-14 | Solar |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 10INR0080 | Presidio | 81 | Jan-14 | Solar |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0016 | Harris | 190 | Jun-14 | Gas |
| 14INR0015 | Harris | 192 | Jun-14 | Gas |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0012 | Gray | 401 | Jun-14 | Wind |  | 10INR0021 | Grayson | 646 | Jul-14 | Gas |
| 14INR0010 | Roberts | 300 | Jul-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 13INR0021 | Llano | 600 | Dec-14 | Gas |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 14INR0009 | Kent | 248 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 14INR0003 | Nolan | 850 | Jun-18 | Coal |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

## Wind Generation    Wind Capacity Installed by Year

# Regional Planning Group Project Reviews

- Sharyland Utilities (Sharyland) and Brownsville Public Utilities Board (BPUB) has submitted the Cross Valley Brownsville Loop project. The estimated cost for this project is $275 Million.  ERCOT  has completed the Independent Review for this Tier 1 project. The project was endorsed by the ERCOT BOD in January 2012. ERCOT has sent an endorsement letter.

- Brazos Electric Cooperative has submitted the Olney to Lake Kemp Switch 69kV Rebuild project. This is a Tier 3 project that is estimated to cost approximately $17.8 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- South Texas Electric Cooperative (STEC) has submitted the El Campo to Vanderbilt rebuild project to rebuild the existing 69 kV transmission line between El Campo and Vanderbilt with a double circuit 138/69 kV line. The proposed project is to accommodate 118 MW of new load in Jackson County. This is a Tier 2 project that is estimated to cost $26.8 million. ERCOT has completed the Independent Review and has sent the RPG acceptance letter.

- South Texas Electric Cooperative (STEC) has submitted the Karnes Electric Cooperative (KEC) load addition project to accommodate 167 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $33.1 million. This Tier 2 project is undergoing ERCOT Independent Review.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - January 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 2502 | 0-436 | 8,364,352 | CREZ |  |
| Aspermont - Paint Creek 138 kV, Sacroc - Sun Switch 138 kV, Scurry Switch - Sun Switch, Salt Creek - Spur 138 kV | Aspermont 138/69 kV autotransformer T1 | 3388 | 0-332 | 1,582,952 | CREZ | High wind generation in the West |
| Nelson Sharpe - Lon_Hill 345 kV | Kingsville - Lon_Hill 138 kV | 41 | 0-3500 | 1,153,541 |  |  |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69 kV Autotransformer | 236 | 0-1092 | 992,846 | 5YTP [2010-R7, R8] |  |
| Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 665 | 4-132 | 832,040 | CREZ | High wind generation in the West |
| Orange Grove Switching Station - Lon_Hill 138 kV, Pawnee - Lon_Hill 345 kV, Whitepoint 345/138 kV autotransformer | Sinton - Skidmore 69 kV | 926 | 0-2800 | 717,348 |  |  |
| Wharton - Dyann 138 kV | Blessing - Lane City 138 kV | 317 | 0-3500 | 611,039 |  | Outage on South Lane City - New Gulf 138 kV , Pledger - West Columbia 138 kV |
| Fort Stockton Plant - Barrilla 138 kV | Barrilla - Fort Stockton Switch 69 kV | 802 | 0-1077 | 541,229 | CREZ | High wind generation in the West |
| Gaf Tnp - PH Robinson 138 kV | Heights Tnp - PH Robinson 138 kV | 8 | 0-3500 | 491,271 |  | Outage on Center - PH Robinson 345 kV |
| Singleton - Zenith 345 kV | Betka - Hockley 138 kV | 371 | 0-436 | 429,631 |  | Outage on King - Rothwood 345 kV |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The Contingency List update was completed and posted on ERCOT POI.  The Data Dictionary update is underway.  The TPIT update to begin the week of January 9th:

  - Dec 14, 2011	ERCOT Finalized and Posted Contingency database

  - Jan 16, 2012	Data Dictionary Posted

  - Jan 9, 2012	TPIT No Cost Report posted on ERCOT POI

  - Jan 13, 2012	12DSA and 12DSB Pass0 TPIT updates begin

  - Feb 27, 2012	12DSA and 12DSB TPIT updates posted to ERCOT POI

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2, 4, 9):  Scheduled for Production on February 2012 (approx 23rd) on-cycle release.

  - Item 5:  Requirements completed by ERCOT and TSPs and agreed upon with vendor.  Awaiting vendor estimate on cost for implementation so that SOW can be prepared.

  - Bundle 4 (Items 1 and 6):  ERCOT and TSPs have identified new fields or records added between version 33 and version 30 of the PSS/E RAWD format and are decided which new fields need to be implemented.  The evaluation process for Item 1 has been added to the SSWG Procedure Manual currently being updated.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Planning |
| SCR760-2 | Distribution Capacitor banks | Release |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Release |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Release |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

The 2011 Five-Year Transmission Plan reliability analysis has been completed for 2012, 2014 and 2016 and all the reliability projects are posted on the ERCOT Planning and Operations Information. Work on the 2011 Five-Year Transmission Plan economic analysis is ongoing. ERCOT is also working on the 2011 Five-Year Transmission Plan draft report that is expected to be completed in March 2012.