## ERCOT SCRIPT SUGGESTIONS
Script Name | ERCOT/MP | MP Only | Registration Set-Up | Notes
MTIGRV1_Redirect Fees (IG) | X |  | Y
MTIGRV2_Redirect Fees (IG) | X |  | Y
MTIGRV3_Redirect Fees (IG) | X |  | Y | Short script involving only unexecutable transition. Unexecutable is not new functionality such as the Agree transition.
MTIGRV1_Redirect Fees (IG) | X |  | Y
MTRES18_Customer Rescission | X |  | Y
MTRES18-2_Customer Rescission | X |  | Y | This script tests Unexecutable transition which is also covered in MTRES18-3. Also unexecutable is not new functionality.
MTRES18-3_Customer Rescission | X |  | Y
MTRES18-4_Customer Rescission | X |  | Y | Similar to MTRES18-6
MTRES18-5_Customer Rescission | X |  | Y
MTRES18-6_Customer Rescission | X |  | Y
MTRES18-7_Customer Rescission |  | X | N | ESIID validations covered in other flight scripts as well as UAT scripts
MTRES18-8_Customer Rescission | X |  | Y | Timing adjustment auto transition/auto close and escalation emails not fully functional in CERT environment
MTRES18-9_Customer Rescission | X |  | Y | Timing adjustment auto transition/auto close and escalation emails not fully functional in CERT environment
MTRES18-10_Customer Rescission | X |  | Y | Timing adjustment auto transition/auto close and escalation emails not fully functional in CERT environment
MTUSG13D-1_Usage/ Billing AMS LSE Interval Dispute |  | X | N
MTUSG13D-2_Usage/ Billing AMS LSE Interval Dispute |  | X | N
MTUSG13D-3_Usage/ Billing AMS LSE Interval Dispute |  | X | N
MTUSG13D-4_Usage/ Billing AMS LSE Interval Dispute |  | X | N
MTUSG13M-1_Usage/ Billing AMS LSE Interval Missing |  | X | N
MTUSG13M-2_Usage/ Billing AMS LSE Interval Missing |  | X | N
MTUSG13M-3_Usage/ Billing AMS LSE Interval Missing |  | X | N
MTUSG13M-4_Usage/ Billing AMS LSE Interval Missing |  | X | N
MTSWH19-1_Switch Hold Removal |  | X | N
MTSWH19-2_Switch Hold Removal |  | X | N
MTSWH19-3_Switch Hold Removal |  | X | N
MTSWH19-4_Switch Hold Removal |  | X | N
MTSWH19-5_Switch Hold Removal |  | X | N
MTSWH19-6_Switch Hold Removal |  | X | N
MTSWH19-7_Switch Hold Removal |  | X | N
MTSWH19-8_Switch Hold Removal |  | X | N
MTSWH19-9_Switch Hold Removal |  | X | N
MTSWH19-10_Switch Hold Removal |  | X | N
MTMR29-1_Market Rule Subtype |  | X | N
MTMR29-2_Market Rule Subtype | X |  | N
MTMR29-3_Market Rule Subtype |  | X | N
MTMR29-4_Market Rule Subtype | X |  | N
MTMR29-5_Market Rule Subtype | X |  | N
MTMR29-6_Market Rule Subtype | X |  | N
MTMR29-7_Market Rule Subtype | X |  | N | Proprietary Information testing also included in MTMR29-5
MTMR29-8_Market Rule Subtype |  | X | N

## ERCOT V2 SCRIPT SUGGESTIONS
Script Name | Siebel Set-Up | ERCOT | TDSP 1 | TDSP 2 | TDSP 3 | TDSP 4 | CR 1 | CR 2 | CR 3 | CR 4 | CR 5 | CR 6 | No. Iterations
MTIGRV1_Redirect Fees (IG) | Y | xx | [10 empty] | 2 | bar: TDSP 1 to TDSP 2; CR 1 to CR 2; CR 5 to CR 6
MTIGRV2_Redirect Fees (IG) | Y | xx | [10 empty] | 2 | bar: TDSP 2 to TDSP 3; CR 1; CR 3 to CR 4; CR 6
MTIGRV1_Redirect Fees (IG) | Y | xx | [10 empty] | 2 | bar: TDSP 3 to CR 2; CR 4 to CR 5
MTRES18_Customer Rescission | Y | xx | [10 empty] | 2 | bar: TDSP 1; TDSP 4; CR 2 to CR 3; CR 5 to CR 6
MTRES18-3_Customer Rescission | Y | xx | [10 empty] | 2 | bar: TDSP 1 to TDSP 2; CR 2 to CR 4; CR 6
MTRES18-5_Customer Rescission | Y | xx | [10 empty] | 2 | bar: CR 1 to CR 2
MTRES18-6_Customer Rescission | Y | xx | [10 empty] | 2 | bar: TDSP 1; TDSP 4; CR 3 to CR 6
MTUSG13D-1_Usage/ Billing AMS LSE Interval Dispute | N | [11 empty] | 1 | bar: TDSP 4; CR 4
MTUSG13D-2_Usage/ Billing AMS LSE Interval Dispute | N | [11 empty] | 1 | bar: TDSP 1; CR 3
MTUSG13D-3_Usage/ Billing AMS LSE Interval Dispute | N | [11 empty] | 1 | bar: TDSP 2; CR 2
MTUSG13D-4_Usage/ Billing AMS LSE Interval Dispute | N | [11 empty] | 1 | bar: TDSP 3; CR 1
MTUSG13M-1_Usage/ Billing AMS LSE Interval Missing | N | [11 empty] | 1 | bar: TDSP 4; CR 6
MTUSG13M-2_Usage/ Billing AMS LSE Interval Missing | N | [11 empty] | 1 | bar: TDSP 1; CR 5
MTUSG13M-3_Usage/ Billing AMS LSE Interval Missing | N | [11 empty] | 1 | bar: TDSP 2; CR 4
MTUSG13M-4_Usage/ Billing AMS LSE Interval Missing | N | [11 empty] | 1 | bar: TDSP 3; CR 3
MTSWH19-1_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 1; TDSP 4 to CR 2; CR 4; CR 6
MTSWH19-2_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 1 to TDSP 2; CR 5 to CR 6
MTSWH19-3_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 2 to TDSP 3; CR 1 to CR 4
MTSWH19-4_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 3 to CR 2; CR 5 to CR 6
MTSWH19-5_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 2; TDSP 4; CR 3; CR 6
MTSWH19-6_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 1; CR 5
MTSWH19-7_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 2 to TDSP 3; CR 1 to CR 2; CR 4 to CR 5
MTSWH19-8_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 3 to TDSP 4; CR 3 to CR 6
MTSWH19-9_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 1; TDSP 4 to CR 4
MTSWH19-10_Switch Hold Removal | N | [11 empty] | 2 | bar: TDSP 1 to TDSP 2; CR 1 to CR 2; CR 5 to CR 6
MTMR29-1_Market Rule Subtype | N | [11 empty] | 1 | bar: TDSP 2; CR 5 to CR 6
MTMR29-2_Market Rule Subtype | N | x | [10 empty] | 1 | bar: TDSP 3; CR 3 to CR 4
MTMR29-3_Market Rule Subtype | N | [11 empty] | 1 | bar: TDSP 4 to CR 2
MTMR29-4_Market Rule Subtype | N | x | [10 empty] | 1 | bar: TDSP 1; CR 3
MTMR29-5_Market Rule Subtype | N | x | [10 empty] | 1 | bar: TDSP 2; CR 5
MTMR29-6_Market Rule Subtype | N | x | [10 empty] | 1 | bar: TDSP 3; CR 4
MTMR29-8_Market Rule Subtype | N | [11 empty] | 1 | bar: TDSP 3; CR 1; CR 3
|  | 18 | 12 | 12 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 49

## ERCOT EMAIL 02142012
From: Michelsen, David [mailto:dmichelsen@ercot.com]
Sent: Tuesday, February 14, 2012 12:46 PM
To: 'Jonathan Landry' (jonathan.landry@gexaenergy.com); 'monica.jones@reliant.com' (monica.jones@reliant.com); Reed, Carolyn E.
Cc: Stewart, Tammy; Cervenka, Gene
Subject: PR010 - Flight Scripts
Afternoon All,
As requested this is a summary of topics and options for consideration for voluntary and API flight certification of MarkeTrak PR010.
My interpretation of the TX SET TF request was that we would seek to reduce the number of MarkeTrak scripts during the flight from the current number of 40;
and per our conversation ERCOT will not be able to perform set up, coordinate, track, etc all volunteer MPs at that volume with current resources and constraints.
Of course this would be dependent to some degree on the number of UI volunteers which is currently not known.
I understand and appreciate the Task Force enthusiasm for running as many scripts as possible.
However as I communicated in late November to a group asking these questions initially:
4. ‘Confirm if the market will be able to test after ITEST completion in March/2012
Yes we will be able to support a limited number of MPs executing connectivity/API scripts in the back half of the scheduled 4.0 flight.
We’ll have more information as we exit testing and approach flight.
Unfortunately we will not be able to recreate the ‘mimic user’ functionality we used in the initial app release.
MarkeTrak has become too integrated with other retail systems over the past 2 projects to allow that kind of flexibility with historical proprietary data.
Here are a few options that we can use to jump start the discussion next week:
1) If we had a relatively small group of MPs volunteer I don’t believe an All/All strategy would be a serious issue. By ‘small’ I mean no more than 4 or 5.
I don’t think anyone wants to limit participation to this degree.
2) Select a number of ERCOT scripts to be executed (say 50 total) and have the MTTF review the impact to business functionality and divide these up
as agreed upon. I would assume the primary path of new subtypes would be more heavily requested than 5 iterations of the
Market Rules for example (sample attached).
3) Execute a selected number of voluntary scripts involving ERCOT per #2 weighted towards the beginning of the MarkeTrak portion of the flight on 5/1.
MPs requesting additional script execution could request ad hoc after the scheduled execution period and before a predetermined
cutoff prior to flight contingency.
If you have any additional suggestions you would like us to review and bring to the meeting next week feel free to send them over.
Please feel free to distribute as you see fit…I don’t have a good list of those that participated on the call.
David Michelsen
Retail Customer Choice
512.248.6740