## Slide 1
Business Integration Update to PRS
February 23, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-5
    Recent and Upcoming Project Implementations
    2012 Release Targets
    Project Spending Update
  ERCOT FTE Tracking p. 6
  2013 Project Funding p. 7-10
  Appendix
    Project Portfolio Gantt Chart p. 11-16

## Slide 3: Recent and Upcoming Project Implementations
Go-Lives in January (no integrated software release)
  Data Center Migration
  Taylor Facilities Remodel
    Build-out of shipping/receiving area and conversion of 2 team rooms into office space for Security and HR
Go-Lives in February
  NPRR326 – Adjust the Calculation of the Real-Time Settlement Point Price for a Resource Node
  NPRR355 – Adjust the Calculation of the Real-Time Settlement Point Price for a Load Zone
  SCR760 – Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models
    2nd release – Items 2, 4 and 9
      #2 - Distribution Capacitor Banks
      #4 - Associate Loads and Capacitor Banks with the Correct CNG
      #9 - Multi-section Line Grouping
  SCR761 – Provide Price Republication Notifications via API and Provide Price Corrections via XML
  SCR764 – Public Access to Select MIS Dashboards
    5th phase – Deliver LMP Contour Map via Google Earth technology
Go-Lives in March (no integrated software release)
  Compliance Software Purchase and Installation
  Cyber Security Project #3
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 | NPRR294 NPRR313 NPRR351 NPRR357 NPRR382 NPRR383 NPRR403 SCR756(a) SCR760(c) | NPRR322 NPRR354 NPRR360 | NPRR207 NPRR222 NPRR272 | NPRR260 | NPRR407 NPRR422 NPRR434 SCR756(b)
ERCOT | NPRR326 NPRR355 |  | NPRR379 | NPRR348 NPRR365 |  |  | NPRR347 NPRR377 NPRR400 NPRR437
Counts | 5 | 4 | 10 | 5 | 3 | 1 | 8
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change

## Slide 5: Project Spending Update – 1/31/2012
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 6,387,511 | $ 520,568
Regulatory |  | $ 1,600,000 | $ 1,038,084 | $ 60,916
Efficiencies/Enhancements |  | $ 2,050,000 | $ 3,552,383 | $ 225,437
Technical Foundation |  | $ 6,500,000 | $ 6,711,473 | $ 758,971
Totals | $ 15,000,000 | $ 16,100,000 | $ 17,689,451 | $ 1,565,892
ERCOT Public

## Slide 6: ERCOT FTE (Full Time Equivalent) Tracking
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 5.70 | 2 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | To be considered at 3/1/2012 TAC
NPRR393 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | To be considered at 4/17/2012 Board
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | To be considered at 4/17/2012 Board
NPRR421 | Operations | Operations Analysis | 1.00 | 1 | $120k-$130k | To be considered at 4/17/2012 Board
 | Operations | Wholesale Client Svs | 0.25 | 0 | $0 | 
 | In-Flight at TAC |  | 3.35 | 3 |  | 
 | Total of All Items |  | 9.05 | 5 |  | 

## Slide 7: 2013 Project Funding – Introductory Comments
Accelerated review and approval schedule for ERCOT’s budget filing
  April Board Review
  May PUCT Review
$15M is expected to be allocated for capital projects in 2013
  No change from 2012
Multi-Year PPL will be used to forecast projects expected in 2013
  No need for extensive bottom-up PPL effort
In order to reserve funds for NPRRs and SCRs that will be filed and approved over the next 18 months, ERCOT proposes $3M in PPL funding for 2013 NPRR/SCR activity

## Slide 8: 2013 Project Funding – Schedule
February 2012
  Initial review at PRS (February 23)
March 2012
  Review at market subcommittee meetings
    WMS (March 7)
    ROS (March 8)
    RMS (March 21)
    PRS (March 22)
    COPS (April 10)
April 2012
  Review at TAC (April 5)
  Available for F&A and Board review (April 16)
May 2012
  Review at PUCT (May 1)

## Slide 9: 2013 Project Funding – Introductory Comments (cont’d)
Is $3M sufficient for 2013 NPRRs and SCRs?
  Answer: Most Likely (in ERCOT’s opinion)
  2011 activity was reviewed to assist in formulating this estimate
    In 2011, $3.4M was spent on nearly 40 NPRRs and SCRs
      Funded by both the PPL and Nodal Stabilization
      Includes $0.9M spent on the Texas SET 4.0 project
  The $3M funding would include NPRRs already on the PPL and targeted for 2013 delivery
    NPRR181, NPRR210, NPRR210, NPRR241, NPRR240, NPRR256
    Sum of the forecasts for these items is $550k
    Remaining $2.45M in funding would be held in an NPRR/SCR placeholder
Management of the NPRR/SCR placeholder
  As new NPRRs and SCRs targeted for 2013 are approved by the Board, the appropriate amount will be deducted from the placeholder

## Slide 10: 2013 Project Funding – Additional Information
The current 2013 spending forecast on the Multi-Year PPL is >$20M
  This estimate includes the proposed $3M funding for NPRR/SCR work
  ERCOT staff is working to reconsider and reprioritize internal project efforts to get the forecast closer to the $15M budget level
  Reminder: In the 2012 project budget approval process, we had a $16.1M spending forecast for a $15M budget
    We expect to take a similar approach for the 2013 project proposal
ERCOT planning to visit each market subcommittee in March to review the new approach
In March, ERCOT will ask PRS to endorse the NPRR/SCR funding concept and amount
ERCOT would like PRS to consider the priority of the Parking Deck items targeted for 2013

## Slide 11: Business Integration Update – Appendix
  Appendix
    2/20/2012 Project Gantt

## Slide 12
Project Portfolio Status – as of 2/20/2012

## Slide 13
Project Portfolio Status – as of 2/20/2012

## Slide 14
Project Portfolio Status – as of 2/20/2012

## Slide 15
Project Portfolio Status – as of 2/20/2012

## Slide 16
Project Portfolio Status – as of 2/20/2012