|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report February 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 127 active generation interconnection requests totaling almost 34,000 MW. This includes over 18,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $128.6 Million - Transmission Projects endorsed in 2012 total $319.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $10.0 Billion - Transmission Projects energized in 2011 total about $817.8 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

New – 10INR0021 Panda Sherman Power – 717 MW Combined Cycle Gas in Grayson County

New – 12INR0075 Blue Summit Wind – 170 MW in Wilbarger County

## New Generation Registering for Commercial Operations

Non-Modeled Harbor Wind – 9 MW in Nueces County

The total installed wind capacity is now reported as 9,838 MW by the resource owners through the registration process. Capacity by North, South and West is 232 MW,  2075 MW, and 7531 MW respectively.  Included in the South zone total is 850 MW which is able to switch between the West and South zones.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 167 generation interconnection or change requests |  |  |  |  |
| As of February 29, 2012 | North | South | West | Total |
| Security Screening Study | 0 | 1 | 4 | 5 |
| SSS Completed | 4 | 5 | 8 | 17 |
| Full Interconnect Study | 8 | 19 | 48 | 75 |
| FIS Completed | 1 | 2 | 5 | 8 |
| Suspended Studies | 8 | 4 | 28 | 40 |
| Capacity of Suspended Study Projects | 6,486 | 3,338 | 11,273 | 21,097 |
| Interconnect Agreement Completed | 8 | 10 | 4 | 22 |
| Capacity under Interconnection Agreements | 5,294 | 4,340 | 720 | 10,354 |
| Capacity for Grid, MW | 8,918 | 10,545 | 14,349 | 33,812 |
| Wind Capacity, MW | 2,894 | 3,331 | 11,845 | 18,069 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 1,014 |
| Gas-CombinedCycle |  |  | 5,449 | 2,890 | 10,642 |
| Total Gas | 1,843 | 1,474 | 5,449 | 2,890 | 11,656 |
| Nuclear |  |  |  | 5,900 | 5,900 |
| Coal |  | 850 | 2,785 |  | 3,635 |
| Wind | 1,730 | 14,119 | 2,220 | 11,904 | 29,973 |
| Solar | 315 | 481 | 60 | 353 | 1,209 |
| Biomass |  |  | 100 | 50 | 150 |
| Storage | 560 | 346 |  |  | 906 |
| Other |  | 240 | 1,240 |  | 1,480 |
| Grand Total | 4,448 | 17,510 | 11,854 | 21,097 | 54,909 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

(Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of February 29, 2012 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 |  | Biomass |  | 100 |  |
| 10INR0060 | Redfish Wind Project | IA | Willacy | South | Jun-12 |  | Wind |  | 206 | Name |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 |  | Solar |  | 60 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-12 |  | Wind |  | 150 |  |
| 12INR0075 | Blue Summit Windfarm | IA | Wilbarger | West | Nov-12 |  | Wind |  | 170 | New |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 |  | Wind |  | 100 |  |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 |  | Wind |  | 92 |  |
| 10INR0023 | Baker Ranch | IA | Haskell | West | Dec-12 |  | Wind |  | 400 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 |  | Wind |  | 50 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 |  | Coal |  | 925 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 10INR0021 | Panda Sherman Power | IA | Grayson | North | Jul-14 |  | Gas-CC |  | 717 | New |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 |  | Wind |  | 120 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Jan-15 |  | Gas-CC |  | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-15 |  | Gas-CC |  | 1,792 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other |  | 620 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Jan-16 |  | Gas-CC |  | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jan-16 |  | Gas-CC |  | 1,380 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other |  | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
|  |  |  |  |  |  |  | Total |  | 10,354 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1,200 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 11INR0054 | San Patricio | 161 | TBD | Wind |
| 10INR0062a | Pecos | 80 | TBD | Wind |  | 11INR0094 | Kent | 100 | TBD | Solar |
| 12INR0086 | Harris | 89 | Jun-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0050 | King | 332 | Jun-12 | Wind |
| 11INR0085 | Nolan | 106 | Jul-12 | Wind |  | 12INR0079 | Kenedy | 200 | Aug-12 | Wind |
| 12INR0076 | Winkler | 36 | Sep-12 | Other |  | 12INR0075 | Wilbarger | 170 | Nov-12 | Wind |
| 13INR0036 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0071 | Caldwell | 30 | Dec-12 | Wind |
| 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |  | 12INR0067 | Webb | 94 | Dec-12 | Wind |
| 11INR0093 | San Patricio | 41 | Dec-12 | Wind |  | 11INR0091 | Webb | 92 | Dec-12 | Wind |
| 11INR0079a | Clay | 200 | Dec-12 | Wind |  | 12INR0059 | Pecos | 50 | Dec-12 | Solar |
| 12INR0057 | Ector | 50 | Dec-12 | Solar |  | 12INR0060 | Schleicher | 58 | Dec-12 | Wind |
| 12INR0055 | Baylor | 80 | Dec-12 | Wind |  | 10INR0023 | Haskell | 400 | Dec-12 | Wind |
| 09INR0048 | Jack | 113 | Dec-12 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-12 | Wind |
| 12INR0085 | Stonewall | 25 | Dec-12 | Wind |  | 12INR0081 | Upton | 113 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 13INR0040 | Harris |  | Jan-13 | Gas |
| 13INR0010a | Parmer | 200 | Jan-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0050 | Crosby | 149 | Mar-13 | Wind |
| 09INR0051 | Borden | 249 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 12INR0070 | Knox | 300 | Apr-13 | Wind |  | 10INR0089 | Harris | 40 | May-13 | Other |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 10INR0085 | Ector | 40 | May-13 | Solar |  | 13INR0031 | Austin | 30 | Jun-13 | Solar |
| 12INR0045 | Kleberg | 135 | Jun-13 | Wind |  | 13INR0032 | Andrews | 30 | Jun-13 | Solar |
| 13INR0023 | Ector | 240 | Jul-13 | Other |  | 13INR0025 | Randall | 150 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |
| 13INR0050 | Comanche | 260 | Dec-13 | Wind |  | 13INR0038 | Swisher | 300 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 13INR0044 | Wilacy | 400 | Dec-13 | Wind |
| 13INR0039 | Castro | 500 | Dec-13 | Wind |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 12INR0058 | San Patricio | 50 | Dec-13 | Wind |  | 11INR0057 | Cameron | 165 | Dec-13 | Wind |
| 12INR0034 | Borden | 342 | Dec-13 | Wind |  | 14INR0014 | Val Verde | 100 | Jan-14 | Solar |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 10INR0080 | Presidio | 81 | Jan-14 | Solar |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0016 | Harris | 190 | Jun-14 | Gas |
| 14INR0015 | Harris | 192 | Jun-14 | Gas |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0012 | Gray | 401 | Jun-14 | Wind |  | 10INR0021 | Grayson | 717 | Jul-14 | Gas |
| 14INR0010 | Roberts | 300 | Jul-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 13INR0021 | Llano | 600 | Dec-14 | Gas |
| 14INR0009 | Kent | 248 | Dec-14 | Wind |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 14INR0003 | Nolan | 850 | Jun-18 | Coal |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

Wind Generation    Wind Capacity Installed by Year

County Location of Installed Generation and Interconnection Requests (Wind Generation Projects Only)

# Regional Planning Group Project Reviews

- South Texas Electric Cooperative (STEC) has submitted the El Campo to Vanderbilt rebuild project to rebuild the existing 69 kV transmission line between El Campo and Vanderbilt with a double circuit 138/69 kV line. The proposed project is to accommodate 118 MW of new load in Jackson County. This is a Tier 2 project that is estimated to cost $26.8 million. This project has completed the Independent Review and ERCOT has sent the RPG acceptance letter.

- South Texas Electric Cooperative (STEC) has submitted the Karnes Electric Cooperative (KEC) load addition project to accommodate 167 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $33.1 million. This Tier 2 project is undergoing ERCOT Independent Review.

- CenterPoint Energy has submitted the Mont Belvieu Area upgrades project. This is a Tier 3 project that is estimated to cost approximately $42 million. This project has been submitted for RPG comments.

- Texas Municipal Power Agency (TMPA) has submitted the Denton 138 kV loop upgrades project. This is a Tier 3 project that is estimated to cost approximately $21.1 million. This project has been submitted for RPG comments.

- LCRA TSC, San Bernard Electric Cooperative (SBEC), and South Texas Electric Cooperative (STEC) have jointly submitted the Glidden to Colorado to Nada 69 kV upgrade project. This is a Tier 3 project that is estimated to cost approximately $32.4 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

RUC net Make Whole payment in million$

Monthly Average LMP

Binding Constraints - February 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 1763 | 0 - 136 | 6,090,505 | CREZ |  |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69 kV Autotransformer | 700 | 0 - 2275 | 3,340,495 | 5YTP [2010-R7, R8] |  |
| Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 1797 | 0 - 129 | 2,191,125 | CREZ | High west wind generation |
| Scurry Switch - Sun Switch 138 kV, Aspermont Aep - Spur 138 kV, Salt Creek Bepc - Salt Creek Reactor 138 kV | Girard Tap - Spur 69 kV | 2708 | 0 - 2800 | 1,800,958 |  | High west wind generation; Outage on Matador-Paducah 69 kV line |
| San Angelo Red Creek 345/138kV autotransformer T1 | San Angelo Red Creek 345/138 kV autotransformer T2 | 21 | 20 - 3500 | 891,664 | CREZ |  |
| Fort Stockton Plant - Barrilla 138 kV | Barrilla - Fort Stockton Switch 69 kV | 906 | 0 - 1186 | 684,921 | CREZ | High west wind generation |
| Graham SES - Long Creek 345 kV, Bracketville - Asphalt Mines | Hamilton Road - Maverick 138 kV | 263 | 3 - 456 | 585,740 | CREZ | High west wind generation |
| Orange Grove Switching Station - Lon_Hill 138 kV, Pawnee - Lon_Hill 345 kV, Whitepoint 345/138 kV autotransformer | Sinton - Skidmore 69 kV | 678 | 0 - 1646 | 394,911 |  |  |
| Willow Creek Switch - Parker Switch 345 kV | Fort Worth Substation - West Denton 138 kV | 34 | 209 - 555 | 279,252 | 5YTP [2010-R12] |  |
| Lewisville Switch - Carrollton Northwest | Lewisville Switch - Jones Street Tnp 138 kV | 94 | 1 - 262 | 220,211 | 5YTP [2010-R21] | Outage on West Tnp - TI TNP 138 kV |

Binding Constraints – January to February 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 4265 | 0 - 436 | 14,454,858 | CREZ |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69 kV Autotransformer | 936 | 0 - 2275 | 4,333,342 | 5YTP [2010-R7, R8] |
| Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 2462 | 0 - 132 | 3,023,165 | CREZ |
| Scurry Switch - Sun Switch 138 kV, Aspermont Aep - Spur 138 kV, Salt Creek Bepc - Salt Creek Reactor 138 kV | Girard Tap - Spur 69 kV | 2708 | 0 - 2800 | 1,800,958 |  |
| Aspermont - Paint Creek 138 kV, Sacroc - Sun Switch 138 kV, Scurry Switch - Sun Switch, Salt Creek - Spur 138 kV | Aspermont 138/69 kV autotransfomer T1 | 3509 | 0 - 332 | 1,622,045 | CREZ |
| Fort Stockton Plant - Barrilla 138 kV, Crane Arco - Pegasus 138 kV | Barrilla - Fort Stockton Switch 69 kV | 1708 | 0 - 1186 | 1,226,150 | CREZ |
| Nelson Sharpe - Lon_Hill 345 kV | Kingsville - Lon_Hill 138 kV | 41 | 0 - 3500 | 1,153,541 |  |
| Orange Grove Switching Station - Lon_Hill 138 kV, Pawnee - Lon_Hill 345 kV, Whitepoint 345/138 kV autotransformer | Sinton - Skidmore 69 kV | 1604 | 0 - 2800 | 1,112,259 |  |
| San Angelo Red Creek 345/138kV autotransformer T1 | San Angelo Red Creek 345/138 kV autotransformer T2 | 21 | 20 - 3500 | 891,664 | CREZ |
| Wharton - Dyann 138 kV | Blessing - Lane City 138 kV | 349 | 0 - 3500 | 614,631 |  |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The December TPIT updates to the base cases were completed and the cases were posted on ERCOT MIS and POI.  Work has begun to update all the base cases to use the transmission topology from the Topology Processor.

| By second week of April | 13DSA Initial case build |
| --- | --- |
| By second week of April | 13DSA NOIE dispatch due to ERCOT |
| By first week of May | 12DSA/12DSB TPIT March updates are posted at the ERCOT POI site |
| By June 30 | SSWG meeting (at ERCOT in Taylor, TX) |
| By August 1st | 13DSA cases and June TPIT updates are posted at the ERCOT POI site |

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2, 4, 9):  In Production.

  - Bundle 3 (Items 5, 2b, and 2c):  Requirements are complete.  Vendor estimate received and being negotiated.  Item 5 target date for production is before the start of 2013 Data Set B in July 2012.  Items 2b and 2c are extensions of Bundle 2 Item 2 to make RMPCT and Control Mode available for existing ShuntCompensator objects and may not be available prior to 2013 Data Set B.

  - Bundle 4 (Items 1 and 6):

    - For Item 1, a process to determine the new fields and records that need to be implemented in NMMS for new releases of PSS/E has been created and added to the SSWG Procedure Manual.  This item will be given the status of Production. Item 6 is considered to be the first implementation of this process.

    - For Item 6, ERCOT and TSPs have identified new fields or records added between version 33 and version 30 of the PSS/E RAWD format and have decided which new fields need to be implemented.  Requirements have started but are on-hold awaiting SOW for Bundle 3.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The 2011 Five-Year Transmission Plan reliability analysis has been completed for 2012, 2014 and 2016 and all the reliability projects are posted on the ERCOT Planning and Operations Information. Work on the 2011 Five-Year Transmission Plan economic analysis is ongoing. ERCOT is also working on the 2011 Five-Year Transmission Plan draft report that is expected to be completed in March 2012.