## Slide 1
Business Integration Update to PRS
March 22, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-5
    Recent and Upcoming Project Implementations
    2012 Release Targets
    Project Spending Update
  ERCOT FTE Tracking p. 6
  2013 Project Funding p. 7-10
  Appendix
    Project Portfolio Gantt Chart p. 12-16

## Slide 3: Recent and Upcoming Project Implementations
Go-Lives in March (no integrated software release)
  Compliance Software Purchase and Installation
  Cyber Security Project #3
Go-Lives in April
  NPRR314 – Requirement to Post Generation Resources Temporal Constraints
  NPRR359 – Monthly TDSP Load Report
  NPRR361 – Real-Time Wind Power Production Data Transparency
  NPRR395 – CRR Auction Offer Award Disclosure
  Outage Capacity Calculation Tool
  EDW Platform Transition
  RARF Upgrade for Wind, Solar, and Storage Resources
  Cyber Security Project #2
Go-Lives in May (no integrated software release)
  NPRR434 – Increase the Capacity Limitation of a Generation Resource Providing RRS
    Current target is to deliver this in May as an off-cycle release
    The project team is evaluating whether it can be included in the April release to leverage deployment resources
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs
Off-cycle May Release or Release 2
Off-cycle
Source | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
Market / PUCT | SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR294 NPRR403 SCR756(a) NPRR351 NPRR357 NPRR360 NPRR382 SCR760(c) | NPRR313 NPRR322 NPRR354 NPRR383 NPRR422 | NPRR207 NPRR222 NPRR272 | NPRR260 | NPRR407 SCR756(b)
ERCOT | NPRR326 NPRR355 |  | NPRR379 NPRR437 | NPRR348 NPRR365 | NPRR377 |  | NPRR347 NPRR400
Counts Total = 36 | 5 | 5 | 10 | 7 | 4 | 1 | 4
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change

## Slide 5: Project Spending Update – 2/29/2012
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,650,167 | $ 872,368
Regulatory |  | $ 1,600,000 | $ 891,940 | $ 173,427
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,802,148 | $ 324,138
Technical Foundation |  | $ 6,500,000 | $ 7,540,189 | $ 877,846
Totals | $ 15,000,000 | $ 16,100,000 | $ 18,884,444 | $ 2,247,779
ERCOT Public

## Slide 6: ERCOT FTE (Full Time Equivalent) Tracking
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Board approved - 2/21/2012
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 5.80 | 2 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | To be considered at 4/17/2012 Board
NPRR393 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | To be considered at 4/17/2012 Board
NPRR421 | Operations | Operations Analysis | 1.00 | 1 | $120k-$130k | To be considered at 4/17/2012 Board
 | Operations | Wholesale Client Svs | 0.25 | 0 | $0 | 
 | In-Flight at TAC |  | 3.25 | 3 |  | 
 | Total of All Items |  | 9.05 | 5 |  | 

## Slide 7: 2013 Project Funding – Introductory Comments
Accelerated review and approval schedule for ERCOT’s budget filing
  April Board Review
  May PUCT Review
$15M is expected to be allocated for capital projects in 2013
  No change from 2012
Multi-Year PPL will be used to forecast projects expected in 2013
  No need for extensive bottom-up PPL effort
In order to reserve funds for NPRRs and SCRs that will be filed and approved over the next 18 months, ERCOT proposes $3M in PPL funding for 2013 NPRR/SCR activity
  This is not a cap on NPRR/SCR funding
  If the Board directs NPRR/SCR spending in excess of $3M, priorities will be reassessed and/or a request for additional funding will be considered

## Slide 8: 2013 Project Funding – Schedule
February 2012
  Initial review at PRS (February 23)
March 2012
  Review at market subcommittee meetings
    WMS (March 7)
    ROS (March 8)
    RMS (March 21)
    PRS (March 22)
    COPS (April 10)
April 2012
  Review at TAC (April 5)
  Available for F&A and Board review (April 16)
May 2012
  Review at PUCT (May 1)
ü
ü

## Slide 9: 2013 Project Funding – Introductory Comments (cont’d)
Is $3M sufficient for 2013 NPRRs and SCRs?
  Answer: Most Likely (in ERCOT’s opinion)
  2011 activity was reviewed to assist in formulating this estimate
    In 2011, $3.4M was spent on nearly 40 NPRRs and SCRs
      Funded by both the PPL and Nodal Stabilization
      Includes $0.9M spent on the Texas SET 4.0 project
  The $3M funding would include NPRRs already on the PPL and targeted for 2013 delivery
    NPRR181, NPRR210, NPRR240, NPRR241, NPRR256
      Sum of the forecasts for these items is $550k
    Remaining $2.45M in funding would be held in an NPRR/SCR placeholder
Management of the NPRR/SCR placeholder
  As new NPRRs and SCRs targeted for 2013 are approved by the Board, the appropriate amount will be deducted from the placeholder

## Slide 10: 2013 Project Funding – Additional Information
The current 2013 spending forecast on the Multi-Year PPL is >$20M
  This estimate includes the proposed $3M funding for NPRR/SCR work
  ERCOT staff is working to reconsider and reprioritize internal project efforts to get the forecast closer to the $15M budget level
  Reminder: In the 2012 project budget approval process, we had a $16.1M spending forecast for a $15M budget
    We expect to take a similar approach for the 2013 project proposal
ERCOT will be visiting WMS, ROS and RMS in March to review the new approach (COPS in April)
In March, ERCOT will ask PRS to endorse the NPRR/SCR funding concept and amount
In April, ERCOT will ask TAC to endorse the NPRR/SCR funding concept and amount

## Slide 11: Business Integration Update – Appendix
  Appendix
    3/16/2012 Project Gantt

## Slide 12
Project Portfolio Status – as of 3/16/2012

## Slide 13
Project Portfolio Status – as of 3/16/2012

## Slide 14
Project Portfolio Status – as of 3/16/2012

## Slide 15
Project Portfolio Status – as of 3/16/2012

## Slide 16
Project Portfolio Status – as of 3/16/2012