|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report March 2012 |
|  | Report Highlights |  |
|  | ERCOT is currently tracking 128 active generation interconnection requests totaling over 34,000 MW. This includes over 19,000 MW of wind generation. |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $74.2 Million Transmission Projects endorsed in 2012 total $394 Million All projects (in engineering, routing, licensing and construction) total approximately $9.84 Billion Transmission Projects energized in 2012 total about $108.8 million |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

12INR0034 Stephens-Borlynn Wind – 378 MW in Borden County

## New Generation Registering for Commercial Operations

Non-Modeled SUNEDISON VALLEY ROAD – 9.9 MW Solar in Bexar County

Non-Modeled SUNEDISON RABEL ROAD – 9.9 MW Solar in Bexar County

The total installed wind capacity is now reported as 9,838 MW by the resource owners through the registration process. Capacity by North, South and West is 232 MW,  2075 MW, and 7531 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |
| --- |
| Currently tracking 168 generation interconnection or change requests |
| As of March 31, 2012 | North | South | West | Total |
| Security Screening Study | 0 | 2 | 2 | 4 |
| SSS Completed | 3 | 5 | 7 | 15 |
| Full Interconnect Study | 7 | 17 | 48 | 72 |
| FIS Completed | 2 | 5 | 7 | 14 |
| Suspended Studies | 8 | 3 | 28 | 39 |
| Capacity of Suspended Study Projects | 6,486 | 638 | 11,273 | 18,397 |
| Interconnect Agreement Completed | 8 | 10 | 5 | 23 |
| Capacity under Interconnection Agreements | 5,294 | 4,340 | 1,098 | 10,732 |
| Capacity for Grid, MW | 9,610 | 10,653 | 14,524 | 34,787 |
| Wind Capacity, MW | 3,616 | 3,398 | 12,110 | 19,124 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 1,014 |
| Gas-CombinedCycle |  |  | 5,449 | 2,890 | 10,642 |
| Total Gas | 1,843 | 1,474 | 5,449 | 2,890 | 11,656 |
| Nuclear |  |  |  | 3,200 | 3,200 |
| Coal |  | 850 | 2,785 |  | 3,635 |
| Wind | 2,266 | 14,260 | 2,598 | 11,904 | 31,028 |
| Solar | 235 | 481 | 60 | 353 | 1,129 |
| Biomass |  |  | 100 | 50 | 150 |
| Storage | 560 | 346 |  |  | 906 |
| Other |  | 240 | 1,240 |  | 1,480 |
| Grand Total | 4,904 | 17,651 | 12,232 | 18,397 | 53,184 |

County Location of Installed Generation and Interconncection Requests (all fuels)

## Projects with Interconnection Agreements

(Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of March 31, 2012 |
| --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type | MW For Grid | Change from Last Report |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Jun-12 | Biomass | 100 |  |
| 10INR0060 | Redfish Wind Project | IA | Willacy | South | Jun-12 | Wind | 206 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 | Solar | 60 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-12 | Wind | 150 |  |
| 12INR0075 | Blue Summit Windfarm | IA | Wilbarger | West | Nov-12 | Wind | 170 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 | Wind | 30 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 | Wind | 100 |  |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 | Wind | 92 |  |
| 10INR0023 | Baker Ranch | IA | Haskell | West | Dec-12 | Wind | 400 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 | Wind | 400 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 | Wind | 50 |  |
| 12INR0034 | Stephens-Borlynn Wind | IA | Borden | West | Dec-13 | Wind | 378 | New |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 | Coal | 925 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 | Wind | 202 |  |
| 10INR0021 | Panda Sherman Power | IA | Grayson | North | Jul-14 | Gas-CC | 717 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 | Wind | 120 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Jan-15 | Gas-CC | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-15 | Gas-CC | 1,792 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 | Other | 620 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Jan-16 | Gas-CC | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jan-16 | Gas-CC | 1,380 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 | Other | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 | Coal | 660 |  |
|  |  |  |  |  |  | Total | 10,732 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1,200 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 10INR0062a | Pecos | 80 | TBD | Wind |
| 11INR0094 | Kent | 100 | TBD | Solar |  | 12INR0087 | Harris | 144 | Jun-12 | Gas |
| 12INR0086 | Harris | 89 | Jun-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 12INR0050 | King | 332 | Jun-12 | Wind |
| 12INR0079 | Kenedy | 200 | Aug-12 | Wind |  | 12INR0076 | Winkler | 36 | Oct-12 | Other |
| 12INR0089 | Pecos | 230 | Nov-12 | Wind |  | 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |
| 12INR0067 | Webb | 94 | Dec-12 | Wind |  | 11INR0093 | San Patricio | 41 | Dec-12 | Wind |
| 11INR0081 | Live Oak | 72 | Dec-12 | Wind |  | 12INR0059 | Pecos | 50 | Dec-12 | Solar |
| 12INR0057 | Ector | 50 | Dec-12 | Solar |  | 12INR0060 | Schleicher | 58 | Dec-12 | Wind |
| 12INR0055 | Baylor | 80 | Dec-12 | Wind |  | 09INR0048 | Jack | 113 | Dec-12 | Wind |
| 12INR0088 | Crosby | 201 | Dec-12 | Wind |  | 12INR0085 | Stonewall | 25 | Dec-12 | Wind |
| 12INR0081 | Upton | 113 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 13INR0040 | Harris |  | Jan-13 | Gas |  | 13INR0051 | Cameron | 67 | Jan-13 | Wind |
| 13INR0010a | Parmer | 200 | Jan-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0050 | Crosby | 149 | Mar-13 | Wind |
| 09INR0051 | Borden | 249 | Mar-13 | Wind |  | 13INR0045 | Castro | 288 | Apr-13 | Wind |
| 12INR0018 | Gray | 500 | Apr-13 | Wind |  | 12INR0070 | Knox | 300 | Apr-13 | Wind |
| 10INR0089 | Harris | 40 | May-13 | Other |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 10INR0085 | Ector | 40 | May-13 | Solar |
| 13INR0031 | Austin | 30 | Jun-13 | Solar |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 13INR0032 | Andrews | 30 | Jun-13 | Solar |  | 13INR0023 | Ector | 240 | Jul-13 | Other |
| 13INR0048 | Oldham | 150 | Jul-13 | Wind |  | 13INR0049 | Harris | 378 | Jul-13 | Gas |
| 13INR0046 | Limestone | 71 | Sep-13 | Wind |  | 13INR0025 | Randall | 150 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 12INR0071 | Caldwell | 30 | Nov-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 13INR0047 | Cooke | 20 | Dec-13 | Solar |
| 13INR0050 | Comanche | 260 | Dec-13 | Wind |  | 13INR0038 | Swisher | 300 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 14INR0019 | Wilacy | 400 | Dec-13 | Wind |
| 13INR0044 | Wilacy | 400 | Dec-13 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-13 | Wind |
| 13INR0039 | Castro | 500 | Dec-13 | Wind |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 11INR0085 | Nolan | 106 | Dec-13 | Wind |
| 10INR0009 | Castro | 300 | Dec-13 | Wind |  | 12INR0058 | San Patricio | 50 | Dec-13 | Wind |
| 11INR0057 | Cameron | 165 | Dec-13 | Wind |  | 14INR0013 | Cameron | 103 | Jan-14 | Wind |
| 14INR0014 | Val Verde | 100 | Jan-14 | Solar |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 12INR0084 | Randall | 242 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 10INR0080 | Presidio | 81 | Jan-14 | Solar |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0016 | Harris | 190 | Jun-14 | Gas |
| 14INR0015 | Harris | 192 | Jun-14 | Gas |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0021 | Erath | 125 | Jun-14 | Wind |  | 14INR0012 | Gray | 401 | Jun-14 | Wind |
| 14INR0024 | Kinney | 40 | Jul-14 | Solar |  | 11INR0054 | San Patricio | 161 | Jul-14 | Wind |
| 14INR0010 | Roberts | 300 | Jul-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 13INR0021 | Llano | 600 | Dec-14 | Gas |
| 14INR0023 | Briscoe | 361 | Dec-14 | Wind |  | 14INR0022 | Briscoe | 361 | Dec-14 | Wind |
| 14INR0018 | Nolan | 35 | Dec-14 | Solar |  | 14INR0020 | Floyd | 150 | Dec-14 | Wind |
| 14INR0009 | Kent | 248 | Dec-14 | Wind |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 11INR0079a | Clay | 200 | Dec-14 | Wind |  | 13INR0010c | Parmer | 500 | Jan-15 | Wind |
| 15INR0013 | Anderson | 280 | Oct-15 | Gas |  | 15INR0014 | Matagorda | 280 | Oct-15 | Gas |
| 15INR0012 | DeWitt | 1,321 | Dec-15 | Gas |  | 15INR0015 | Pecos | 140 | Dec-15 | Solar |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 16INR0003 | Brazoria | 11 | Jun-16 | Gas |
| 14INR0003 | Nolan | 850 | Jun-18 | Coal |  |  |  |  |  |  |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- South Texas Electric Cooperative (STEC) has submitted the Karnes Electric Cooperative (KEC) load addition project to accommodate 167 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $33.1 million. This Tier 2 project is undergoing ERCOT Independent Review.

- CenterPoint Energy has submitted the Mont Belvieu Area upgrades project. This is a Tier 3 project that is estimated to cost approximately $42 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- Texas Municipal Power agency (TMPA) has submitted the Denton 138 kV loop upgrades project. This is a Tier 3 project that is estimated to cost approximately $21.1 million. This project is currently in the study mode.

- LCRA TSC, San Bernard Electric Cooperative (SBEC), and South Texas Electric Cooperative (STEC) has jointly submitted the Glidden to Colorado to Nada 69 kV upgrade project. This is a Tier 3 project that is estimated to cost approximately $32.4 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- AEPSC has submitted the Lobo – Rio Bravo 138 kV line project. This is a Tier 3 project that is estimated to cost approximately $20 million. This project is currently in the study mode.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 5751 | 0 - 436 | 19,466,587 | CREZ |
| Lewisville Switch - Carrollton Northwest 345 kV | Lewisville Switch - Jones Street Tnp 138 kV | 2733 | 0 - 2870 | 10,801,138 | 07TPIT0042 |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69 kV Autotransformer | 1508 | 0 - 2800 | 7,750,232 | 5YTP [2010-R7, R8] |
| Midland East - Cal Energy 345 kV | China Grove - Bluff Creek 138 kV | 216 | 0 - 3500 | 6,222,628 |  |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 54 | 0 - 4500 | 4,592,529 | 14TPIT0050 |
| Bluff Creek Auto T2_H & T2_L & T2_T | Nicole - Oak Creek 138kV | 2629 | 0 - 132 | 3,254,766 | CREZ |
| Scurry Switch - Sun Switch 138 kV, Aspermont Aep - Spur 138 kV, Salt Creek Bepc - Salt Creek Reactor 138 kV | Girard Tap - Spur 69 kV | 4677 | 0 - 2800 | 3,136,124 | CREZ |
| Fort Stockton Plant - Barrilla 138 kV | Barrilla - Fort Stockton Switch 69 kV | 2805 | 0 - 1263 | 2,250,880 | CREZ |
| Aspermont - Paint Creek 138 kV, Sacroc - Sun Switch 138 kV, Scurry Switch - Sun Switch, Salt Creek - Spur 138 kV | Aspermont 138/69 kV autotransfomer T1 | 4536 | 0 - 332 | 2,038,781 | CREZ |
| Cal Energy - Morgan Creek 345 kV | McDonald - Forsan Tap 138 kV | 56 | 3 - 3500 | 1,456,070 | CREZ |

Binding Constraints – March 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Lewisville Switch - Carrollton Northwest 345 kV | Lewisville Switch - Jones Street Tnp 138 kV | 2639 | 0 - 2870 | 10,580,927 | 07TPIT0042 |  |
| Midland East - Cal Energy 345 kV | China Grove - Bluff Creek 138 kV | 216 | 0 - 3500 | 6,222,628 |  | Moss Switch bus outage |
| BASE CASE | West to North Stability Limit | 1486 | 0 - 68 | 5,011,729 | CREZ | High west wind |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 54 | 0 - 4500 | 4,592,529 | 14TPIT0050 |  |
| Amoco North Cowden Tap - Moss Switch 138kV | Odessa North 138/69 kV Autotransformer | 572 | 0 - 2800 | 3,416,891 | 5YTP [2010-R7, R8] | Moss Switch bus outage and high west wind |
| Cal Energy - Morgan Creek 345 kV | McDonald - Forsan Tap 138 kV | 56 | 3 - 3500 | 1,456,070 | CREZ | High west wind |
| Scurry Switch - Sun Switch 138 kV, Aspermont Aep - Spur 138 kV, Salt Creek Bepc - Salt Creek Reactor 138 kV | Girard Tap - Spur 69 kV | 1969 | 0 - 1329 | 1,335,166 | CREZ | High west wind and Matador -Paducah 69 kV line outage |
| Fort Stockton Plant - Barrilla 138 kV | Barrilla - Fort Stockton Switch 69 kV | 1097 | 0 - 1263 | 1,024,730 | CREZ | High McCamey and West wind |
| Odessa EHV - Crane Arco 138 kV | Woodward - 16th Street 138 kV | 958 | 0 - 173 | 665,813 | CREZ | High west wind |
| Morgan Creek SES - Sun Switch 138 kV | China Grove - Snyder 138 kV | 79 | 34 - 3500 | 659,512 | CREZ | High west wind |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The March TPIT update is underway utilizing for the first time the topology from the NMMS Topology Processor (TP) in the Model on Demand (MOD) case building environment.  TSP’s and ERCOT have been reviewing all PMCR’s for relevancy and updating the generation, load, and device control profiles to match the slightly different topology.

- Network Operations Model Change Requests (NOMCR’s) were submitted by TSP’s to populate data for new data types recently made available by completion of Bundle 2 of SCR760, which included sub parts 2, 4, and 9 from the table below.  An incremental update to the NMMS Topology Processed base case in MOD was made to insert the data as a Planning Model Change Request (PMCR).

- The short term calendar of major events during Planning Go-Live follows:

  - Feb 27, 2012	ERCOT produces TP case with 7/1/2012 energization date and uses this output as the new base case in MOD.

  - Feb 29, 2012	Planning Go-Live initiated with creation of a MOD base case utilizing the TP case produced two days earlier.

  - Apr 30, 2012	Creation of 13DSA Pass 1 cases

  - May 11, 2012	March TPIT case posted on POI.

  - Aug 1, 2012	13DSA cases completed and posted on POI.

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  Sample TP output produced by vendor and examined by ERCOT.  TP Release expected during week of Apr 9th.  Target June production date.

  - Bundle 4 (Items 1, 6):  ERCOT and TSPs have identified new fields or records added between version 33 and version 30 of the PSS/E RAWD format and are decided which new fields need to be implemented.  The evaluation process for Item 1 has been added to the SSWG Procedure Manual as section 5.3.  Item 1 considered to be in production.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Planning |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The System Protection Working Group 2012 Current Year (CY) case completed.  An attempt was made by ERCOT and TSPs to make the SPWG 2012 CY generation include all the generation in the 2012 SUM1 SSWG case with matching bus numbers, names, and machine ID.  Some changes to accomplish the matching had to be backed out due to lack of complete and detailed RARF information that resulted in fault-current differences that could not be accepted by SPWG.  This could be due to required fields in the current RARF being blank and to the fact that the current RARF does not include zero sequence data place-holders for lines and transformers.  This should be rectified by October 2012 as RARF 5.0 has been released that contains these fields.  Resource Entities and Interconnecting Entities need to provide this data by the required date.

- The 2011 Five-Year Transmission Plan reliability analysis has been completed including both reliability and economic studies. All of the reliability and economic final cases are posted on the ERCOT Planning and Operations Information website. ERCOT has sent the 2011 Five-Year Transmission Plan draft report to the TOs and received feedback from TOs. The final report is expected to be posted before the next RPG meeting (April 13, 2012).

- ERCOT System Planning is reviewing and comparing the dynamic model data submitted through the RARF to the DWG dynamic base case. Review results are being provided to Resource Entities for updates and confirmation.

- ERCOT is spot checking governor model performance by comparing the actual measurement with dynamic model response. Review results will be provided to Resource Entities for updates and confirmation.