## Slide 1
Business Integration Update to PRS
April 19, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets (draft)
    Project Spending Update
  ERCOT FTE Tracking p. 7
  2013 Project Funding Approval p. 8-9
  Appendix
    Project Portfolio Gantt Chart p. 10-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in April
  NPRR314 – Requirement to Post Generation Resources Temporal Constraints
  NPRR359 – Monthly TDSP Load Report
  NPRR361 – Real-Time Wind Power Production Data Transparency
  NPRR395 – CRR Auction Offer Award Disclosure
  NPRR434 – Increase the Capacity Limitation of a Generation Resource Providing RRS
  Outage Capacity Calculation Tool
  EDW Platform Transition
  Cyber Security Project #2
Go-Lives in May (no integrated software release)
  Quality Training Database
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 RMGRR100 SCR760(c) | NPRR365 NPRR382 NPRR383 NPRR422 | NPRR207 NPRR313 NPRR322 NPRR397 | NPRR222 NPRR260 NPRR272 NPRR377 NPRR419 SCR756(b) SCR768 | 
Off-Cycle |  |  | NPRR294 NPRR403 SCR756(a) | NPRR348 NPRR354(b) | NPRR357 | NPRR347 NPRR400 | 
Counts Total = 40 | 5 | 5 | 10 | 6 | 5 | 9 | 0
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change
November
None
Late July
Early June
None
Early Oct

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release | Rel 1 TBD | Rel 2 TBD | Rel 3 TBD | Rel 4 TBD | Rel 5 TBD | Rel 6 TBD | 2013 TBD
On-Cycle |  | SCR760(d) | NPRR327 NPRR393 SCR769 | NPRR407 |  |  | 
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 5 |  | 1 | 3 | 1 |  |  | 
Note 1: Underline indicates new/revised release targets
Note 2: (a), (b), etc. indicates multiple release phases
Note 3: Release targets are subject to change

## Slide 6: Project Spending Update – 3/31/2012
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,753,950 | $ 1,375,150
Regulatory |  | $ 1,600,000 | $ 1,056,195 | $ 339,035
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,906,530 | $ 467,628
Technical Foundation |  | $ 6,500,000 | $ 8,583,718 | $ 1,368,469
Totals | $ 15,000,000 | $ 16,100,000 | $ 20,300,393 | $ 3,550,282
ERCOT Public

## Slide 7: ERCOT FTE (Full Time Equivalent) Tracking
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NPRR393 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Board approved - 2/21/2012
NPRR421 | Operations | Operations Analysis | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
 | Operations | Wholesale Client Svs | 0.25 | 0 | $0 | 
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 9.05 | 5 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
 | In-Flight at TAC |  | 0.00 | 0 |  | 
 | Total of All Items |  | 9.05 | 5 |  | 

## Slide 8: 2013 Project Funding Approval – Schedule
February 2012
    Initial review at PRS (February 23)
March 2012
  Review at market subcommittee meetings
    WMS (March 7)
    ROS (March 8)
    RMS (March 21)
    PRS (March 22)
    COPS (TBD)
April 2012
    Review at TAC (April 5)
    Available for F&A and Board review (April 16/17)
June / July 2012
    Approval at Board (no F&A meeting in May)
    Review at PUCT
ü
ü
ü
ü
ü
ü

## Slide 9: 2013 Project Funding Approval – Additional Information
TAC endorsed the NPRR/SCR funding concept and amount
The ERCOT F&A and Board reviewed the preliminary budget
The Board will reconsider the budget in June
After Board approval, the budget will be filed with the PUCT

## Slide 10: Business Integration Update – Appendix
  Appendix
    4/13/2012 Project Gantt
      Revision: Now sorted by Start Date

## Slide 11
Project Portfolio Status – as of 4/18/2012

## Slide 12
Project Portfolio Status – as of 4/18/2012

## Slide 13
Project Portfolio Status – as of 4/18/2012

## Slide 14
Project Portfolio Status – as of 4/18/2012

## Slide 15
Project Portfolio Status – as of 4/18/2012

## Slide 16
Project Portfolio Status – as of 4/18/2012

## Slide 17
Project Portfolio Status – as of 4/18/2012