|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report April 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 125 active generation interconnection requests totaling over 34,000 MW. This includes over 18,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $81.5 Million - Transmission Projects endorsed in 2012 total $413 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.84 Billion - Transmission Projects energized in 2012 total about $108.8 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

None for April 2012

## New Generation Registering for Commercial Operations

09INR0007 Nacogdoches Project  – 105 MW Biomass in Nacogdoches County

10INR0060 Redfish Wind Farm  – 206 MW Wind in Willacy County

The total installed wind capacity is now reported as 10,044 MW by the resource owners through the registration process. Capacity by North, South and West is 232 MW,  2,281 MW, and 7,531 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 166 generation interconnection or change requests |  |  |  |  |
| As of April 30, 2012 | North | South | West | Total |
| Security Screening Study | 1 | 1 | 2 | 4 |
| SSS Completed | 3 | 6 | 7 | 16 |
| Full Interconnect Study | 7 | 15 | 47 | 69 |
| FIS Completed | 3 | 5 | 7 | 15 |
| Suspended Studies | 8 | 3 | 30 | 41 |
| Capacity of Suspended Study Projects | 6,486 | 638 | 11,524 | 18,648 |
| Interconnect Agreement Completed | 7 | 9 | 5 | 21 |
| Capacity under Interconnection Agreements | 5,194 | 4,134 | 1,098 | 10,426 |
| Capacity for Grid, MW | 9,510 | 9,597 | 15,002 | 34,109 |
| Wind Capacity, MW | 3,616 | 2,342 | 12,560 | 18,518 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 1,014 |
| Gas-CombinedCycle |  |  | 5,449 | 2,890 | 10,642 |
| Total Gas | 1,843 | 1,474 | 5,449 | 2,890 | 11,656 |
| Nuclear |  |  |  | 3,200 | 3,200 |
| Coal |  | 2,050 | 1,585 |  | 3,635 |
| Wind | 2,295 | 14,131 | 2,092 | 12,154 | 30,672 |
| Solar | 263 | 481 | 60 | 353 | 1,157 |
| Biomass |  |  |  | 50 | 50 |
| Storage | 560 | 346 |  |  | 906 |
| Other |  | 240 | 1,240 |  | 1,480 |
| Grand Total | 4,961 | 18,722 | 10,426 | 18,647 | 52,756 |

County Location of Installed Generation and Interconncection Requests (all fuels)

## Projects with Interconnection Agreements

(Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of April 30, 2012 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 |  | Solar |  | 60 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-12 |  | Wind |  | 150 |  |
| 12INR0075 | Blue Summit Windfarm | IA | Wilbarger | West | Nov-12 |  | Wind |  | 170 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 |  | Wind |  | 100 |  |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 |  | Wind |  | 92 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 10INR0023 | Baker Ranch | IA | Haskell | West | Dec-12 |  | Wind |  | 400 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 |  | Wind |  | 50 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 |  | Coal |  | 925 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 12INR0034 | Stephens-Borlynn Wind | IA | Borden | West | Dec-13 |  | Wind |  | 378 |  |
| 10INR0021 | Panda Sherman Power | IA | Grayson | North | Jul-14 |  | Gas-CC |  | 717 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 |  | Wind |  | 120 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Jan-15 |  | Gas-CC |  | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-15 |  | Gas-CC |  | 1,792 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Oct-15 |  | Other |  | 620 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Jan-16 |  | Gas-CC |  | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jan-16 |  | Gas-CC |  | 1,380 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Oct-16 |  | Other |  | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
|  |  |  |  |  |  |  | TOTAL |  | 10,426 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1,200 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10INR0062a | Pecos | 80 | TBD | Wind |  | 11INR0094 | Kent | 100 | TBD | Solar |
| 12INR0053 | Crockett | 615 | Jun-12 | Wind |  | 12INR0086 | Harris | 89 | Jun-12 | Gas |
| 12INR0050 | King | 332 | Jun-12 | Wind |  | 12INR0079 | Kenedy | 200 | Aug-12 | Wind |
| 12INR0076 | Winkler | 36 | Oct-12 | Other |  | 12INR0089 | Pecos | 230 | Nov-12 | Wind |
| 11INR0081 | Live Oak | 72 | Dec-12 | Wind |  | 11INR0093 | San Patricio | 41 | Dec-12 | Wind |
| 12INR0055 | Baylor | 80 | Dec-12 | Wind |  | 12INR0057 | Ector | 50 | Dec-12 | Solar |
| 12INR0059 | Pecos | 50 | Dec-12 | Solar |  | 12INR0060 | Schleicher | 58 | Dec-12 | Wind |
| 12INR0067 | Webb | 94 | Dec-12 | Wind |  | 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |
| 12INR0080 | Floyd | 300 | Dec-12 | Wind |  | 09INR0048 | Jack | 113 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 12INR0081 | Upton | 113 | Dec-12 | Wind |
| 12INR0085 | Stonewall | 25 | Dec-12 | Wind |  | 13INR0040 | Harris |  | Jan-13 | Gas |
| 13INR0010a | Parmer | 200 | Jan-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 09INR0051 | Borden | 249 | Mar-13 | Wind |
| 11INR0050 | Crosby | 149 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 12INR0070 | Knox | 300 | Apr-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 10INR0089 | Harris | 40 | May-13 | Other |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 12INR0045 | Kleberg | 135 | Jun-13 | Wind |  | 13INR0031 | Austin | 30 | Jun-13 | Solar |
| 13INR0032 | Andrews | 30 | Jun-13 | Solar |  | 13INR0023 | Ector | 240 | Jul-13 | Other |
| 11INR0082A | Val Verde | 50 | Sep-13 | Wind |  | 11INR0083A | Crockett | 50 | Sep-13 | Wind |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 13INR0046 | Limestone | 71 | Sep-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 12INR0071 | Caldwell | 30 | Nov-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 11INR0085 | Nolan | 106 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0036 | Hidalgo | 200 | Dec-13 | Wind |  | 13INR0038 | Swisher | 300 | Dec-13 | Wind |
| 13INR0039 | Castro | 500 | Dec-13 | Wind |  | 13INR0050 | Comanche | 260 | Dec-13 | Wind |
| 13INR0052 | Starr | 200 | Dec-13 | Wind |  | 11INR0057 | Cameron | 165 | Dec-13 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 14INR0013 | Cameron | 103 | Jan-14 | Wind |  | 14INR0014 | Val Verde | 100 | Jan-14 | Solar |
| 10INR0080 | Presidio | 81 | Jan-14 | Solar |  | 13INR0010b | Parmer | 500 | Jan-14 | Wind |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0012 | Gray | 401 | Jun-14 | Wind |  | 14INR0015 | Harris | 192 | Jun-14 | Gas |
| 14INR0016 | Harris | 190 | Jun-14 | Gas |  | 11INR0054 | San Patricio | 161 | Jul-14 | Wind |
| 14INR0005 | Matagorda | 1,200 | Jul-14 | Coal |  | 14INR0010 | Roberts | 300 | Jul-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 10INR0085 | Ector | 40 | Dec-14 | Solar |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 13INR0021 | Llano | 600 | Dec-14 | Gas |  | 14INR0009 | Kent | 248 | Dec-14 | Wind |
| 14INR0020 | Floyd | 150 | Dec-14 | Wind |  | 11INR0079a | Clay | 200 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 14INR0003 | Nolan | 850 | Jun-18 | Coal |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- South Texas Electric Cooperative (STEC) submitted the Karnes Electric Cooperative (KEC) load addition project to accommodate 167 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $23.1 million. This Tier 2 project has completed ERCOT Independent Review and ERCOT will send the RPG acceptance letter.

- Texas Municipal Power Agency (TMPA) submitted the Denton 138 kV loop upgrades project. This is a Tier 3 project that is estimated to cost approximately $21.1 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- AEPSC submitted the Lobo – Rio Bravo 138 kV line project. This is a Tier 3 project that is estimated to cost approximately $20 million. This project has completed the RPG review and ERCOT will send the RPG acceptance letter.

- South Texas Electric Cooperative (STEC) has submitted the Karnes Electric Cooperative (KEC) and Medina Electric Cooperative (MEC) load addition project to accommodate 245 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $48.4 million. This project has been submitted for RPG comments.

- Oncor has submitted the Wink-Mason 138 kV Rebuild project. This is a Tier 3 project that is estimated to cost approximately $30 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 7039 | 0 - 436 | 23,851,256 | CREZ |
| Quail - Odessa EHV 345 kV & Longshore - Odessa EHV 345 kV; Golden Switch - Camp Springs Energy Center 138 kV; Lamesa - Willow Valley 138 kV; or Holt - Andrews North 138 kV | China Grove - Bluff Creek 138 kV | 861 | 0 - 3500 | 17,803,622 |  |
| Lewisville - Carrollton Northwest 345 kV | Lewisville - Jones Street Tnp 138 kV | 3020 | 0 - 2870 | 11,572,571 | CREZ, 07TPIT0042 |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 1729 | 0 - 2800 | 9,152,661 | 5YTP [2010-R7, R8] |
| Comanche Peak 1 & 2 | Austrop - Sandow 345 kV | 247 | 0 - 4500 | 5,526,564 |  |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 62 | 0 - 4500 | 5,215,549 | 14TPIT0050 |
| China Grove - Bluff Creek 138 kV | Moss - Amoco North Cowden Tap 138 kV | 370 | 0 - 3500 | 4,431,919 |  |
| Barrilla - Fort Stockton Plant 138 kV | Barrilla - Fort Stockton Switch 69 kV | 4340 | 0 - 1263 | 3,733,738 | CREZ |
| Bluff Creek Auto 345/138 kV Autotransformer 2 | Nicole - Oak Creek 138kV | 2629 | 0 - 132 | 3,254,766 | CREZ |
| Spur - Aspermont 138 kV; Spur - Scurry 138 kV; or Sun - Scurry 138 kV | Spur - Girard 69 kV | 4677 | 0 - 2800 | 3,136,124 | CREZ |

Binding Constraints – April 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Quail - Odessa EHV 345 kV & Longshore - Odessa EHV 345 kV; Golden Switch - Camp Springs Energy Center 138 kV; Lamesa - Willow Valley 138 kV; or Holt - Andrews North 138 kV | China Grove - Bluff Creek 138 kV | 645 | 0 - 3500 | 11,580,993 |  | High west wind and Brand to Golden Switch 138 kV outage |
| Comanche Peak 1 & 2 | Austrop - Sandow 345 kV | 247 | 0 - 4500 | 5,526,564 |  |  |
| China Grove - Bluff Creek 138 kV | Moss - Amoco North Cowden Tap 138 kV | 370 | 0 - 3500 | 4,431,919 |  | High west wind and Brand to Golden Switch 138 kV outage |
| BASE CASE | West to North Stability Limit | 1288 | 0 - 55 | 4,384,669 | CREZ | High west wind |
| North Laredo - Dilley Switch AEP 138 kV | Pleasanton - Big Foot 138 kV | 112 | 17 - 3500 | 2,482,233 | 14TPIT0049, 07TPIT0077 | High load and San Miguel to Pearsall Switching Station 138 kV outage |
| San Angelo Red Creek - Twin Buttes 345 kV | San Angelo Red Creek 345/138 Autotransformer 2 | 63 | 47 - 3500 | 2,108,872 | 14TPIT0067 |  |
| Barrilla - Fort Stockton Plant 138 kV | Barrilla - Fort Stockton Switch 69 kV | 1535 | 0 - 1057 | 1,482,858 | CREZ | High west and McCamey wind |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 221 | 0 - 2275 | 1,402,429 | 5YTP [2010-R7, R8] | High west wind and Brand to Golden Switch 138 kV outage |
| Roanoke - West Denton 345 kV and Roanoke - Lewisville 345 kV | Fort Worth - West Denton 138 kV | 253 | 0 - 732 | 883,077 | 14TPIT0047 | West Denton to Jim Christal 138 kV outage |
| Amoco North Cowden Tap - Moss 138kV | Odessa North - North Cowden 69 kV | 87 | 1548 - 2800 | 866,041 | 14TPIT0009 | High west wind and Brand to Golden Switch 138 kV outage |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The March TPIT update is underway utilizing for the first time the topology from the NMMS Topology Processor (TP) in the Model on Demand (MOD) case building environment.  Pass 1 has been completed and Pass 2 underway.

- Network Operations Model Change Requests (NOMCR’s) were submitted by TSP’s to populate data for new data types recently made available by completion of Bundle 2 of SCR760, which included sub parts 2, 4, and 9 from the table below.  An incremental update to the NMMS Topology Processed base case in MOD was made to insert the data as a Planning Model Change Request (PMCR).

- The short term calendar of major events during Planning Go-Live follows:

  - Feb 27, 2012	ERCOT produces TP case with 7/1/2012 energization date and uses this output as the new base case in MOD.

  - Feb 29, 2012	Planning Go-Live initiated with creation of a MOD base case utilizing the TP case produced two days earlier.

  - Apr 30, 2012	Creation of 13DSA Pass 1 cases

  - May 7, 2012	Creation of 12DSA/DSB Pass 2 cases

  - May 11, 2012	March TPIT case posted on POI.

  - Aug 1, 2012	13DSA cases completed and posted on POI.

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  TP Release received by ERCOT during week of Apr 23rd.  Target June production date.

  - Bundle 4 (Items 1, 6):  ERCOT and TSPs have identified new fields or records added between version 33 and version 30 of the PSS/E RAWD format and are decided which new fields need to be implemented.  The evaluation process for Item 1 has been added to the SSWG Procedure Manual as section 5.3.  Item 1 considered to be in production.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Release |
| SCR760-6 | FACTS Devices | Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The System Protection Working Group 2012 Future Year (FY) case building is underway.  This year, five future year cases instead of four are being built for the first time, for 2013 to 2017.

- The 2011 Five-Year Transmission Plan analysis has been completed and the final report was posted at the ERCOT POI site on April 13, 2012.

- The 2012 Five-Year Transmission Plan study scope was discussed in the last RPG meeting (April 13) and ERCOT is currently reviewing the stakeholder’s comments/feedback received.

- ERCOT System Planning is reviewing and comparing the dynamic model data submitted through the RARF to the DWG dynamic base case. Review results are being provided to Resource Entities for updates and confirmation.

- ERCOT is spot checking governor model performance by comparing the actual measurement with dynamic model response. Review results will be provided to Resource Entities for updates and confirmation.