## Slide 1
RMS Update
December 14, 2011
<number>

## Slide 2
Advanced Meter Settlement Impacts
  April 2012 – ERCOT settling 4.97M ESIIDs using Advanced Meter data
  Settlements as of 4/25/12 – 85.8% of the load in ERCOT is settled using 15-minute interval data (AMS and IDR)
  Commercial Market Operations Report located at:
    http://www.ercot.com/calendar/2012/05/20120515-BOD
        Slide #8>>>>>>>>>>>>>
<number>

## Slide 3
Oncor (approximately):
Installed: 2,607,021 as of 04.30.2012
    Deployment Plan:
      2010 – 929,000 meters – Complete!
      2011 – 902,000 meters – Complete!
      2012 – 902,000 meters
<number>

## Slide 4
CNP (approximately):
Installed: 2,232,776 as of 04.30.2012
  Deployment Plan, includes projected growth:
      2010 – 756,684 meters – Complete!
      2011 – 960,327 meters – Complete!
      2012 – 373,423 meters
<number>
Notes: <number>

## Slide 5
AEP (approximately):
Installed: 520,834 as of 04.30.2012
  Deployment Plan schedule:
      2010 – 188,212 meters – Complete!
      2011 – 251,571 meters – Complete!
      2012 – 279,329 meters
      2013 – 278,280 meters
<number>

## Slide 6
TNMP (approximately):
Installed: 39,732 as of 04.30.2012
    Gulf Coast Complete in Q4 2013
    Lewisville Q1 2014 - Q3 2014
    North Texas Q4 2014 - Q3 2015
    Central Texas Q3 2015 - Q1 2016
    West Texas Q2 2016 - Q3 2016
<number>

## Slide 7
<number>

## Slide 8
During the April 24, 2012 AMIT Steering Committee meeting, the TDSPs provided the following deployment status reports for March 2012:
<number>
Oncor
CNP
AEP
TNMP

## Slide 9
Tuesday, May 22, 2012
Tuesday, June 26, 2012 (reschedule)
July and August- no meetings scheduled
Tuesday, September 18, 2012 (reschedule)
Tuesday, October 23, 2012 (reschedule)
Tuesday, November 27, 2012 (reschedule)
Tuesday, December 11, 2012 (reschedule)
<number>

## Slide 10
AMIT Stakeholder Steering Committee:
  Audio Conference: 1-877-273-4202
  Conference Room: 4856540
  Web Room Link:
    https://www1.gotomeeting.com/register/979713081
The meeting schedule for AMIT has been updated and can be also be accessed online at:
    http://www.puc.state.tx.us/industry/projects/electric/34610/34610.aspx
<number>

## Slide 11
<number>