## Sheet1
Oncor March 2012 Monthly Report to AMIT
1) Number of meters deployed | 2534148
as of | 2012-03-31 | (date)
2) Number of meters provisioned | 2476014
3) % of daily register reads | 99.7%
4) # of HAN devices provisioned | 1769
5) % of service orders performed remotely:
DNP | 96.4% | (month) | 96.2% | (YTD)
RNP | 94.5% |  | 93.9%
Meter Re-Read | 98.1% |  | 98.3%
Switch | 99.9% |  | 99.9%
Move-In | 98.9% |  | 98.8%
Move-Out | 97.3% |  | 97.3%
Other | 0% |  | 0%
Total | 97.1% |  | 96.8%
6) Number of service orders performed remotely:
DNP | 61243 | (month) | 192028 | (YTD)
RNP | 51281 |  | 158531
Meter Re-Read | 636 |  | 5800
Switch | 16072 |  | 51733
Move-In | 78303 |  | 219007
Move-Out | 18614 |  | 53262
Other | 0 |  | 0
Total | 226149 |  | 680361
7) Number of meters replaced | 2936 | (month) | 3204 | (YTD)
8) AMS Upgrades
- TDU Back office upgrade? | HE-yes |  | description
(head- end, DCE, MDM, CIS, etc.) | MDM- yes
- Meter Upgrade? |  |  | description
software | yes - AMS |  | description
firmware | yes |  | description
- Cell Relay or Data Collector upgrade? | yes |  | description
Oncor has upgaded the software on our Head End and MDMS.
We have upgraded the firmware in our AMS meters and Data Collectors
9) Meter Hardware Standardization
- list # of different types of Hardware in the field, and state when upgrade will be performed so that there is just one version
Focus AXR meter
Focus AXR SD meter
Focus S4E RXR meter
These different meter types are necessary to serve different types
of loads (e.g. small residential, large residential, small commercial)
10) Meter Firmware Standardization
- list # of different types of Hardware in the field, and state when upgrade will be performed so that there is just one version
There are 2 firmware versions - 1 for the Focus AXR and AXR SD meters
and 1 for the Focus S4E RXR meters
We are currently striving to upgrade a common firmware version to all meters.
11) Any education updates | See Oncor's monthly report filed in PUC Docket No. 36157
12) Any other deployment updates | None

## Sheet4
9021 | T
9020 | T
9019 | T
9018 | T
9017 | T
9016 | T
9015 | T
9014 | T
9013 | T
9012 | T
9011 | T
9010 | T
9009 | T
9008 | T
9007 | T
9006 | T
9005 | T
9004 | T
9003 | T
9002 | T
9001 | T
9000 | T
8999 | T
8998 | T
8997 | T
8996 | T
8995 | T
8994 | T
8993 | T
8992 | T
8991 | T
8990 | T
8989 | T
8988 | T
8987 | T
8986 | T
8985 | T
8984 | T
8983 | T
8982 | T
8981 | T
8980 | T
8979 | T
8978 | T
8977 | T
8976 | T
8975 | T
8974 | T
8973 | T
8972 | T
8971 | T
8970 | T
8969 | T
8968 | T
8967 | T
8966 | T
8965 | T
8964 | T
8963 | T
8962 | T
8961 | T
8960 | T
8959 | T
8958 | T
8957 | T
8956 | T
8955 | T
8954 | T
8953 | T
8952 | T
8951 | T
8950 | T
8949 | T
8948 | T
8947 | T
8946 | T
8945 | T
8944 | T
8943 | T
8942 | T
8941 | T
8940 | T
8939 | T
8938 | T
8937 | T
8936 | T
8935 | T
8934 | T
8933 | T
8932 | T
8931 | T
8930 | T
8929 | T
8928 | T
8927 | T
8926 | T
8925 | T
8924 | T
8923 | T
8922 | T
8921 | T
8920 | T
8919 | T
8918 | T
8917 | T
8916 | T
8915 | T
8914 | T
8913 | T
8912 | T
8911 | T
8910 | T
8909 | T
8908 | T
8907 | T
8906 | T
8905 | T
8904 | T
8903 | T
8902 | T
8901 | T
8900 | T
8899 | T
8898 | T
8897 | T
8896 | T
8895 | T
8894 | T
8893 | T
8892 | T
8891 | T
8890 | T
8889 | T
8888 | T
8887 | T
8886 | F