| PGRR Number | 015 | PGRR Title | New Section 3, Regional Planning |  |
| --- | --- | --- | --- | --- |
| Timeline | Normal | Action |  | Approved |
| Date of Decision |  | May 15, 2012 |  |  |
| Effective Date |  | June 1, 2012 |  |  |
| Priority and Rank Assigned |  | Not applicable |  |  |
| Planning Guide Sections Requiring Revision |  | 2.2, Acronyms and Abbreviations 3, Regional Planning (new) 3.1, Communications (new) 3.1.1, Overview of Major Transmission Planning Activities (new) 3.1.1.1, Long-Term System Assessment (new) 3.1.1.2, Five-Year Transmission Plan (new) 3.1.1.3, Regional Planning Group Project Reviews (new) 3.1.1.4, Generation Interconnection Process (new) 3.1.2, Regional Planning Group Project Submission (new) 3.1.2.1, All Projects (new) 3.1.2.2, Projects That Are Not Included in the Current Five-Year Transmission Plan (new) 3.1.2.3, Other Information (new) 3.1.3, Project Evaluation (new) 3.1.3.1, Definitions of Reliability-Driven and Economic-Driven Projects (new) 3.1.3.2, Reliability-Driven Project Evaluation (new) 3.1.4, Five-Year Transmission Plan Development Process (new) 3.1.4.1, Development of Five-year Transmission Plan (new) 3.1.4.2, Use of Five-year Transmission Plan (new) 3.1.5, Regional Planning Group Comment Process (new) 3.1.6, Notify PUCT of Recommended Transmission Projects (new) |  |  |
| Protocol Section(s) Requiring Revision |  | None. |  |  |
| Revision Description |  | This Planning Guide Revision Request (PGRR) adds certain provisions of the Regional Planning Group Charter and Procedures (RPG Charter), approved by the ERCOT Board in January 2009, to the Planning Guide without changing requirements or process. |  |  |
| Reason for Revision |  | With the creation of the Planning Guide, it is intended that the RPG Charter, as well as several other documents and procedures, will no longer independently exist. |  |  |
| Procedural History |  | - On 12/2/11, PGRR015 was posted. - On 12/12/11, ERCOT comments were posted. - On 1/26/12, the Planning Working Group (PLWG) considered PGRR015. - On 2/10/12, an Impact Analysis was posted. - On 2/29/12, PLWG considered the 1/26/12 PLWG Report and Impact Analysis for PGRR015. - On 3/5/12, a second set of ERCOT comments were posted. - On 3/8/12, ROS considered PGRR015. - On 4/5/12, TAC considered PGRR015. - On 5/15/12, the ERCOT Board considered PGRR015. |  |  |
| PLWG Decision |  | On 1/26/12, PLWG was in consensus to recommend approval of PGRR015 as amended by the 12/12/11 ERCOT comments and as revised by PLWG. On 2/29/12, PLWG was in consensus to endorse and forward the 1/26/12 PLWG Report and Impact Analysis for PGRR015 to ROS. |  |  |
| Summary of PLWG Discussion |  | On 1/26/12, the 12/12/11 ERCOT comments were discussed. ERCOT Staff stated that a PGRR will be submitted to clarify when Generation Resources will be added to the planning models. It was requested that the flowchart illustrating the process used for assigning Tiers to proposed transmission projects be posted to the ERCOT website. On 2/29/12, there was no discussion. |  |  |
| ROS Decision |  | On 3/8/12, ROS unanimously voted to recommend approval of PGRR015 as recommended by PLWG in the 2/29/12 PLWG Report and as amended by the 3/5/12 ERCOT comments. All Market Segments were present for the vote. |  |  |
| Summary of ROS Discussion |  | On 3/8/12, there was no discussion. |  |  |
| TAC Decision |  | On 4/5/12, TAC unanimously voted to recommend approval of PGRR015 as recommended by ROS in the 3/8/12 ROS Report. All Market Segments were present for the vote. |  |  |
| Summary of TAC Discussion |  | On 4/5/12, there was no discussion. |  |  |
| Board Decision |  | On 5/15/12, the ERCOT Board approved PGRR015 as recommended by TAC in the 4/5/12 TAC Report. |  |  |

Business Case

| Business Case | 1 | Benefits: - Allows the established PGRR process to be used for any revision of these certain provisions related to the planning process. |
| --- | --- | --- |
|  | 2 | Impacts to Market Segments: - None. The provisions exist within the RPG Charter and have not been substantively changed. |

| Sponsor |  |
| --- | --- |
| Name | Rob Lane on behalf of PLWG |
| E-mail Address | Robert.Lane@luminant.com |
| Company | Luminant Energy Company LLC |
| Phone Number | (214) 875-8063 |
| Cell Number |  |
| Market Segment | Investor Owned Utility (IOU) |

| Market Rules Staff Contact |  |
| --- | --- |
| Name | Yvette M. Landin |
| E-Mail Address | ylandin@ercot.com |
| Phone Number | (512) 248-4513 |

| Comments Received |  |
| --- | --- |
| Comment Author | Comment Summary |
| ERCOT 121211 | Inserted paragraph (4) in Section 3.1.4.2, which was inadvertently omitted from PGRR015. |
| ERCOT 030512 | Proposed non-substantive administrative changes to PGRR015. |

Comments

Although the normal process is to introduce new language as redline, PLWG agreed that since the language currently exists in the RPG Charter, only proposed changes will be shown as redline.

Revised Proposed Guide Language

- 2.2	ACRONYMS AND ABBREVIATIONS

LTSA		Long-Term System Assessment

ERCOT Planning Guide

Section 3:  Regional Planning

# 3	Regional Planning

3.1	Communications

3.1.1		Overview of Major Transmission Planning Activities

The process of planning a reliable and efficient transmission system for the ERCOT Region is composed of several types of activities and studies.

3.1.1.1	Long-Term System Assessment

The Long-Term System Assessment (LTSA) is performed by ERCOT in coordination with the Regional Planning Group (RPG) on a biennial basis (in even-numbered years) and reviewed annually.  The study uses scenario analysis techniques to assess the potential needs of the ERCOT System up to 20 years into the future.  The role of the LTSA is not to recommend the construction of specific system upgrades, due to the high degree of uncertainty associated with the amount and location of loads and Resources in this timeframe.  Instead, the role of the LTSA is to evaluate the system upgrades that are indicated under each of a wide variety of scenarios in order to identify upgrades that are robust across a range of scenarios or might be more economic than the upgrades that would be determined considering only near-term needs in the Five-Year Transmission Plan development.

3.1.1.2	Five-Year Transmission Plan

The Five-Year Transmission Plan is developed annually by ERCOT, in coordination with the RPG and Transmission Service Providers (TSPs).  The Five-Year Transmission Plan addresses region-wide reliability and economic transmission needs and the planned improvements to meet those needs for the upcoming five years.  These planned improvements include projects previously approved by the ERCOT Board, projects previously reviewed by the RPG, new projects that will be refined at the appropriate time by TSPs in order to complete RPG review, and the local projects currently planned by TSPs.  Combined, these projects represent ERCOT’s plan addressing the reliability and efficiency of the ERCOT System to meet North American Electric Reliability Corporation (NERC) Reliability Standards, the Protocols, Operating Guides and this Planning Guide.  Projects that are included in the Five-Year Transmission Plan are not considered to have been endorsed by ERCOT until they have undergone the appropriate level of RPG Project Review as outlined in Protocol Section 3.11.4, Regional Planning Group Project Review Process, if required.

3.1.1.3	Regional Planning Group Project Reviews

Except for minor transmission projects that have only localized impacts and projects that are directly associated with the interconnection of new Generation Resources, all transmission projects in the ERCOT Region undergo a formal review by the RPG in accordance with Protocol Section 3.11.4.  In addition, ERCOT performs an independent analysis of the need for major transmission projects that are submitted for RPG Project Review.  The affirmative result of this review is formal endorsement of the project by ERCOT.   This ERCOT project endorsement is intended to support, to the extent applicable, a finding by the Public Utility Commission of Texas (PUCT) that a project is necessary for the service, accommodation, convenience, or safety of the public within the meaning of Public Utility Regulatory Act, Tex. Util. Code Ann. § 37.056 and P.U.C. Subst. R. 25.101, Certification Criteria.

3.1.1.4	Generation Interconnection Process

This process facilitates the interconnection of new generation units in the ERCOT Region by assessing the transmission upgrades necessary for new generating units to operate reliably.  The process to study interconnecting new generation or modifying an existing generation interconnection to the ERCOT Transmission Grid is covered in Section 4, Transmission Planning Criteria.  The generation interconnection study process primarily covers the direct connection of generation Facilities to the ERCOT Transmission Grid and directly-related projects.  Additional upgrades to the ERCOT Transmission Grid that might be cost-effective as a result of new or modified generation may be initiated by any stakeholder through the RPG Project Review procedure described in Protocol Section 3.11.4, Regional Planning Group Project Review Process, at the appropriate time, subject to the confidentiality provisions in Section 5, Generation Resource Interconnection or Change Request.

3.1.2	Regional Planning Group Project Submission

Transmission projects that are proposed for RPG Review, pursuant to Protocol Section 3.11.4.1, Project Submission, shall be submitted according to the provisions outlined in Section 3.1.2.1, All Projects, through 3.1.2.3, Other Information.

3.1.2.1	All Projects

The submittal of each transmission project (60 kV and above) for RPG Project Review should include the following elements:

(a)	The proposed project description including expected cost, feasible alternative(s) considered, transmission topology and Transmission Facility modeling parameter data, and all study cases used to generate results supporting the need for the project in electronic format (powerflow data should be in PTI PSS/E RAWD format).  Also, the submission should include accurate maps and one-line diagrams showing locations of the proposed  project and feasible alternatives (AutoCad-compatible format preferred);

(b)	Identification of the Steady State Working Group (SSWG) or Five-Year Transmission Plan powerflow cases used as a basis for the study and any associated changes that describe and allow accurate modeling of the proposed project;

(c)	Description and data for all changes made to the SSWG or Five-Year Transmission Plan cases used to identify the need for the project, such as Generation Resource unavailability and area peak Load forecast;

(d)	A description of the reliability and/or economic problem that is being solved;

(e)	Desired/needed in-service date for the project, and feasible in-service date, if different; and

(f)	The phone number and email address of the single point of contact who can respond to ERCOT and RPG participant questions or requests for additional information necessary for stakeholder review.

3.1.2.2		Projects That Are Not Included in the Current Five-Year Transmission Plan

(1)	For projects that are not included in the current Five-Year Transmission Plan, the following elements should be included in the submission.  While it is not necessary, if any of these additional elements are available for projects that are included in the Five-Year Transmission Plan, they should be included in the submittal of these projects as well.

(a)	Analysis of rejected alternatives, including cost estimates, effect upon transfer capability, and other factors considered in the comparison of alternatives with the proposed project;

(b)	Assumptions modeled in performance studies such that credible performance deficiencies can be identified through study;

(c)	Results of performance analyses that are consistent with system operating practices and procedures; and

(d)	Documentation of the process used to identify specific performance deficiencies (reliability and economic).

(2)

Both transmission and non-transmission solutions to performance deficiencies may be considered where applicable.

3.1.2.3		Other Information

If there is any other information, not included above, that the submitter believes is relevant to consideration of the need for any submitted project, they should include that information in the project submission.

3.1.3		Project Evaluation

(1)	Proposed transmission projects will be evaluated using a variety of tools and techniques to ensure that the system is able to meet applicable reliability criteria in a cost-effective manner.  For most proposed projects, several alternatives will be identified to meet the reliability criteria or other performance improvement objectives that the proposed project is designed to meet.  The project alternative with the expected lowest cost over the life of the project is generally recommended, subject to consideration of the expected long-term system needs in the area (as identified in the LTSA), and consideration of the relative operational impacts of the alternatives.

(2)	In some cases, one alternative may be to dispatch the system in such a way that all reliability requirements are met, even without the proposed project or any transmission alternative, resulting in a less efficient dispatch than what would be required to meet the reliability requirements if the proposed project was in place.  Consideration of the merits of this alternative relative to the proposed transmission project is more complex.  To facilitate the discussion and consideration of these alternatives, ERCOT has adopted certain definitions and practices, described in paragraph (4) of Protocol Section 3.11.2, Planning Criteria, and Sections 3.1.3.1, Definitions of Reliability-Driven and Economic-Driven Projects, and 3.1.3.2, Reliability-Driven Project Evaluation below.

3.1.3.1	Definitions of Reliability-Driven and Economic-Driven Projects

(1)	Proposed transmission projects are categorized for evaluation purposes into two types:

(a)	Reliability-driven projects; and

(b)	Economic-driven projects.

(2)	The differentiation between these two types of projects is based on whether a simultaneously-feasible, security-constrained generating unit commitment and Dispatch is expected to be available for all hours of the planning horizon that can resolve the system reliability issue that the proposed project is intended to resolve.  If it is not possible to forecast a dispatch of the generating units such that all reliability criteria are met without the project, and the addition of the project allows the reliability criteria to be met, then the project is classified as a reliability-driven project.  If it is possible to simulate a dispatch of the generating units in such a way that all reliability criteria are met without the project, but the project may allow the reliability criteria to be met at a lower total cost, then the project is classified as an economic-driven project.

3.1.3.2

- Reliability-Driven Project Evaluation

For reliability-driven projects, the comparison of project costs generally includes only the relative capital costs of the alternatives.  In the case of Tier 1 and 2 projects, any differences in expected ERCOT System production costs between the alternatives may be included in the consideration of the relative costs of the alternatives, due to larger potential impacts on losses and congestion of these projects.

3.1.4		Five-Year Transmission Plan Development Process

The purpose of the Five-Year Transmission Plan is to provide a coordinated plan for the ERCOT System, in which all planned improvements to the system are documented, and which includes projects that have achieved a level of review that is commensurate with the impact of the projects.  The Five-Year Transmission Plan is updated on an annual basis.  While unanticipated changes in Load and generation may require additional projects to be needed that were not included in the current Five-Year Transmission Plan, or require additional evaluation of projects included in the current Five-Year Transmission Plan when they are submitted for RPG Project Review, the Five-Year Transmission Plan provides a reasonable and supportable basis for analyses of the planned ERCOT Transmission Grid.

3.1.4.1		Development of Five-Year Transmission Plan

(1)	The starting case for the Five-Year Transmission Plan development is created by removing all Tier 1, 2 and 3 projects that have not undergone RPG Project Review from the most recent SSWG summer peak base cases for each year of the planning horizon.  The planning process begins with computer modeling studies of the generation and Transmission Facilities and substation Loads under normal conditions in the ERCOT System.  Contingency conditions along with changes in Load and generation that might be expected to occur in operation of the ERCOT Transmission Grid are also modeled.  To maintain adequate service and minimize interruptions during Outages, model simulations are used to identify adverse results based upon the planning criteria and to examine the effectiveness of various problem-solving alternatives.

(2)	The effectiveness of each alternative will be evaluated under a variety of possible operating environments because Loads and operating conditions cannot be predicted with certainty.  As a result, repeated simulations under different conditions are often required.  In addition, options considered for future installation may affect other alternatives so that several different combinations must be evaluated, thereby multiplying the number of simulations required.

(3)	Once feasible alternatives have been identified, the process is continued with a comparison of those alternatives.  To determine the most favorable, the short-range and long-range benefits of each must be considered including operating flexibility and compatibility with future plans.

3.1.4.2		Use of Five-Year Transmission Plan

(1)	The Five-Year Transmission Plan will generally serve as the basis for all subsequent RPG Project Reviews, both of projects included within the Five-Year Transmission Plan and of other proposed projects.  Stakeholders are encouraged to submit, at the start of the Five-Year Transmission Plan development process, any known transmission projects that are not in the current SSWG base cases and are likely to be submitted within the next year, as work on RPG Project Reviews will be limited while the Five-Year Transmission Plan is being developed and documented.  Projects submitted for RPG Project Review after the Five-Year Transmission Plan development has begun and which need ERCOT Independent Review may be delayed.  Inputs to the Five-Year Transmission Plan, such as new Generation Resources and updated local transmission projects, may be updated at the time these subsequent studies are performed if ERCOT or stakeholders identify such updates as being needed to appropriately consider the need for the specific project under review.  If the project under review is included in the Five-Year Transmission Plan, and no changes are identified which would affect the need for the proposed project through the 21-Day Comment Period described in Section 3.1.5, Regional Planning Group Comment Process, then the Five-Year Transmission Plan will serve as the ERCOT Independent Review of the proposed project, if required.

(2)	Tier 1, 2, and 3 projects that are included in the Five-Year Transmission Plan should be submitted for RPG Project Review at an appropriate lead time.  Generally, this lead time should be sufficient to allow the review to be completed before the TSP reaches the decision point at which it must initiate the engineering and procurement in order to meet the required in-service date, but not farther in advance than is necessary.  In general, these lead times will be three to four months for Tier 3 projects and six to seven months for Tier 1 and 2 projects.

(3)	Tier 1, 2 and 3 projects that are included in the Five-Year Transmission Plan but do not reach this decision point before the development of the next year’s Five-Year Transmission Plan begins will be removed from the case used to develop the Five-Year Transmission Plan and will be re-evaluated as a part of the development of this subsequent Five-Year Transmission Plan.

(4)	Once ERCOT receives a signed Standard Generation Interconnection Agreement (SGIA) or public, financially-binding agreement between the Generation Resource and the TSP under which Generation Resources would be constructed or a letter from a duly authorized official from the Municipally Owned Utility (MOU) or Electric Cooperative (EC) building a Generation Resource, the project will be included in the base cases beyond its expected in-service year in the development of the Five-Year Transmission Plan and RPG Project Reviews.

- 3.1.5	Regional Planning Group Comment Process

Any stakeholder may initiate an RPG project as accordance with Protocol Section 3.11.4.1, Project Submission.  The RPG Project Review procedure is designed to review projects in a manner commensurate with the cost and impact to the market and to system reliability of the project, based on the Tier into which the project is grouped.   The RPG Project Review procedure for submitted projects in all Tiers consists of the following steps.

(a)	ERCOT will provide electronic copies of RPG Project Review submittals to the RPG within seven days of receipt and solicit comments or questions from the RPG;

(b)	All concerns/questions or objections about the submitted project by any stakeholder or ERCOT should be submitted to the RPG within 21 days after ERCOT’s transmittal to the RPG;

(c)	Each Entity  providing comments should provide a “single” complete comment about each project by the end of the 21-day review period rather than sending multiple comments at various times or from various individuals.  A single comment will help

ERCOT and the project submitter keep track of the comments and develop an appropriate response;

(d)	Any questions related to data deficiency should be submitted to ERCOT and the submitter immediately;

(e)	If concerns or objections about a project are received, the project will be put into “study mode” until all concerns are resolved or until ERCOT assesses that a reasonable effort has been made to resolve all concerns, generally no more than an additional 28 days;

(f)	Project submitters should answer all questions and respond to all concerns in a timely manner;

(g)	Comments should be based on Good Utility Practice and sound engineering judgment. Suggestions should be able to be implemented by the TSP constructing and operating the project; and

(h)	ERCOT will post all project submissions, the comments received, and other information and databases associated with submitted transmission projects on its website.

3.1.6	Notify PUCT of Recommended Transmission Projects

ERCOT will notify the PUCT of the disposition of all Tier 1 or 2 projects and of the designated TSPs for those projects.  ERCOT will then support ERCOT-endorsed projects in future Certificate of Convenience and Necessity (CCN) proceedings required for those projects through the use of filed supporting documents and testimony if necessary.