## Slide 1
Business Integration Update to PRS
May 17, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets
    Project Spending Update
  ERCOT FTE Tracking p. 7
  Appendix
    Project Portfolio Gantt Chart p. 9-15
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in May (no integrated software release)
  Quality Training Database
Go-Lives in June
  NPRR294 – Texas SET 4.0
    Also includes NPRR403 and RMGRR100
  NPRR351 – Look-Ahead SCED Phase 1
  NPRR354 – Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment
    EMS portion
  NPRR360 – Summary Report of HDL and LDL
  NPRR379 – EILS Dispatch Sequence and Performance Criteria Upgrades
  NPRR437 – Aggregation of Multiple Generators Into a Single Resource for Mkt and Eng Modeling
  SCR756 – MarkeTrak Enhancements for Texas SET 4.0
    Portions of SCR756 needed for Texas SET 4.0 implementation
  SCR760 – Recommended Changes Needed for Information Model Mgr and Topology Processor
    Deliverable #5 (Additional Transformer Data for Planning)
  RARF Upgrade for Wind, Solar, and Storage Resources
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR365 NPRR382 NPRR383 NPRR422 NPRR348 NPRR354(b) | NPRR207 NPRR313 NPRR322 NPRR397 | NPRR222 NPRR260 NPRR272 NPRR377 NPRR419 SCR756(b) SCR768 | 
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) |  | NPRR357 | NPRR347 NPRR400 | 
Counts Total = 40 | 5 | 5 | 10 | 6 | 5 | 9 | 0
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change
November
None
None
Early June
None
Early Oct

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2013 TBD
On-Cycle |  | SCR760(d) | NPRR327 NPRR393 SCR769 | NPRR407 |  |  | 
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 5 |  | 1 | 3 | 1 |  |  | 
Note 1: Underline indicates new/revised release targets
Note 2: (a), (b), etc. indicates multiple release phases
Note 3: Release targets are subject to change – Please watch for market notices as effective dates approach
None
None
None
None
None
None
Note 4: Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details

## Slide 6: Project Spending Update – 4/30/2012
PPL – 2012 | Portfolio Budget | Initial Target Funding | Current Forecast | 2012 YTD Actual
Business Strategy |  | $ 5,950,000 | $ 7,488,202 | $ 1,924,864
Regulatory |  | $ 1,600,000 | $ 947,197 | $ 302,260
Efficiencies/Enhancements |  | $ 2,050,000 | $ 2,863,982 | $ 720,287
Technical Foundation |  | $ 6,500,000 | $ 8,759,683 | $ 2,163,694
Totals | $ 15,000,000 | $ 16,100,000 | $ 20,059,064 | $ 5,111,105
ERCOT Public

## Slide 7: ERCOT FTE (Full Time Equivalent) Tracking
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NPRR393 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Board approved - 2/21/2012
NPRR421 | Operations | Operations Analysis | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
 | Operations | Wholesale Client Svs | 0.25 | 0 | $0 | 
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 9.05 | 5 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
 | In-Flight at TAC |  | 0.00 | 0 |  | 
 | Total of All Items |  | 9.05 | 5 |  | 

## Slide 8: Business Integration Update – Appendix
  Appendix
    5/11/2012 Project Gantt
      Sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 5/11/2012

## Slide 10
Project Portfolio Status – as of 5/11/2012

## Slide 11
Project Portfolio Status – as of 5/11/2012

## Slide 12
Project Portfolio Status – as of 5/11/2012

## Slide 13
Project Portfolio Status – as of 5/11/2012

## Slide 14
Project Portfolio Status – as of 5/11/2012

## Slide 15
Project Portfolio Status – as of 5/11/2012