## Slide 1
Business Integration Update to PRS
June 21, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets
    Project Spending Update
  Project Prioritization Discussion p. 7-8
  Appendix
    Project Portfolio Gantt Chart p. 10-16
    ERCOT FTE Tracking p. 17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in June
  NPRR294 – Texas SET 4.0
    Also includes NPRR403 and RMGRR100
  NPRR351 – Look-Ahead SCED Phase 1
  NPRR354 – Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment
    EMS portion
  NPRR360 – Summary Report of HDL and LDL
  NPRR379 – EILS Dispatch Sequence and Performance Criteria Upgrades
  NPRR437 – Aggregation of Multiple Generators Into a Single Resource for Mkt and Eng Modeling
  SCR756 – MarkeTrak Enhancements for Texas SET 4.0
    Portions of SCR756 needed for Texas SET 4.0 implementation
  SCR760 – Recommended Changes Needed for Information Model Mgr and Topology Processor
    Deliverable #5 (Additional Transformer Data for Planning)
  RARF Upgrade for Wind, Solar, and Storage Resources
Go-Lives in July (no integrated software release)
  None
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 | NPRR207 NPRR313 NPRR322 NPRR365 NPRR397 | NPRR222 NPRR260 NPRR272 NPRR377 NPRR419 SCR756(b) SCR768 | 
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) |  | NPRR357/ NPRR430 | NPRR347 NPRR391 NPRR400 | 
Counts Total = 43 | 5 | 5 | 10 | 6 | 7 | 10 | 0
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change
November
None
Early June
None
Early Oct
None

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2013 TBD
On-Cycle |  | NPRR439 SCR760(d) | NPRR327 NPRR393 SCR769 SCR771 | NPRR407 SCR770 | NOGRR084 |  | 
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 9 | 0 | 2 | 4 | 2 | 1 | 0 | 0
Note 1: Underline indicates new/revised release targets
Note 2: (a), (b), etc. indicates multiple release phases
Note 3: Release targets are subject to change – Please watch for market notices as effective dates approach
None
None
None
None
None
None
Note 4: Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details

## Slide 6: Project Spending Update
PPL – 2012 | Portfolio Budget (effective 1/1/2012) | 2012 Spending Projection of In-Flight Projects (as of 5/31/2012) | Current 2012 Demand (as of 5/31/2012) | 2012 YTD Actual (as of 5/31/2012)
Business Strategy |  | $ 4,939,381 | $ 7,253,611 | $ 2,449,157
Regulatory |  | $ 860,835 | $ 933,792 | $ 397,127
Efficiencies/Enhancements |  | $ 2,490,729 | $ 2,813,022 | $ 952,543
Technical Foundation |  | $ 5,958,434 | $ 7,490,748 | $ 2,481,466
Totals | $ 15,000,000 | $ 14,249,379 | $ 18,491,173 | $ 6,280,293
ERCOT Public

## Slide 7: PPL Prioritization Discussion
At the May PRS meeting, a recommendation was made to hold a review of upcoming revision request project efforts in order to get stakeholder input on the priority of various items in the project queue
  ERCOT plans to hold similar reviews every 3 to 6 months
  The conclusion of several large projects in June makes the timing of this review appropriate
Today’s discussion will center on the timing of 30 upcoming efforts
  18 NPRRs, SCRs and NOGRRs that are Board-approved with projects that have not yet started
  7 NPRRs, SCRs and NOGRRs that require additional analysis before seeking final Board approval
    These are the remaining Parking Deck items
  4 NPRRs and SCRs that were initiated by ERCOT on June 13, 2012
  1 NPRR that was removed by a subsequent NPRR
ERCOT will present an initial recommendation for all 30 items and request stakeholder input on the proposed schedule of activities and next steps

## Slide 8: Business Integration Update – Appendix
  Appendix
    6/8/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date
    ERCOT FTE Tracking

## Slide 9
Project Portfolio Status – as of 6/8/2012

## Slide 10
Project Portfolio Status – as of 6/8/2012

## Slide 11
Project Portfolio Status – as of 6/8/2012

## Slide 12
Project Portfolio Status – as of 6/8/2012

## Slide 13
Project Portfolio Status – as of 6/8/2012

## Slide 14
Project Portfolio Status – as of 6/8/2012

## Slide 15
Project Portfolio Status – as of 6/8/2012

## Slide 16: ERCOT FTE (Full Time Equivalent) Tracking
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
Summary of FTE Impact of Revision Requests By Department |  |  |  |  |  | 
--- Board Approved --- |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact |  | 
Revision Request | Division | Department Name | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact | Status / Comments
SCR760 | Operations | Network Modeling | 2.20 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR286 | Corporate | Credit | 0.50 | 0 | $0 | Absorbed in 2012 budget and staffing plan
NPRR327 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR365 | Operations | Outage Coordination | 2.00 | 2 | $240k-$260k | Board approved - 9/20/2011
NPRR393 | Operations | Operations Support | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
NPRR408 | Operations | Resource Integration | 0.10 | 0 | $0 | Board approved - 2/21/2012
NPRR421 | Operations | Operations Analysis | 1.00 | 1 | $120k-$130k | Board approved - 4/17/2012
 | Operations | Wholesale Client Svs | 0.25 | 0 | $0 | 
NOGRR054 | Compliance | Compliance | 1.00 | 0 | $0 | Absorbed in 2012 budget and staffing plan
 | Board-Approved Items |  | 9.05 | 5 |  | 
--- In-Flight at Board/TAC --- |  |  |  |  |  | 
 | In-Flight at TAC |  | 0.00 | 0 |  | 
 | Total of All Items |  | 9.05 | 5 |  |