|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report June 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 131 active generation interconnection requests totaling over 35,000 MW. This includes over 19,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $95.6 Million - Transmission Projects endorsed in 2012 total $446.7 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.77 Billion - Transmission Projects energized in 2012 total about $208.4 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0021 – Ferguson Replacement Project – 570 MW Natural Gas in Llano County

12INR0076 – NoTrees Battery Storage – 36 MW Storage in Winkler County

## New Generation Registering for Commercial Operations

Non-modeled – Somerset North – 5.6 Solar in Bexar County

Non-modeled – Somerset South – 4.9 Solar in Bexar County

The total installed wind capacity is now reported as 10,035 MW by the resource owners through the registration process. Capacity by North, South and West is 519 MW,  2,283 MW, and 7,233 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 172 generation interconnection or change requests |  |  |  |  |
| As of June 30, 2012 | North | South | West | Total |
| Security Screening Study | 0 | 5 | 1 | 6 |
| SSS Completed | 2 | 4 | 6 | 12 |
| Full Interconnect Study | 8 | 19 | 47 | 74 |
| FIS Completed | 2 | 5 | 9 | 16 |
| Suspended Studies | 8 | 3 | 30 | 41 |
| Capacity of Suspended Study Projects | 6,486 | 638 | 11,348 | 18,472 |
| Interconnect Agreement Completed | 8 | 9 | 6 | 23 |
| Capacity under Interconnection Agreements | 5,764 | 4,134 | 1,134 | 10,426 |
| Capacity for Grid, MW | 9,351 | 10,288 | 15,398 | 35,037 |
| Wind Capacity, MW | 3,443 | 3,092 | 12,966 | 19,501 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 1,862 |
| Gas-CombinedCycle |  |  | 6,019 | 2,890 | 10,537 |
| Total Gas | 1,390 | 2,100 | 6,019 | 2,890 | 12,399 |
| Nuclear |  |  |  | 3,200 | 3,200 |
| Coal |  | 1,090 | 2,785 |  | 3,875 |
| Wind | 2,070 | 15,039 | 2,392 | 11,979 | 31,480 |
| Solar | 270 | 506 | 60 | 353 | 1,189 |
| Biomass |  |  |  | 50 | 50 |
| Storage |  | 40 | 36 |  | 76 |
| Petroleum Coke |  |  | 1,240 |  | 1,240 |
| Grand Total | 3,730 | 18,775 | 12,532 | 18,472 | 53,509 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

(Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of June 30, 2012 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 12INR0076 | Notrees Battery Storage | IA | Winkler | West | Oct-12 |  | Storage |  | 36 | New |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-12 |  | Solar |  | 60 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-12 |  | Wind |  | 150 |  |
| 12INR0075 | Blue Summit Windfarm | IA | Wilbarger | West | Nov-12 |  | Wind |  | 170 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 |  | Wind |  | 100 |  |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 |  | Wind |  | 92 |  |
| 10INR0023 | Baker Ranch | IA | Haskell | West | Dec-12 |  | Wind |  | 400 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 |  | Wind |  | 50 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 |  | Coal |  | 925 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 12INR0034 | Stephens-Borlynn Wind Project | IA | Borden | West | Dec-13 |  | Wind |  | 378 |  |
| 13INR0021 | Ferguson Replacement Project | IA | Llano | North | Jul-14 |  | Gas-CC |  | 570 | New |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 |  | Wind |  | 120 |  |
| 10INR0021 | Panda Sherman Power | IA | Grayson | North | Jan-15 |  | Gas-CC |  | 717 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-15 |  | Gas-CC |  | 1,792 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-15 |  | Gas-CC |  | 780 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-16 |  | Gas-CC |  | 780 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-16 |  | Gas-CC |  | 1,380 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-17 |  | Coal |  | 660 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | May-18 |  | PetCoke |  | 620 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | May-18 |  | PetCoke |  | 620 |  |
|  |  |  |  |  |  |  | TOTAL |  | 11,032 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0080 | Blanco Canyon Wind | PL | Floyd | West | Dec-12 | Wind | 300 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 | Coal | 1,200 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10INR0062a | Pecos | 80 | TBD | Wind |  | 11INR0094 | Kent | 100 | TBD | Solar |
| 12INR0086 | Harris | 89 | TBD | Gas |  | 12INR0053 | Crockett | 615 | TBD | Wind |
| 12INR0050 | King | 332 | TBD | Wind |  | 12INR0079 | Kenedy | 200 | Aug-12 | Wind |
| 12INR0089 | Pecos | 230 | Nov-12 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-12 | Wind |
| 12INR0059 | Pecos | 50 | Dec-12 | Solar |  | 12INR0067 | Webb | 94 | Dec-12 | Wind |
| 12INR0055 | Baylor | 80 | Dec-12 | Wind |  | 11INR0093 | San Patricio | 41 | Dec-12 | Wind |
| 12INR0060 | Schleicher | 58 | Dec-12 | Wind |  | 12INR0080 | Floyd | 300 | Dec-12 | Wind |
| 12INR0068 | Jim Hogg | 80 | Dec-12 | Wind |  | 12INR0081 | Upton | 113 | Dec-12 | Wind |
| 13INR0040 | Harris | 0 | Jan-13 | Gas |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 11INR0050 | Crosby | 149 | Mar-13 | Wind |  | 09INR0051 | Borden | 249 | Mar-13 | Wind |
| 13INR0045 | Castro | 288 | Apr-13 | Wind |  | 12INR0070 | Knox | 300 | Apr-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0089 | Harris | 40 | May-13 | Storage |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 13INR0032 | Andrews | 30 | Jun-13 | Solar |  | 13INR0057 | Archer | 65 | Jun-13 | Wind |
| 13INR0023 | Ector | 240 | Jul-13 | Coal |  | 13INR0049 | Harris | 352 | Jul-13 | Gas |
| 13INR0046 | Limestone | 71 | Sep-13 | Wind |  | 11INR0082A | Val Verde | 50 | Sep-13 | Wind |
| 11INR0083A | Crockett | 50 | Sep-13 | Wind |  | 13INR0025 | Randall | 150 | Sep-13 | Wind |
| 11INR0013 | Mills | 150 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 12INR0071 | Caldwell | 30 | Nov-13 | Wind |
| 13INR0052 | Starr | 200 | Dec-13 | Wind |  | 11INR0085 | Nolan | 106 | Dec-13 | Wind |
| 12INR0054 | Jones | 200 | Dec-13 | Wind |  | 13INR0055 | Zapata | 250 | Dec-13 | Wind |
| 13INR0038 | Swisher | 300 | Dec-13 | Wind |  | 13INR0050 | Comanche | 200 | Dec-13 | Wind |
| 13INR0036 | Hidalgo | 200 | Dec-13 | Wind |  | 10INR0009 | Castro | 300 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 13INR0026 | Oldham | 201 | Dec-13 | Wind |  | 13INR0030 | Archer | 100 | Dec-13 | Wind |
| 13INR0039 | Castro | 500 | Dec-13 | Wind |  | 11INR0057 | Cameron | 165 | Dec-13 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 12INR0084 | Randall | 242 | Jan-14 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 14INR0013 | Cameron | 103 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 14INR0014 | Val Verde | 100 | Jan-14 | Solar |  | 10INR0080 | Presidio | 81 | Jan-14 | Solar |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 13INR0020b | Glasscock | 150 | May-14 | Wind |
| 14INR0015 | Harris | 192 | Jun-14 | Gas |  | 14INR0012 | Gray | 401 | Jun-14 | Wind |
| 14INR0016 | Harris | 190 | Jun-14 | Gas |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0010 | Roberts | 300 | Jul-14 | Wind |  | 11INR0054 | San Patricio | 161 | Jul-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 13INR0031 | Austin | 30 | Oct-14 | Solar |  | 14INR0023 | Briscoe | 361 | Dec-14 | Wind |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 12INR0018 | Gray | 500 | Dec-14 | Wind |
| 14INR0018 | Nolan | 35 | Dec-14 | Solar |  | 14INR0009 | Kent | 248 | Dec-14 | Wind |
| 14INR0020 | Floyd | 150 | Dec-14 | Wind |  | 10INR0085 | Ector | 40 | Dec-14 | Solar |
| 11INR0079a | Clay | 200 | Dec-14 | Wind |  | 12INR0029 | Swisher | 500 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 12INR0057 | Ector | 40 | Apr-15 | Solar |
| 15INR0014 | Matagorda | 280 | Oct-15 | Gas |  | 15INR0013 | Anderson | 324 | Oct-15 | Gas |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 14INR0005 | Matagorda | 1,200 | Jan-16 | Coal |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 14INR0003 | Nolan | 850 | Jun-18 | Coal |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- South Texas Electric Cooperative (STEC) has submitted the Karnes Electric Cooperative (KEC) and Medina Electric Cooperative (MEC) load addition project to accommodate 245 MW of new load in Karnes and Atascosa Counties. This is a Tier 2 project that is estimated to cost $48.4 million. This Tier 2 project is undergoing ERCOT Independent Review.

- CenterPoint Energy has submitted the Freeport Area upgrades project. This is a Tier 3 project that is estimated to cost approximately $47.2 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 5906 | 0 - 2800 | 37,627,990 | 5YTP [2010-R7, R8] |
| BASE CASE | West to North Stability Limit | 8109 | 0 - 436 | 26,823,063 | CREZ |
| Sacroc - Sun Switch 138 kV; or Golden Switch - Sun Switch 138 kV | China Grove - Bluff Creek 138 kV | 1357 | 0 - 3500 | 24,675,406 | 13TPIT0093 |
| Twin Buttes 345/138/ kV Autotransformer | San Angelo Red Creek 345/138 kV Autotransformer 2 | 113 low-side; and 262 high-side | 19 - 3500 low-side; and 2 - 4500 high-side | 18,360,051 | 14TPIT0067 |
| Lewisville - Carrollton Northwest 345 kV | Lewisville - Jones Street Tnp 138 kV | 4632 | 0 - 3500 | 16,918,023 | CREZ, 07TPIT0042 |
| Batesville 138/69 kV Autotransformer; or Batesville Switching Station - Paloduro Substation 138 kV | Moore Switching Station - Downie Switching Station 138 kV | 844 | 0 - 3500 | 11,526,855 |  |
| Kyle - San Marcos 138 kV | Turnersville - Buda 138 kV | 276 | 0 - 3500 | 10,106,920 | 09TPIT0060 |
| Marshall Ford - Lago Vista 138 kV | Buttercup - Whitestone 138 kV | 151 | 6 - 3500 | 7,020,443 | 10TPIT0074 |
| China Grove - Bluff Creek 138 kV | Moss - Amoco North Cowden Tap 138 kV | 396 | 0 - 3500 | 5,898,186 | 13TPIT0093 |
| Comanche Peak 1 & 2 | Austrop - Sandow 345 kV | 247 | 0 - 4500 | 5,526,564 |  |

Binding Constraints – May 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Amoco North Cowden Tap - Moss 138kV; or Moss - Odessa EHV 345 kV & Moss - Midland East 345 kV | Odessa North 138/69 kV Autotransformer | 2615 | 0 - 2275 | 20,210,515 | 5YTP [2010-R7, R8] |  |
| Twin Buttes 345/138 kV Autotransformer | San Angelo Red Creek 345/138 kV Autotransformer 2 | 226 | 2 - 4500 | 11,787,813 | 14TPIT0067 | Forced outage of San Angelo Red Creek 345/138 kV Autotransformer 1 |
| Batesville 138/69 kV Autotransformer; or Batesville Switching Station - Paloduro Substation 138 kV | Moore Switching Station - Downie Switching Station 138 kV | 726 | 0 - 3500 | 9,381,324 |  | PCAP has been developed |
| Kyle - San Marcos 138 kV | Turnersville - Buda 138 kV | 241 | 0 - 3500 | 7,842,507 | 09TPIT0060 | Kendall 138 kV bus outage |
| Marshall Ford - Lago Vista 138 kV | Buttercup - Whitestone 138 kV | 151 | 6 - 3500 | 7,020,443 | 10TPIT0074 | Glasscock - Andice 138 kV line outage |
| Farmersville - Monticello SES 345 kV double-circuit | Monticello SES - Allen Switch 345 kV | 66 | 6 - 4500 | 3,126,906 | 07TPIT0119 |  |
| Brownwood - Comanche Switch 138 kV | Brownwood Switch - Camp Bowie 138 kV | 107 | 247 - 3500 | 2,777,558 |  |  |
| Sacroc - Sun Switch 138 kV; or Golden Switch - Sun Switch 138 kV | China Grove - Bluff Creek 138 kV | 81 | 8 - 3500 | 2,550,017 | 13TPIT0093 |  |
| Lytton Springs - Fayette Plant 2 345 kV & Holman - Fayette Plant 2 345 kV; or Austrop - Lost Pines 345 kV double-circuit | Fayetteville 345/138 kV Autotransformer | 1089 | 0 - 3157 | 2,371,040 |  |  |
| Allen Switch - Royse Switch 345 kV & Allen Switch - Monticello SES 345 kV | Apollo - Richardson East 138 kV | 89 | 6 - 3500 | 2,168,449 | 09TPIT0044 10TPIT0013 |  |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Work on the development of the 2013 Data Set A cases continues with an expected completion the second week of July.

- The June base case TPIT updates will begin the second week of July with anticipated completion the second week of August.

- Data Set B is expected to begin the first week of August with the Topology Processor case extracted from NMMS on August 1 with a build date of January 1, 2013.

- The short term calendar of major planning model events follows:

  - July 9, 2012	Post 13 Data Set A cases.

  - Aug 1, 2012	Extract Topology Processor case with Jan 1, 2013 build date.

  - Aug 10, 2012	Post 12 Data Set A and B June TPIT updated cases.

  - Oct 15, 2012	Data Set B cases posted

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  Item 1 considered to be in production.  Requirements for Item 6 are in development.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The System Protection Working Group 2012 Future Year (FY) cases are complete and posted.  This year, five future year cases instead of four were built for the first time, from 2013 to 2017.

- The 2012 Five-Year Transmission Plan study final scope and Reliability start cases were posted at ERCOT POI on June 14. Currently the 2012 5YTP reliability analysis is being performed.

- ERCOT System Planning is reviewing and comparing the dynamic model data submitted through the RARF to the DWG dynamic base case. Review results are being provided to Resource Entities for updates and confirmation.

- ERCOT is spot checking governor model performance by comparing the actual measurement with dynamic model response. Review results will be provided to Resource Entities for updates and confirmation.