## 2012 5YTP Schedule
Task | Sub-Task | 2012-05-01 | 2012-05-08 | 2012-05-15 | 2012-05-22 | 2012-05-29 | 2012-06-05 | 2012-06-12 | 2012-06-19 | 2012-06-26 | 2012-07-03 | 2012-07-10 | 2012-07-17 | 2012-07-24 | 2012-07-31 | 2012-08-07 | 2012-08-14 | 2012-08-21 | 2012-08-28 | 2012-09-04 | 2012-09-11 | 2012-09-18 | 2012-09-25 | 2012-10-02 | 2012-10-09 | 2012-10-16 | 2012-10-23 | 2012-10-30 | 2012-11-06 | 2012-11-13 | 2012-11-20 | 2012-11-27 | 2012-12-04 | 2012-12-11 | 2012-12-18
Reliability case conditioning | Prepare the input data for the PW condition case | bar: 2012-05-01 to 2012-05-29
Condition case for Powerworld case for 2017, 2015 & 2013 | bar: 2012-05-29 to 2012-06-12
Reliability start cases | Reliability Analysis including 2011 5YTP projects for 2017, 2015, 2013 | bar: 2012-06-19 to 2012-07-03
Reliability Analysis | Work with TO's to identify projects for all remaining Reliability issues | bar: 2012-07-10 to 2012-07-24
2013-2017 Reliability Analysis - finalize analysis | bar: 2012-07-24 to 2012-08-07
Generator Outage Screening - TARA | bar: 2012-08-07 to 2012-08-14
Voltage Screening & identify projects | bar: 2012-08-07 to 2012-08-14
Identify G-1 & N-1 projects | bar: 2012-08-14 to 2012-08-21
Reliability Projects Backout | bar: 2012-08-14 to 2012-08-21
Draft Report Section I & II | Draft Report Section I & II | bar: 2012-07-31 to 2012-08-07
Draft Report Section III | Prepare data/tables for Section III | bar: 2012-08-07 to 2012-08-21
Draft Report Section III | bar: 2012-08-21 to 2012-09-04
Economic case building | Gather UPLAN data | bar: 2012-07-31 to 2012-08-21
Convert 2017, 2015, 2013 Reliability Case to UPLAN | bar: 2012-08-21 to 2012-08-28
Economic Start Cases | 2017 Economic Analysis - Initial | bar: 2012-08-28 to 2012-09-11
2015 Economic Analysis - Initial | bar: 2012-09-11 to 2012-09-25
Economic Analysis | 2017 Economic Analysis - Work with TOs & 2nd pass | bar: 2012-10-02 to 2012-10-16
2015 Economic Analysis - Work with TOs & 2nd pass | bar: 2012-10-16 to 2012-10-30
2017 & 2015 Economic Analysis - Back Out and Finalize | bar: 2012-11-06 to 2012-11-13
2013 Economic Analysis | bar: 2012-10-30 to 2012-11-13
Draft Report Section IV | Draft Report Section IV | bar: 2012-11-13 to 2012-11-20
Final Reliability cases including Economic projects | bar: 2012-11-13 to 2012-11-20
Sensitivity Analysis | Other sensitivity for Reliability analysis | bar: 2012-10-30 to 2012-11-20
Final Report & postings | Final Report & postings | bar: 2012-11-20 to 2012-12-18