## Slide 1
Business Integration Update to PRS
June 19, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets
    Project Spending Update
  Project Update p. 7
    Settlement System Upgrade
  Appendix
    Project Portfolio Gantt Chart p. 9-15
    ERCOT FTE Tracking p. 16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in July (no integrated software release)
  NPRR354 – Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment
    EIS portion (Non-Spin Performance Report)
    All other portions went live in June release
  Lawson Upgrade
Go-Lives in August (8/26/2012 – 8/29/2012)
  NPRR348 – Generation Resource Start-Up and Shut-Down Process
  NPRR382 – Verbal RUC Committed or Decommitted Resources Report
  NPRR383 – Unconfirmed Trades Reports
  NPRR422 – Public DAM Shift Factors
  NPRR442 – Energy Offer Curve Requirement for Generation Resources Providing RMR Service
  ERCOT Mobile App
    Completion of Execution phase
    Both Apple and Android versions available for download
  SMTNET Improvements
    Study Multi-Time Network update to enhance granularity in data used for analysis
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 | NPRR313 NPRR322 NPRR365 NPRR397 | NPRR260 NPRR272 NPRR377 SCR768 | NPRR222 NPRR416 NPRR419 NPRR456 NPRR469
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) |  | NPRR357 NPRR430 | NPRR347 NPRR391 NPRR400 | 
Counts Total = 44 | 5 | 5 | 10 | 6 | 6 | 7 | 5
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change
November
None
Early June
None
Early Oct
None

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2013 TBD
On-Cycle |  | NPRR439 SCR760(d) | NPRR327 NPRR393 NPRR463 SCR769 SCR771 | NPRR407 SCR770 | NOGRR084 |  | NPRR207 NPRR457 SCR756(b)
Off-Cycle |  |  |  |  |  |  | NPRR455
Counts Total = 14 | 0 | 2 | 5 | 2 | 1 | 0 | 4
Note 1: Underline indicates new/revised release targets
Note 2: (a), (b), etc. indicates multiple release phases
Note 3: Release targets are subject to change – Please watch for market notices as effective dates approach
None
None
None
None
None
None
Note 4: Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
2014 TBD

## Slide 6: Project Spending Update
PPL – 2012 | Portfolio Budget (effective 1/1/2012) | 2012 Spending Projection of In-Flight Projects (as of 6/30/2012) | Current 2012 Demand (as of 6/30/2012) | 2012 YTD Actual (as of 6/30/2012)
Business Strategy |  | $ 5,474,719 | $ 6,748,696 | $ 3,098,069
Regulatory |  | $ 840,822 | $ 936,967 | $ 489,131
Efficiencies/Enhancements |  | $ 2,421,248 | $ 2,782,290 | $ 1,253,356
Technical Foundation |  | $ 6,814,047 | $ 7,792,962 | $ 3,022,771
Totals | $ 15,000,000 | $ 15,550,836 | $ 18,260,915 | $ 7,863,327
ERCOT Public
Project Spending Update Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that have started or are complete
Current 2012 Demand: Projected 2012 spend of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: Project Update
Settlement System Rewrite
  Overview
    Project to replace the current Settlements application code with an optimized, self-supported solution (includes only the conversion of code – no enhancements)
    Gated to Execution early in 2012
    Development, testing and deployment will span 2012-2104
    During this timeframe, there is increased risk of impacting the project cost and schedule by either:
      Creating a need to make develop, test and deploy changes in both the current production system and the Rewrite code under development
      Redirecting resources intended for the Rewrite effort to other Settlements changes, thus impacting the Rewrite schedule
  Risk Management Approach
    It is important to manage risk to the project by assessing impacts of other requested changes to the Settlements system
    To assist in this, ERCOT will begin capturing impacts to the Rewrite project on any Impact Analysis that impacts the Settlements system
    Going forward, ERCOT requests that the market consider impacts to the Rewrite project when assigning Priority and Rank to new revision requests

## Slide 8: Business Integration Update – Appendix
  Appendix
    6/29/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date
    ERCOT FTE Tracking
      Revised format

## Slide 9
Project Portfolio Status – as of 6/29/2012

## Slide 10
Project Portfolio Status – as of 6/29/2012

## Slide 11
Project Portfolio Status – as of 6/29/2012

## Slide 12
Project Portfolio Status – as of 6/29/2012

## Slide 13
Project Portfolio Status – as of 6/29/2012

## Slide 14
Project Portfolio Status – as of 6/29/2012

## Slide 15
Project Portfolio Status – as of 6/29/2012

## Slide 16: ERCOT FTE (Full Time Equivalent) Impacts of Revision Requests
This slide documents additional staff required to support ongoing ERCOT operations activities
ERCOT Public
--- Board Approved --- (August 2011 – Current) |  |  |  |  |  | Incremental Labor Impact of Change | Net ERCOT Staffing Impact | 
Board Approval | Revision Request | Revision Description |  |  | ERCOT Department | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact
9/20/2011 | NPRR365 | Change in Resource Outage Approvals from Eight to 45 Days |  |  | Outage Coordination | 2.00 | 2 | $240k-$260k
2/21/2012 | NPRR408 | Clarification of ERCOT Authority to Deny Energization of Non-Compliant Generators |  |  | Resource Integration | 0.10 | 0 | $0
4/17/2012 | NPRR327 | State Estimator Data Redaction Methodology |  |  | Operations Support | 1.00 | 1 | $120k-$130k
4/17/2012 | NPRR393 | SCED Constraint Management Transparency |  |  | Operations Support | 1.00 | 1 | $120k-$130k
4/17/2012 | NPRR421 | Clarification of RMR Notifications |  |  | Operations Analysis | 1.00 | 1 | $120k-$130k
 |  |  |  |  | Wholesale Client Services | 0.25 | 0 | $0
6/19/2012 | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users |  |  | Enterprise Info. Mgmt. | 1.00 | 1 | $120k-$130k
6/19/2012 | NPRR463 | CRR Auction Structure Enhancements |  |  | Congestion Revenue Rights | 0.70 | 1 | $120k-$130k
7/17/2012 | NPRR438 | Add’l Minimum Counter-Party Qualification Reqs., Including Risk Mgmt Capability Reqs. |  |  | Credit | 1.00 | 1 | $120k-$130k
 | Board Approved Items |  |  |  |  | 8.05 | 8 | 
--- In-Flight at Board / TAC --- |  |  |  |  |  | Labor Effort (in FTEs) | Additional FTEs Required | Budget Impact
 | In-Flight at Board / TAC |  |  |  |  | 0.00 | 0 | 
 | Total of All Items |  |  |  |  | 8.05 | 8 |