## Slide 1
Business Integration Update to PRS
August 23, 2012
Notes: <number>

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets
    Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-13
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Notes: <number>

## Slide 3: Upcoming Project Implementations
Go-Lives in August (8/26/2012 – 8/29/2012)
  NPRR348 – Generation Resource Start-Up and Shut-Down Process
  NPRR354 – Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment
    EIS portion (Non-Spin Performance Report)
    All other portions went live in June release
  NPRR382 – Verbal RUC Committed or Decommitted Resources Report
  NPRR383 – Unconfirmed Trades Reports
  NPRR422 – Public DAM Shift Factors
  NPRR442 – Energy Offer Curve Requirement for Generation Resources Providing RMR Service
  SMTNET Improvements
    Study Multi-Time Network update to enhance granularity in data used for analysis
  Lawson Upgrade
Go-Lives in September (no integrated software release)
  NPRR357 – Revisions to Collateral Requirements Concerning CRR Auctions
  NPRR430 – Corrections Related to NPRR357, Revisions to Collateral Requirements Concerning CRR Auctions, and Clarification to Collateral Requirements
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 | NPRR365 | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR469 SCR768 | NPRR456
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) | NPRR357 NPRR430 |  | NPRR347 NPRR391 NPRR400 | NPRR222
Counts Total = 41 | 5 | 5 | 10 | 6 | 3 | 10 | 2
Note 1: Bold indicates inclusion in the original Board-approved 2012 PPL
Note 2: Underline indicates new/revised release targets
Note 3: (a), (b), etc. indicates multiple release phases
Note 4: Release targets are subject to change
ERCOT Public
November
Early Sept
Early June
None
None
None
Deleted

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2013 TBD
On-Cycle |  | NPRR207 NPRR416 NPRR419 NPRR439 NPRR463 SCR760(d) | NPRR272 NPRR393 NPRR457 SCR769 SCR770 SCR771 | NPRR327 NPRR407 | NOGRR084 |  | SCR756(b)
Off-Cycle |  |  |  |  |  |  | NPRR455
Counts Total = 17 | 0 | 6 | 6 | 2 | 1 | 0 | 2
Note 1: Underline indicates new/revised release targets
Note 2: (a), (b), etc. indicates multiple release phases
Note 3: Release targets are subject to change – Please watch for market notices as effective dates approach
ERCOT Public
None
None
None
None
None
None
Note 4: Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
2014 TBD

## Slide 6: Project Spending Update
PPL – 2012 | Portfolio Budget (effective 1/1/2012) | 2012 YTD Actual (as of 7/31/2012) | 2012 Spending Projection of In-Flight Projects (as of 7/31/2012) | Current 2012 Demand (as of 7/31/2012)
Business Strategy |  | $ 3,725,160 | $ 5,702,758 | $ 6,670,059
Regulatory |  | $ 628,316 | $ 914,091 | $ 956,999
Efficiencies/Enhancements |  | $ 1,515,216 | $ 2,631,530 | $ 2,770,057
Technical Foundation |  | $ 3,642,205 | $ 6,882,589 | $ 7,272,666
Totals | $ 15,000,000 | $ 9,510,897 | $ 16,130,968 | $ 17,669,781
ERCOT Public
Project Spending Update Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that have started or are complete
Current 2012 Demand: Projected 2012 spend of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: Business Integration Update – Appendix
  Appendix
    8/10/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date
Notes: <number>

## Slide 8
ERCOT Public
Project Portfolio Status – as of 8/10/2012

## Slide 9
ERCOT Public
Project Portfolio Status – as of 8/10/2012

## Slide 10
ERCOT Public
Project Portfolio Status – as of 8/10/2012

## Slide 11
ERCOT Public
Project Portfolio Status – as of 8/10/2012

## Slide 12
ERCOT Public
Project Portfolio Status – as of 8/10/2012

## Slide 13
ERCOT Public
Project Portfolio Status – as of 8/10/2012