## Sheet1
Items for Prioritization Discussion at June PRS Meeting
Row # | Sort Char | Category | Revision Req # | Revision Request Description | Board Approval Date | Current Status | Systems Impacted | ERCOT Position | Recommended Next Step | Target Start Date | Target Go-Live Date | IA Details
1 | 0 | Deleted by Subsequent NPRR | NPRR164 | Resubmitting Ancillary Service Offers in SASM - Revises existing rules for resubmitting AS offers in the Adjustment Period. [TPTF] | 2010-01-19 | Parking Deck | MMS | No action necessary due to approval of NPRR307 on 3/22/2011 | Remove from Parking Deck tracking tab | n/a | n/a | Due to “Not Needed for Go-Live” designation by the ERCOT CEO, the Impact Analysis for this item will be conducted at a future date.
2 | 1 | Project initiated on 6/13 | NPRR377 | Alternate Inputs to Base Point Deviation Charge - Align the Adjusted Aggregated Base Points (AABP) formula with the inputs to the GREDP measure. [ERCOT] | 2011-12-12 | Board Approved | EMS, CSI, S&B, EIS, Storage | Proceed according to plan as noted on the PPL and project Gantt | Proceed with a target implementation in Q4/2012 | June 2012 | Dec 2012 | Cost: $150k - $165k Duration: 14 weeks
3 | 1 | Project initiated on 6/13 | NPRR422 | Public DAM Shift Factors. - Creates a new report to provide Day-Ahead Shift Factors on the MIS Public Area. [MISUG] | 2012-02-21 | Board Approved | MMS, CDR | Proceed according to plan as noted on the PPL and project Gantt | Proceed with a target implementation in Q3/2012 | June 2012 | Aug 2012 | Cost: $20k - $25k Duration: 3 - 5 months
4 | 1 | Project initiated on 6/13 | NPRR442 | Energy Offer Curve Requirement for Generation Resources Providing Reliability Must-Run Service - Adds a requirement for the Energy Offer Curve to be set at the SWCAP for Generation Resources providing RMR Service. [Morgan Stanley] | 2012-05-15 | Board Approved | MMS | Initiate project in late Q2/2012 due to synergies discovered after Board approval | Request PRS reprioritization to 2012 -- target release in Q3/2012 | June 2012 | Aug 2012 | Cost: $35k - $45k Duration: 3 - 4 months
5 | 1 | Project initiated on 6/13 | SCR768 | Automatic Non-Spin Redeployment and Deployment Based on Resource Availability - Modifies the MMS Automatic Redeployment function such that it accounts for the delay involved in deployment of Off-Line Non-Spinning Reserve (Non-Spin) Resources. [ERCOT] | 2012-04-17 | Board Approved | MMS, EIS, ISM | Proceed according to plan as noted on the PPL and project Gantt | Proceed with a target implementation in Q4/2012 | June 2012 | Dec 2012 | Cost: $55k - $70k Duration: 4 - 6 months
6 | 2 | "Not Started" Project | NOGRR084 | Daily Grid Operations Summary Report - Creates a summary level report of daily operational information to be posted on the MIS Public Area. [MIS Users Group] | 2012-05-15 | Board Approved | MMS, EMS, ISM, MIS | Due to project size and complexity, defer initiation to late 2012 or early 2013 | Initiate project in Q4/2012 or Q1/2013 | Jan 2013 | R5 2013 | Cost: $300k-$500k Duration: 7-9 months
7 | 2 | "Not Started" Project | NPRR207 | Unit Deselection - Allow ERCOT to deselect units from RUC processes. - [QSTF/WMS] | 2010-07-20 | Board Approved | MMS | Requesting market input on timing and need -- NPRR416 might make this less critical | Discuss with MPs to see if NPRR needed; affected by NPRR416 | Aug 2012 | Oct 2012 | Cost: $50k - $55k Duration: 9 - 11 weeks
8 | 2 | "Not Started" Project | NPRR210 | Wind Forecasting Change to P50, Synchronization with PRR841 - Changes the wind forecasting methodology to use a 50% probability of exceedance calculation instead of an 80% for RUC considerations. [Morgan Stanley] | 2010-06-15 | Board Approved | EMS, MMS, CSI, S&B, EIS | Consider waiting for decision on NPRR429 because it also impacts RUC Capacity Short calculation | Leave start date "TBD" until resolution on NPRR429 is reached | TBD 2013 | TBD | Cost: $45k - $55k Duration: 8 - 16 weeks
9 | 2 | "Not Started" Project | NPRR222 | Half-Hour Start Unit RUC Clawback - Removes RUC Clawback on all Half-Hour Start Units (a) that participate in the DAM and (b) during EEA events. [WMS] | 2010-07-20 | Board Approved | S&B, CSI | Consider waiting for decision on NPRR416; it strikes NPRR222 grayboxes | Change start date "TBD" until resolution on NPRR416 is reached | Oct 2012 | Dec 2012 | Cost: $15k - $20k Duration: 5 - 7 weeks
10 | 2 | "Not Started" Project | NPRR240 | Proxy Energy Offer Curve - The Entity with decision making authority over how a Resource or Split Generation Resource is offered or scheduled shall be responsible for all offers associated with each Resource, including offers represented by a proxy Energy Offer Curve. [Potomas Economics] | 2010-09-21 | Board Approved | MMS, EIS | Requesting market input on 2013 timing for this effort | Initiate project in Q?/2013 | TBD 2013 | TBD | Cost: $50k - $60k Duration: 12 - 14 weeks
11 | 2 | "Not Started" Project | NPRR241 | AIL Calculation and Credit Reports Publish Corrections - Updates AIL calculation to reflect Max ADTE during the previous 60-day period) instead of ADTE to match EAL calculation. [ERCOT] | 2010-09-21 | Board Approved | CMM | Requesting market input on 2013 timing for this effort | Initiate project in Q?/2013 | TBD 2013 | TBD | Cost: $100k - $120k Duration: 5 - 10 months
12 | 2 | "Not Started" Project | NPRR256 | Synchronize Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards - Aligns the Nodal Protocols with changes implemented from PRR787 and addresses the exclusion of GREDP during testing periods . [Luminant] | 2010-11-16 | Board Approved | EIS | Requesting market input on 2013 timing -- consider striking graybox if the current manual approach is acceptable to everyone | Discuss with stakeholders to see if NPRR is still needed | TBD 2013 | TBD | Cost: $120k - $135k Duration: 9 - 10 months
13 | 2 | "Not Started" Project | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users - Adds "Independent Market Information System Registered Entity (IMRE)" to Section 2.1 and Section 22. [Crescent Power] | 2011-01-18 | TAC Approved | ERCOT.com, MIS, Siebel, MPIM, EI, EIS | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q3/2012 | July 2012 | Dec 2012 | Implementation Cost: $140k-$220k - Includes a temporary contract resource for up to 6 months. Annual Recurring O&M Budget Cost : $120k-$130k
14 | 2 | "Not Started" Project | NPRR272 | Definition and Participation of Quick Start Generation Resources - Provides language for effective participation of QSGRs in SCED. [ERCOT] | 2010-11-16 | Board Approved | EMS, MMS, CSI, S&B, CDR, EIS | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q3/2012 | Aug 2012 | Dec 2012 | Cost: $145k - $160k Duration: 20 - 22 weeks
15 | 2 | "Not Started" Project | NPRR327 | State Estimator Data Redaction Methodology. Inserts language to define a redaction methodology for the posting of State Estimator data. [ERCOT] | 2012-04-17 | Board Approved | EMS, CDR, MIS, ISM, NMMS | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q3/2012 | Aug 2012 | R3 2013 | Cost: $155k - $175k Duration: 5 - 8 months
16 | 2 | "Not Started" Project | NPRR393 | SCED Constraint Management Transparency. - Creates a reporting requirement to provide transparency into SCED constraint management decisions. [J Aron] | 2012-04-17 | Board Approved | EMS, MIS, ISM | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q4/2012 | Dec 2012 | R3 2013 | Cost: $80k - $85k Duration: 4 - 6 months
17 | 2 | "Not Started" Project | NPRR397 | Balance of the Day Ancillary Service Market. - Allows the SASM to be operated as a balance of the day market for Ancillary Services. [Morgan Stanley] | 2012-04-17 | Board Approved | MMS | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q3/2012 | Jul 2012 | Oct 2012 | Cost: $20k - $25k Duration: 3 months
18 | 2 | "Not Started" Project | NPRR407 | Credit Monitoring Posting Requirements - Adds language to require posting of current and previously effective credit parameters to the MIS Certified Area. [Tenaska] | 2012-02-21 | Board Approved | MMS, CRR, CDR, MIS, ISM | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q4/2012 | Oct 2012 | R4 2013 | Cost: $120k - $130k Duration: 4 - 6 months
19 | 2 | "Not Started" Project | NPRR419 | Revise Real Time Energy Imbalance and RMR Adjustment Charge. - Revises the Real-Time Energy Imbalance equations and revises the RMR Adjustment Charge to charge the QSE for the revenues paid in accordance with the energy imbalance calculation. [ERCOT] | 2012-04-17 | Board Approved | S&B | Consider 2 phases: RMR portion first, hold energy imbalance until NPRR461 is resolved | Initiate project in Q3/2012 | Aug 2012 | Dec 2012 | Cost: $25k - $30k Duration: 3 - 5 months
20 | 2 | "Not Started" Project | NPRR439 | Updating a Counter-Party’s Available Credit Limit for Current Day DAM. - Provides flexibility for Counter-Parties to increase the credit limit available for the Day-Ahead Market (DAM) on the day the DAM is running by posting additional Financial Security under certain circumstances after ERCOT has already set a daily credit limit. [ERCOT] | 2012-05-15 | Board Approved | MMS; CMM; ISM | Proceed according to plan as noted on the PPL and project Gantt | Initiate project in Q4/2012 | Oct 2012 | R2 2013 | Cost: $125k - $135k Duration: 4 - 6 months
21 | 2 | "Not Started" Project | SCR769 | CRRAH Digital Certificate New Role for Read Only Access - Provide the capability to a read only role in addition to the read and write role for CRR Account Holders. [Austin Energy] | 2012-04-17 | Board Approved | CRR, MPIM | Due to resource constraints with CRR development, defer initiation to 2013 | Initiate project in 2013 | Jan 2013 | R3 2013 | Cost: $100k - $110k Duration: 3 - 5 months
22 | 2 | "Not Started" Project | SCR770 | Revision to Outage Scheduler Entry for Resource Maintenance Outage Level Designation - Change the Outage Scheduler system so that the QSE is able to schedule Level I, II and III Maintenance Outages. [Luminant] | 2012-05-15 | Board Approved | Outage Scheduler | ERCOT concurs with the market recommendation to defer action on this item to 2013 | Initiate project in Q1/2013 | Jan 2013 | R4 2013 | Cost: $90k - $105k Duration: 3 - 5 months
23 | 2 | "Not Started" Project | SCR771 | ERCOT System Change Allowing Independent Master QSE to Represent Split Generation Resources - Allows owners of Split Generation Resources to contract for service with an independent Master QSE. [Sandy Creek Services] | 2012-05-15 | Board Approved | EMS, NMMS, Registration | Due to project size and complexity, defer initiation to late 2012 (potential conflict with Siebel upgrade) | Initiate project in Q4/2012 | Dec 2012 | R3 2013 | Cost: $100k - $110k Duration: 3 - 5 months
24 | 3 | Pending Further Market Approvals | NOGRR034 | Rescind Telemetry Performance Calculation Exclusions - Allows QSE and TSPs to request removal of telemetry from Telemetry Standard performance metrics when certain situations exist. [ERCOT] | 2010-09-21 | Parking Deck | TBD | ERCOT questions the economic value of this change | Submit NPRR to strike grey-boxed language | TBD | TBD | Due to “Not Needed for Go-Live” designation by the ERCOT CEO for the grey-boxed portions of NOGRR034, the Impact Analysis for the grey-boxed language will be conducted at a future date.
25 | 3 | Pending Further Market Approvals | NPRR153 | Generation Resource Fixed Quantity Block Offer - Allows a fixed quantity and time block bid for Offline Non-Spin with the contingency that all hours be purchased in the block. [TPTF] | 2010-01-19 | Parking Deck | MMS, EIF, EIS, CDR | ERCOT recommends that an IA be conducted to determine path forward | Prepare IA for PRS review in Q3/2012 | TBD | TBD | Due to “Not Needed for Go-Live” designation by the ERCOT CEO, the Impact Analysis for this item will be conducted at a future date.
26 | 3 | Pending Further Market Approvals | NPRR181 | FIP Definition Revision - Revises the definition of FIP to correctly account for the timing difference between ERCOT’s application of FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900). [Luminant] | 2010-01-19 | TAC (Tabled 11/3/11) | MMS, COMS, Integration | ERCOT questions the economic value of this change | Submit NPRR to strike grey-boxed language -- or -- leave tabled pending potential FERC ruling | TBD 2013 | TBD | Cost: $210k and $225k Duration: 10-12 Weeks
27 | 3 | Pending Further Market Approvals | NPRR219 / NOGRR050 | NPRR219, Resolution of Alignment Items A33, A92, A106, and A150 - TSPs Must Submit Outages for Resource Owned Equipment and Clarification of Changes in Status of Transmission Element Postings [ERCOT] NOGRR050, Resolution of Reporting Issues Related to NPRR219 [CenterPoint] | 2010-10-19 | Board (No action from the BOD on 3/22/11) | NMMS, RARF, SIEBEL, UI, NMMS TO OS, EIS, EI, EWS | ERCOT questions the economic value of the changes in 3.1.5.1 and 3.3.2.1 | Submit NPRR to strike grey-boxed language in 3.1.5.1 and 3.3.2.1 -- conduct IA on change to 3.1.3.1 | TBD | TBD | Cost: $565k - $750k Duration: 12-15 months
28 | 3 | Pending Further Market Approvals | NPRR257 / NOGRR025 | NPRR257, Synchronization with NOGRR025 - Greyboxes multiple sections to align with NOG Section 9, Monitoring ProgramsPrograms [ERCOT] NOGRR025, Monitoring Programs for QSEs, TSPs, and ERCOT, [ERCOT] | NPRR257 - 11/16/10 NOGRR025 - 9/15/2009 | Parking Deck | EMS, EIS, MIS | Revisit IA to determine elements still desired by stakeholders and elements already delivered | Categorize reports and determine next steps for each grouping | TBD | TBD | NPRR257, Effective upon the TNMID NOGRR025, Cost: $500k - $1M
29 | 3 | Pending Further Market Approvals | SCR755 | ERCOT.com Website Enhancements - Implementation of 10 improvements to ERCOT.com received in the 2008 Market Participant Survey. Includes document archiving, search improvements, training, meeting calendar enhancements, and RSS feeds. [CCWG] | 2010-02-16 | Parking Deck | ERCOT.com | Revisit IA to determine elements still desired by stakeholders and elements already delivered | Prepare IA for PRS review in Q3/2012 | TBD | TBD | Due to “Not Needed for Go-Live” designation by the ERCOT CEO, the Impact Analysis for this item will be conducted at a future date
30 | 3 | Pending Further Market Approvals | SCR756 | Enhancements to the MarkeTrak Application - Adds functionality to MarkeTrak to improve and standardize MP administration functions; implement ERCOT validations requested by the MTTF; and redesign the workflows to leverage potential vendor upgrades to MarkeTrak | 2010-07-20 | Board Approved | MarkeTrak | Perform IA on remaining SCR requirements in parallel with upcoming MarkeTrak Upgrade project | Conduct IA in Q3/2012 so we can initiate project upon completion of MarkeTrak Upgrade | TBD | TBD | Due to “Not Needed for Go-Live” designation by the ERCOT CEO, the Impact Analysis for this item will be conducted at a future date.