## Slide 1
Business Integration Update to PRS
September 20, 2012
Notes: <number>

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
      Note change of R5 release to 10/16-10/18
    2012 Release Targets
      Additions/Revisions in red text
      Prior target release dates in strike-through text
      NPRR407 - MMS/CDR portion to go live in 2012-R6
    2013 Release Targets
      Now includes target release dates!
      NPRR407 - CRR portion to go live in 2012-R4
    Project Spending Update
      Total Demand is reduced, reflecting shifting of work into 2013
  Quarterly Project Prioritization Discussion p. 7-9
  Appendix
    Project Portfolio Gantt Chart p. 11-15
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Notes: <number>

## Slide 3: Upcoming Project Implementations
Go-Lives in September (no integrated software release)
  NPRR357 – Revisions to Collateral Requirements Concerning CRR Auctions
  NPRR430 – Corrections Related to NPRR357, Revisions to Collateral Requirements Concerning CRR Auctions, and Clarification to Collateral Requirements
Go-Lives in October (R5) (10/16/2012 – 10/18/2012)
  NPRR365 – Change in Resource Outage Approvals from Eight to 45 Days
  UC4 Automation Upgrade
    Batch job scheduling software
  Contingency Functionality Enhancements
    Provide a more granular level of defining contingency groups
  ADP-IDM Interface
    Interface between back office ERCOT applications
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
ERCOT Public
November
Mid-Sept
Early June
None
Early Oct
None
Deleted
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
ERCOT Public
None
None
None
None
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
2014 TBD
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 6: Project Spending Update
PPL – 2012 Project Categories | Portfolio Budget (effective 1/1/2012) | 2012 YTD Actual (as of 8/31/2012) | 2012 Spending Projection of In-Flight Projects (as of 8/31/2012) | Current 2012 Demand (as of 8/31/2012)
Business Strategy |  | $ 4,221,288 | $ 5,880,221 | $ 6,453,719
Regulatory |  | $ 774,249 | $ 957,675 | $ 987,155
Efficiencies/Enhancements |  | $ 1,792,253 | $ 2,695,168 | $ 2,783,132
Technical Foundation |  | $ 4,126,596 | $ 6,520,644 | $ 6,788,365
Totals | $ 15,000,000 | $ 10,914,386 | $ 16,053,708 | $ 17,012,371
ERCOT Public
Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that are in-flight or are complete
Current 2012 Demand: Total cost of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: PPL Prioritization Discussion
On a quarterly basis, PRS conducts a review of upcoming revision request project efforts in order to get stakeholder input on the priority of items in the project queue
Today’s discussion will center on the timing of 24 upcoming efforts
  15 NPRRs, SCRs and NOGRRs that are Board-approved with PPL projects that have not yet started
  9 NPRRs, SCRs and NOGRRs that require additional analysis before seeking final Board approval
    These are the remaining Parking Deck items
    Current status of each reported to the Board of Directors this week

## Slide 8: PPL Prioritization Discussion – Revision Requests “Not Started”
Revision Request | Start Date
NPRR327 – State Estimator Data Redaction Methodology | Oct 2012
NPRR272 – Participation of Quick Start Generation Resources | Dec 2012
NPRR416 – Removal of the RUC Clawback Charge … Other than RMR Units | Dec 2012
NPRR419 – Revise Real Time Energy Imbalance and RMR Adjustment Charge | Dec 2012
SCR771 – Allow Independent Master QSE to Represent Split Gen. Resources | Dec 2012
NOGRR084 – Daily Grid Operations Summary Report | Dec 2012
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Dec 2012
NPRR456 – Electrically Similar Settlement Points and Heuristic Pricing Posting | TBD 2012
NPRR464 – SASM Procurement Reporting | TBD 2012
NPRR207 – Unit Deselection | Jan 2013
NPRR393 – SCED Constraint Management Transparency | Jan 2013
SCR770 – Rev. to Outage Sched. Entry for Resource Maint. Outage Level Desig. | Jan 2013
NPRR457 – Daily Update of New ESIIDs & AMS Meter & Switch Hold Ind. Chgs | Jan 2013
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Mar 2013
NPRR455 – CRR Shift Factors Report | TBD 2014

## Slide 9: PPL Prioritization Discussion – Parking Deck
Revision Request | Status
NPRR153, Generation Resource Fixed Quantity Block Offer | Impact Analysis (IA) to be considered at 9/20/12 PRS
NPRR181, FIP Definition Revision | Tabled at 11/3/11 TAC
NPRR219, Resolution of Alignment Items A33, A92, A106, and A150 - TSPs Must Submit Outages for Resource Owned Equipment and Clarification of Changes in Status of Transmission Element Postings NOGRR050, Resolution of Reporting Issues Related to NPRR219 | 3/22/11 Board considered IA; took no action ERCOT/ROS reviewing current need
NPRR257, Synchronization with NOGRR025 NOGRR025, Monitoring Programs for QSEs, TSPs, and ERCOT | ERCOT has categorized reports (~50) and will review next steps with stakeholders
NOGRR034, Rescind Telemetry Performance Calculation Exclusions | ERCOT/ROS reviewing need
SCR755, ERCOT.com Website Enhancements | ERCOT developing IA for stakeholder review
SCR756, Enhancements to the MarkeTrak Application | ERCOT reviewing with MarkeTrak Task Force

## Slide 10: Business Integration Update – Appendix
  Appendix
    9/14/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date
Notes: <number>

## Slide 11
ERCOT Public
Project Portfolio Status – as of 9/14/2012

## Slide 12
ERCOT Public
Project Portfolio Status – as of 9/14/2012

## Slide 13
ERCOT Public
Project Portfolio Status – as of 9/14/2012

## Slide 14
ERCOT Public
Project Portfolio Status – as of 9/14/2012

## Slide 15
ERCOT Public
Project Portfolio Status – as of 9/14/2012