|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report September 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 143 active generation interconnection requests totaling almost 39,000 MW. This includes over 21,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $257.5 Million - Transmission Projects endorsed in 2012 total $550.9 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.68 Billion. - Transmission Projects energized in 2012 total about $732.2 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

11INR0054 – Midway Farms – 161 MW of Wind in San Patricio County

09INR0051 – Mesquite Creek – 249 MW of Wind in Borden County

13INR0023 – Texas Clean Energy – 240 MW of Coal IGCC in Ector County

## New Generation Registering for Commercial Operations - none

The total installed wind capacity is now reported as 10,035 MW by the resource owners through the registration process. Capacity by North, South and West is 519 MW,  2,283 MW, and 7,233 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 159 generation interconnection or change requests |  |  |  |  |
| As of September 30, 2012 | North | South | West | Total |
| Security Screening Study | 4 | 4 | 1 | 9 |
| SSS Completed | 1 | 9 | 8 | 18 |
| Full Interconnect Study | 10 | 21 | 46 | 77 |
| FIS Completed | 1 | 5 | 6 | 12 |
| Suspended Studies | 2 | 1 | 13 | 16 |
| Capacity of Suspended Study Projects | 3,450 | 249 | 6,701 | 10,401 |
| Interconnect Agreement Completed | 9 | 9 | 9 | 27 |
| Capacity under Interconnection Agreements | 5,490 | 3,635 | 1,737 | 10,862 |
| Capacity for Grid, MW | 11,896 | 10,801 | 15,853 | 38,549 |
| Wind Capacity, MW | 3,643 | 4,216 | 13,448 | 21,306 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 2,303 |
| Gas-CombinedCycle |  |  | 5,595 |  | 10,730 |
| Total Gas | 4,227 | 3,211 | 5,595 |  | 13,033 |
| Nuclear |  |  |  | 3,200 | 3,200 |
| Coal |  | 850 | 1,165 |  | 2,015 |
| Wind | 4,196 | 14,345 | 2,766 | 7,162 | 28,469 |
| Solar | 204 | 615 | 60 | 38 | 917 |
| Biomass |  |  |  |  |  |
| Storage |  | 40 | 36 |  | 76 |
| Petroleum Coke |  |  | 1,240 |  | 1,240 |
| Grand Total | 8,627 | 19,061 | 10,862 | 10,400 | 48,950 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

(Status: IA=Interconnect Agreement,  XX= cancelled)

| Generation Interconnections as of September 30, 2012 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid |  | Change from Last Report |
| 12INR0076 | Notrees Battery Storage | IA | Winkler | West | Dec-12 |  | Storage |  | 36 |  |
| 12INR0075 | Blue Summit Windfarm | IA | Wilbarger | West | Dec-12 |  | Wind |  | 135 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Dec-12 |  | Wind |  | 150 |  |
| 11INR0091 | Whitetail Wind Energy Project | IA | Webb | South | Dec-12 |  | Wind |  | 92 |  |
| 12INR0072 | Anacacho Windfarm | IA | Kinney | South | Dec-12 |  | Wind |  | 100 |  |
| 09INR0061 | WKN Mozart | IA | Kent | West | Dec-12 |  | Wind |  | 30 |  |
| 08INR0049 | Briar Creek | IA | Clay | North | Dec-12 |  | Wind |  | 50 |  |
| 11INR0033 | Los Vientos | IA | Cameron | South | Dec-12 |  | Wind |  | 400 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Mar-13 |  | Coal |  | 925 |  |
| 11INR0086 | RRE Austin Solar | IA | Travis | South | Oct-13 |  | Solar |  | 60 |  |
| 11INR0013 | Goldthwaite Wind Energy | IA | Mills | North | Dec-13 |  | Wind |  | 150 |  |
| 11INR0054 | Midway Farms Wind | IA | San Patricio | South | Dec-13 |  | Wind |  | 161 | New |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-13 |  | Wind |  | 202 |  |
| 12INR0034 | Stephens-Borlynn Wind Project | IA | Borden | West | Dec-13 |  | Wind |  | 378 |  |
| 13INR0021 | Ferguson Replacement Project | IA | Llano | North | Jul-14 |  | Gas-CC |  | 116 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Aug-14 |  | Wind |  | 120 |  |
| 11INR0050 | Moore Wind 1 | IA | Crosby | West | Aug-14 |  | Wind |  | 149 |  |
| 10INR0023 | Baker Ranch | IA | Haskell | West | Sep-14 |  | Wind |  | 400 | Date |
| 10INR0021 | Panda Sherman Power | IA | Grayson | North | Dec-14 |  | Gas-CC |  | 717 | Date |
| 10INR0020a | Panda Temple 1 Power | IA | Bell | North | Dec-14 |  | Gas-CC |  | 780 | Date |
| 09INR0051 | Mesquite Creek | IA | Borden | West | Mar-15 |  | Wind |  | 249 | New |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-15 |  | Gas-CC |  | 1,792 |  |
| 10INR0020b | Panda Temple 2 Power | IA | Bell | North | Dec-15 |  | Gas-CC |  | 780 |  |
| 13INR0023 | Texas Clean Energy Project | IA | Ector | West | Jan-16 |  | Coal |  | 240 | New |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-16 |  | Gas-CC |  | 1,380 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | May-18 |  | PetCoke |  | 620 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | May-18 |  | PetCoke |  | 620 |  |
|  |  |  |  |  |  |  | TOTAL |  | 10,862 |  |

Note:  Projects that do not have an interconnection agreement but have been publicly disclosed via a Public Letter to ERCOT and were previously reported on this table have been moved to section 1.5 unless Suspended or Cancelled

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | SiteName | Status | County | Region | COD | Fuel | MW For Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 14INR0005 | White Stallion Energy Center | XX | Matagorda | South | Jul-14 | Coal | 1,200 | Cancelled |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12INR0079 | Kenedy | 200 | Oct-12 | Wind |  | 12INR0089 | Pecos | 230 | Nov-12 | Wind |
| 11INR0093 | San Patricio | 41 | Dec-12 | Wind |  | 12INR0055 | Baylor | 80 | Dec-12 | Wind |
| 12INR0060 | Schleicher | 58 | Dec-12 | Wind |  | 13INR0054 | Bexar |  | Jan-13 | Gas |
| 13INR0040 | Harris |  | Jan-13 | Gas |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 13INR0045 | Castro | 288 | Apr-13 | Wind |  | 12INR0070 | Knox | 300 | Apr-13 | Wind |
| 11INR0094 | Kent | 100 | Apr-13 | Solar |  | 10INR0089 | Harris | 40 | May-13 | Storage |
| 12INR0086 | Fort Bend | 89 | May-13 | Gas |  | 13INR0058 | Bexar | 50 | May-13 | Solar |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 13INR0032 | Andrews | 30 | Jun-13 | Solar |  | 13INR0057 | Archer | 65 | Jun-13 | Wind |
| 13INR0049 | Harris | 352 | Jul-13 | Gas |  | 13INR0046 | Limestone | 71 | Sep-13 | Wind |
| 11INR0082A | Val Verde | 50 | Sep-13 | Wind |  | 11INR0083A | Crockett | 50 | Sep-13 | Wind |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 14INR0030a1 | Carson | 322 | Nov-13 | Wind |
| 14INR0030a2 | Carson | 322 | Nov-13 | Wind |  | 12INR0071 | Caldwell | 30 | Nov-13 | Wind |
| 13INR0038 | Swisher | 300 | Dec-13 | Wind |  | 13INR0050 | Comanche | 200 | Dec-13 | Wind |
| 11INR0062 | Nueces | 178 | Dec-13 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-13 | Wind |
| 13INR0052 | Starr | 200 | Dec-13 | Wind |  | 13INR0055 | Zapata | 250 | Dec-13 | Wind |
| 10INR0009 | Castro | 300 | Dec-13 | Wind |  | 11INR0085 | Nolan | 106 | Dec-13 | Wind |
| 12INR0054 | Jones | 200 | Dec-13 | Wind |  | 12INR0059 | Pecos | 50 | Dec-13 | Solar |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 13INR0026 | Oldham | 201 | Dec-13 | Wind |
| 13INR0030 | Archer | 100 | Dec-13 | Wind |  | 13INR0039 | Castro | 500 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 11INR0057 | Cameron | 165 | Dec-13 | Wind |
| 12INR0068 | Jim Hogg | 80 | Dec-13 | Wind |  | 12INR0088 | Crosby | 201 | Dec-13 | Wind |
| 13INR0048 | Oldham | 161 | Dec-13 | Wind |  | 14INR0013 | Cameron | 103 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 12INR0084 | Randall | 242 | Jan-14 | Wind |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 14INR0014 | Val Verde | 100 | Jan-14 | Solar |
| 13INR0010b | Parmer | 500 | Jan-14 | Wind |  | 14INR0027 | Guadalupe | 471 | May-14 | Gas |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0011 | Swisher | 270 | Jun-14 | Gas |
| 14INR0012 | Gray | 401 | Jun-14 | Wind |  | 14INR0015 | Harris | 192 | Jun-14 | Gas |
| 14INR0016 | Harris | 190 | Jun-14 | Gas |  | 12INR0085 | Stonewall | 24 | Jul-14 | Wind |
| 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |  | 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |
| 09INR0034 | Coryell | 200 | Oct-14 | Wind |  | 13INR0031 | Austin | 30 | Oct-14 | Solar |
| 14INR0023 | Briscoe | 361 | Dec-14 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-14 | Wind |
| 14INR0009 | Kent | 248 | Dec-14 | Wind |  | 14INR0018 | Nolan | 35 | Dec-14 | Solar |
| 14INR0020 | Floyd | 150 | Dec-14 | Wind |  | 10INR0085 | Ector | 40 | Dec-14 | Solar |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 11INR0079a | Clay | 200 | Dec-14 | Wind |
| 08INR0031 | Childress | 120 | Dec-14 | Wind |  | 12INR0029 | Swisher | 500 | Dec-14 | Wind |
| 13INR0010c | Parmer | 500 | Jan-15 | Wind |  | 12INR0057 | Ector | 40 | Apr-15 | Solar |
| 15INR0013 | Anderson | 324 | Oct-15 | Gas |  | 15INR0014 | Matagorda | 280 | Oct-15 | Gas |
| 11INR0065 | Nueces | 240 | Oct-15 | Wind |  | 15INR0015 | Pecos | 140 | Dec-15 | Solar |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 12INR0018 | Gray | 500 | Dec-15 | Wind |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 11INR0040 | Freestone | 640 | Mar-18 | Gas |
| 14INR0003 | Nolan | 850 | Jun-18 | Coal |  |  |  |  |  |  |

Note:  ERCOT recently requested that the Transmission Service Providers comprehensively review the status of each of their assigned Full Interconnection Studies and report the status of each study back to ERCOT.  Projects that were classified as “Cancelled” or “Suspended” as a result of this review are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- South Texas Electric Cooperative (STEC) submitted the Karnes Electric Cooperative (KEC) and Medina Electric Cooperative (MEC) load addition project to accommodate 245 MW of new load in Karnes and Atascosa Counties. This is a Tier 1 project that is estimated to cost $57 million. The ERCOT Independent Review was completed in August 2012. The ERCOT Board of Directors endorsed the project on September 18, 2012, and ERCOT has sent the approval letter.

- AEPSC has submitted the Airline/North Padre Island Area Improvements project. This project is submitted as a revision to the Barney Davis to Laguna 138 kV line (AEPSC Corpus Christi Improvements Project ) that was endorsed by ERCOT in November 2009. This is a Tier 1 project that is estimated to cost approximately $58.1 million. This project is currently under ERCOT independent review.

- CPS Energy has submitted the TCC Transmission project to support load growth on the west side of San Antonio.  The project is Tier 2 project estimated to cost $10.9 million.  This project is currently under ERCOT independent review.

- Sharyland has submitted the Atlas-Driver Load Integration project, this is a Tier 2 project that is estimated to cost approximately $15.4 million. This project is currently under ERCOT independent review.

- American Electric Power Service Corporation (AEPSC) has submitted the Sinton-Beeville-Kenedy Area Improvements project to accommodate load additions due to Eagle Ford Shale development in South Texas.  This is a Tier 1 project that is estimated to cost $89.2 million. This project is currently under ERCOT independent review.

- South Texas Electric Cooperative (STEC) has submitted the Coy City Load Addition project to accommodate load additions due to Eagle Ford Shale development in South Texas. This is a Tier 3 project that is estimated to cost $11.65 million. This project has been submitted for RPG comments.

- CenterPoint Energy has submitted the Fort Bend Area Upgrades project, this is a Tier 3 project that is estimated to cost approximately $16.9 million. This project has been submitted for RPG comments.

- LCRA TSC, Guadalupe Valley Electric Cooperative (GVEC), American Electric Power (AEP), and South Texas Electric Cooperative (STEC) have jointly submitted the Kenedy Switch to Nixon to Seguin Line Upgrade, this is a Tier 1 project that is estimated to cost approximately $55.3 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 16905 | 0 - 2800 | 133,960,488 | 5YTP [2010-R7, R8] 12TPIT0214, 13TPIT0136 |
| Quail Switch - Odessa EHV 345 kV & Longshore Switch - Odessa EHV 345 kV; Golden Switch - Sun Switch 138 kV; Falcon Seaboard - Midland East 345 kV; etc. | China Grove - Bluff Creek 138 kV | 1591 | 0 - 3500 | 31,578,851 | 13TPIT0098, 13TPIT0093 |
| BASE CASE | West to North Stability Limit | 8142 | 0 - 436 | 26,901,966 | CREZ |
| Batesville Switching Station - Paloduro Substation 138 kV; Batesville 138/69 kV Autotransformer; West Batesville - Uvalde 138 kV; etc | Moore Switching Station - Downie Switching Station 138 kV | 1971 | 0 - 3500 | 20,422,574 | 08TPIT0018 |
| Midland East - Odessa EHV 345 kV; or Moss Switch 345/138 kV Autotransformer | Odessa - Odessa North 138 kV | 609 | 0 - 3500 | 18,830,852 | 14TPIT0054 |
| Twin Buttes 345/138 kV Autotransformer | San Angelo Red Creek 345/138 kV Autotransformer 2 | 113 low-side; and 262 high-side | 19 - 3500 low-side; and 2 - 4500 high-side | 18,360,051 | 14TPIT0067 |
| Kyle - San Marcos 138 kV; or Lytton Spring - Zorn 345 kV & Austrop - Zorn 345 kV | Turnersville - Buda 138 kV | 568 | 0 - 3500 | 17,352,442 | 09TPIT0060 |
| Lewisville Switch - Carrollton Northwest 345 kV; or Lewisville Switch - Carrollton Northwest 345 kV double-circuit | Lewisville Switch - Jones Street TNP 138 kV | 4666 | 0 - 3500 | 17,099,428 | 12TPIT0209, 12TPIT0210 |
| North Alvin - Meadow 138 kV; PH Robinson 345/138 kV Autotransformer A2; or PH Robinson 345/138 kV Autotransformer A4 | PH Robinson 345/138 kV Autotransformer A1 | 48 low-side; and 280 high-side | 0 - 3500 low-side; and 1 - 4500 high-side | 12,216,587 | 14TPIT0077 |
| China Grove - Bluff Creek 138 kV; West Over - Odessa 138 kV; etc. | Moss - Amoco North Cowden Tap 138 kV | 469 | 0 - 3500 | 9,686,322 | 13TPIT0098, 13TPIT0093 |

Binding Constraints – Sep 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 2248 | 0 - 2000 | 19,319,292 | 5YTP [2010-R7, R8] 12TPIT0214, 13TPIT0136 | MP is in place |
| North Alvin - Meadow 138 kV; or PH Robinson 345/138 kV Autotransformer A2 or A4 | PH Robinson 345/138 kV Autotransformer A1 | 42 low-side; and 280 high-side | 0 - 3500 low-side; and 1 - 4500 high-side | 11,742,210 | 14TPIT0077 | Planned Outage on PH Robinson Auto A2 and Forced Outage on PH Robinson Auto A3 |
| La Palma - Los Fresnos 138 kV | La Palma - Villa Cavazos 138 kV | 48 | 3500 - 3500 | 2,940,963 |  | Outage of Price Road - Loma Alta 138 kV |
| Camp Springs Energy Center - Golden Switch 138 kV; or Green Mountain Energy Wind Farm at Brazos - Sun Switch 138 kV | Morgan Creek SES - Sun Switch 138 kV | 53 | 545 - 3500 | 2,839,374 |  |  |
| Midland East - Odessa EHV 345 kV | Odessa North - Odessa 138 kV | 68 | 0 - 3500 | 2,650,530 |  |  |
| Amoco North Cowden Tap - Moss 138kV | Odessa North - Odessa Basin Switch 69 kV | 225 | 0 - 2800 | 2,358,599 |  |  |
| Meadow - PH Robinson 345 kV | North Alvin - Alvin 138 kV | 344 | 0 - 3500 | 2,332,639 | 13TPIT0079 | Planned Outage on PH Robinson Auto A2 and Forced Outage on PH Robinson Auto A3 |
| Lewisville Switch - Carrollton Northwest 345 kV double-circuit | Euless - Grapevine Highway 360 138 kV | 71 | 0 - 3500 | 2,317,992 | 11TPIT0012 |  |
| Golden Switch - Sun Switch 138 kV; or Morgan Creek SES - Sun Switch 138 kV | China Grove - Bluff Creek 138 kV | 76 | 0 - 3500 | 2,131,841 | 13TPIT0098, 13TPIT0093 |  |
| Lewisville Switch - Carrollton Northwest 345 kV double-circuit; or Lewisville Switch - Carrollton Northwest 345 kV (from Roanoke) | Jones Street TNP - Lakepointe TNP 138 kV | 333 | 0 - 3500 | 1,403,440 | 12TPIT0210 |  |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Data Set B work began on August 1, 2012 with a Topology Processor case extracted from NMMS with a build date of January 1, 2013.  Process is underway with creation of Pass 1 cases on Aug 31, 2012.

- The short term calendar of major planning model events follows:

  - Oct 15, 2012	Data Set B cases posted.

  - Oct 19, 2012	Begin Sept TPIT update to 12 DSA and 13 DSA cases.

  - Nov 16, 2012	Post Sept TPIT update to 12 DSA and 13 DSA cases.

  - Nov 30, 2012	Begin Contingency database update for 13 DSA and DSB cases.

  - Dec 19, 2012	Post Contingency database update for 13 DSA and DSB cases.

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  Item 1 considered to be in production.  The first draft of Requirements for Item 6 have been completed by ERCOT, reviewed by SSWG, and sent to vendor for review.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- All of the n-1 reliability projects for the 2012 Five-Year Transmission Plan have been identified and the results were sent to the TO’s for comments on Sept. 21, 2012. ERCOT Staff is current working on the g-1 + n-1 screening studies.