## Slide 1
Business Integration Update to PRS
October 18, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-9
    Upcoming Project Implementations
    2012 Release Targets
      Additions/Revisions in red text
      Prior target release dates in strike-through text
    2013 Release Targets
    Project Spending Update
    2013 Revision Request Funding Reconciliation
  Appendix
    Project Portfolio Gantt Chart p. 11-15
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in October (R5) (10/16/2012 – 10/18/2012)
  UC4 Automation Upgrade
    Batch job scheduling software
  Contingency Functionality Enhancements
    Provide a more granular level in defining contingency groups
  ADP-IDM Interface
    Interface between back office ERCOT applications
Go-Lives in November (off-cycle software release)
  NPRR347 – Single Daily Settlement Invoice and Updates to Credit Calculations, including addition of a Minimum Collateral Exposure Component
  NPRR365 – Change in Resource Outage Approvals from Eight to 45 Days
  NPRR400 – Eliminate Unsecured Credit for CRR Auctions and for Future Credit Exposure and Eliminate Netting of FCE with CCE
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 | NPRR365 | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 NPRR464
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) | NPRR357 NPRR430 |  | NPRR347 NPRR365 NPRR391 NPRR400 | NPRR222
Counts Total = 43 | 5 | 5 | 10 | 8 | 0 | 12 | 2
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
November
Mid-Sept
Early June
None
Early Oct
None
Deleted
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle |  | NPRR207 NPRR416 NPRR419 NPRR439 NPRR463 | NPRR272 NPRR393 NPRR457 SCR769 SCR770 | NPRR207 NPRR327 NPRR407(b) NPRR416 SCR760(d) | NOGRR084 SCR771 |  | SCR756(b)
Off-Cycle |  |  |  |  |  |  | NPRR455
Counts Total = 17 | 0 | 3 | 5 | 5 | 2 | 0 | 2
None
None
None
None
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
2014 TBD
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 6: Project Spending Update
PPL – 2012 Project Categories | Portfolio Budget (effective 1/1/2012) | 2012 YTD Actual (as of 9/30/2012) | 2012 Spending Projection of In-Flight Projects (as of 9/30/2012) | Current 2012 Demand (as of 9/30/2012)
Business Strategy |  | $ 4,640,716 | $ 5,866,212 | $ 6,049,127
Regulatory |  | $ 891,021 | $ 952,060 | $ 981,746
Efficiencies/Enhancements |  | $ 2,029,927 | $ 2,542,955 | $ 2,622,247
Technical Foundation |  | $ 4,627,879 | $ 6,374,312 | $ 6,573,070
Totals | $ 15,000,000 | $ 12,189,543 | $ 15,735,539 | $ 16,226,190
ERCOT Public
Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that are in-flight or are complete
Current 2012 Demand: Total cost of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: 2013 Revision Request Funding Reconciliation
2013 Target Funding for Revision Requests = $3.0M
2013 Revision Request Funding – Board Approved = ($1.9M)
  NPRRs: 207, 272, 327, 393, 407, 416, 419, 439, 457, 463
  NOGRRs: 084
  SCRs: 760, 769, 770, 771
2013 Revision Request Funding – In Stakeholder Process = ($0.6M)
  NPRRs: 153, 210, 240, 256, 340, 425
  NOGRRs: 093
  SCRs: 756
“Remaining” 2013 Revision Request Funding = $0.5M

## Slide 8: 2013 Revision Request Funding – Board Approved
Source Doc | Revision Request | Budget Range
SCR760 | Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models | $400k-$500k
NOGRR084 | Daily Grid Operations Summary Report | $300k-$500k
NPRR416 | Removal of the RUC Clawback Charge for Resources Other than RMR Units | $225k-$250k
NPRR272 | Definition and Participation of Quick Start Generation Resources | $125k-$150k
NPRR327 | State Estimator Data Redaction Methodology | $120k-$150k
NPRR439 | Updating a Counter-Party's Available Credit Limit for Current Day DAM | $120k-$130k
SCR769 | CRRAH Digital Certificate New Role for Read Only Access | $100k-$110k
SCR771 | ERCOT System Change Allowing Independent Master QSE to Represent Split Generation Resources | $95k-$110k
NPRR407 | Credit Monitoring Posting Requirements - CRR Portion | $90k-$110k
SCR770 | Revision to Outage Scheduling Entry for Resource Maintenance Outage Level Designation | $90k-$105k
NPRR393 | SCED Constraint Management Transparency | $80k-$85k
NPRR463 | CRR Auction Structure Enhancements | $60k-$80k
NPRR457 | Daily Update of New ESI IDs and AMS Meter and Switch Hold Indicators Changes | $45k-$65k
NPRR207 | Unit Deselection | $45k-$55k
NPRR419 | Revise Real Time Energy Imbalance and RMR Adjustment Charge | $15k-$25k

## Slide 9: 2013 Revision Request Funding – In Stakeholder Process
Source Doc | Revision Request | Budget Range
NPRR425 | Creation of a WGR Group for GREDP and Base Point Deviation Evaluation | $250k-$350k
NPRR256 | Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards | $100k-$250k
SCR756 | MarkeTrak Enhancements - Remaining SCR756 Items | $50k-$100k
NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | $50k-$100k
NPRR240 | Proxy Energy Offer Curve | <$50k
NOGRR093 | Synchronization with NPRR365 | $20k-$25k
NPRR340 | Introduction and Definition of Duration-Limited Resources | $15k-$20k
NPRR153 | Generation Resource Fixed Quantity Block Offer | $12k-$16k

## Slide 10: Business Integration Update – Appendix
  Appendix
    10/12/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 11
Project Portfolio Status – as of 10/12/2012

## Slide 12
Project Portfolio Status – as of 10/12/2012

## Slide 13
Project Portfolio Status – as of 10/12/2012

## Slide 14
Project Portfolio Status – as of 10/12/2012

## Slide 15
Project Portfolio Status – as of 10/12/2012