## Slide 1
Business Integration Update to PRS
November 15, 2012

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-6
    Upcoming Project Implementations
    2012 Release Targets
    2013 Release Targets
    Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 7-12
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Go-Lives in November (off-cycle software release)
  NPRR347 – Single Daily Settlement Invoice and Updates to Credit Calculations, including addition of a Minimum Collateral Exposure Component
  NPRR365 – Change in Resource Outage Approvals from Eight to 45 Days
  NPRR400 – Eliminate Unsecured Credit for CRR Auctions and for Future Credit Exposure and Eliminate Netting of FCE with CCE
Go-Lives in December (R6) (12/5/2012 – 12/9/2012)
  NPRR260 – MIS Secure Access
  NPRR322 – Real-Time PTP Option Modeling
  NPRR377 – Alternate Inputs to Base Point Deviation Charge
  NPRR397 – Balance of the Day Ancillary Service Market
  NPRR407 – Credit Monitoring Posting Requirements (MMS/CDR portion)
  NPRR464 – SASM Procurement Reporting
  NPRR469 – Modifications to CCTs
  SCR768 – Automatic Non-Spin Redeployment and Deployment Based on Resource Availability
  Security and Reliability Compliance Business Enterprise Tracking and Support Software
  Cyber Security Project #1
  Macomber Map NERC/SA Compliance Enhancements
  MAI Conversion to iGrid
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 12/2012 | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 |  | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) | NPRR357 NPRR430 |  | NPRR347 NPRR365 NPRR391 NPRR400 | NPRR222
Counts Total = 41 | 5 | 5 | 10 | 8 | 0 | 12 | 1
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
November
Mid-Sept
Early June
None
Early Oct
None
Deleted
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle | NPRR313 | NPRR419 NPRR439 NPRR456 NPRR463 | NPRR272 NPRR393 NPRR457 SCR769 SCR770 | NPRR207 NPRR327 NPRR407(b) NPRR416 NPRR439 SCR760(d) | NOGRR084 SCR769 SCR771 |  | NPRR419 SCR756(b)
Off-Cycle |  |  |  |  |  |  | NPRR455
Counts Total = 19 | 1 | 2 | 4 | 6 | 3 | 0 | 3
None
None
None
None
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
2014 TBD
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 6: Project Spending Update
PPL – 2012 Project Categories | Portfolio Budget (effective 1/1/2012) | 2012 YTD Actual (as of 10/31/2012) | 2012 Spending Projection of In-Flight Projects (as of 10/31/2012) | Current 2012 Demand (as of 10/31/2012)
Business Strategy |  | $ 4,880,936 | $ 5,822,502 | $ 5,957,698
Regulatory |  | $ 993,862 | $ 1,053,044 | $ 1,071,165
Efficiencies/Enhancements |  | $ 2,479,248 | $ 2,692,767 | $ 2,744,105
Technical Foundation |  | $ 5,200,154 | $ 6,485,544 | $ 6,683,455
Totals | $ 15,000,000 | $ 13,554,200 | $ 16,053,857 | $ 16,456,423
ERCOT Public
Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that are in-flight or are complete
Current 2012 Demand: Total cost of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: Business Integration Update – Appendix
  Appendix
    11/9/2012 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 8
Project Portfolio Status – as of 11/9/2012

## Slide 9
Project Portfolio Status – as of 11/9/2012

## Slide 10
Project Portfolio Status – as of 11/9/2012

## Slide 11
Project Portfolio Status – as of 11/9/2012

## Slide 12
Project Portfolio Status – as of 11/9/2012