| Flight Schedule for Version 4.0 Flights in 2012 | 0312 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Jan. 18, 2012 |
| Signup begins | Feb. 15, 2012 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com | Feb. 22, 2012 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Feb. 24, 2012 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Feb. 24, 2012 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Feb. 24, 2012 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Feb. 27, 2012 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | Feb. 28, 2012 |
| Connectivity and Penny (if applicable) Testing begins for all Testing Participants | Feb. 28, 2012 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Mar. 19, 2012 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Mar. 23, 2012 |
| Day 1 Transactions flow | Mar. 26, 2012 |
| Flight tentatively scheduled to conclude | May 8, 2012 |
| Contingency Testing scheduled to conclude (blackout starts) | May 25, 2012 |
| PROD implementation scheduled for TX SET V4.0 | Jun. 3, 2012 |
| Contingency PROD implementation scheduled for TX SET V4.0 | Jun. 10, 2012 |

| Flight Schedule for Version 4.0 Flights in 2012 | 0912 |
| --- | --- |
| Activity | Calendar Date |
| Notice from ERCOT Retail Client Services of the next flight for Retail Market Testing sent to ERCOT lists.ercot.com distribution | Jul. 18, 2012 |
| Signup begins | Aug. 15, 2012 |
| FLIGHT DEADLINE The following 4 steps must be completed by 5pm cpt. on the deadline: CR must have submitted ERCOT LSE Application and Application Fee CR must have filed for PUC REP Certification TW updated on ERCOT Retail Testing Website Send an e-mail of intent to test to ERCOT at: RetailMarketTesting@ercot.com The following steps must be completed by 5pm cpt. on the deadline for current MPs: TW updated on ERCOT Retail Testing Website Send an email of intent to test to ERCOT at: RetailMarketTesting@ercot.com | Aug. 22, 2012 |
| ERCOT Retail Client Services verifies that each new Testing Participant has completed Registration testing requirements with ERCOT | Aug. 24, 2012 |
| Verification and communication from PUCT Staff that Testing Participants intending to test have applied for REP Certification | Aug. 24, 2012 |
| Communication from ERCOT Flight Administrator of Testing Participants to each TDSP | Aug. 24, 2012 |
| TDSPs and ERCOT have completed communication of connectivity testing schedule to each Trading Partner | Aug. 27, 2012 |
| Connectivity Testing Kick Off Conference Call - Mandatory for all Testing Participants (blackout ends) | Aug. 28, 2012 |
| Connectivity and Penny (if applicable) Testing begins for all Testing Participants | Aug. 28, 2012 |
| TDSPs communicate Test bed load to Trading Partners and ERCOT | Sept. 17, 2012 |
| Flight Kick Off Conference Call - Mandatory for all Testing Participants | Sept. 21, 2012 |
| Day 1 Transactions flow | Sept. 24, 2012 |
| Flight tentatively scheduled to conclude | Nov. 6, 2012 |
| Contingency Testing scheduled to conclude (blackout starts) | Nov. 21, 2012 |